## Sheet1
CONTACT REPORT
Attendees | Connect Marketing | Project | TUCP FIRST MEETING FOR 2016
INK Business Design Team | Femi Odewunmi, CEO
Ikechukwu Okwechime, Head Marketing
Olamide
PR
No Surprises (NS) | Funmi Victor-Okigbo
Orby Ndubisi
Ope Aremo
Date | 2016-01-21 | Time (from/to) | 2.30pm - 4.15pm
Venue | INK Business Design
| Discussion |  | Remarks
1 | TUCP 2015 Evaluation: Evaluation of TUCP started with discussion on what we did right and what went wrong at TUCP 2015. What went wrong - The event flow. Having to move from the main venue to the after party venue killed the morale for a lot of the guest. - It was agreed that the late timing lead to the decrease in number of people that were available for the after party. - There was also concerns about the choice of artist (the upcoming ones) and the artist performance flow.
2 | Preliminary Plans for TUCP 2016: TUCP 2016 is an opportunity for the team to put more effort in content, production, quality and press release for the event. - Product concept and preparation to start from July 2016 with ideas already building up such TUCP 2016 theme announcement, Event date, Artist line up, Friends of TUCP, Engaging activities to create awareness and build anticipation. Also, it was suggested that the band for the day should do cover songs of old cultural music and MCs should come out from different sides of the hall instead of from one angle. To create awareness, an idea was suggested by Mrs Folawiyo to have a christmas tree in July in Falomo. This will raise questions, awareness and anticipation in the mind of the public. Another awareness idea is the CEO Selfless. This involves the CEOs competition and also donation to charity. Emphasis was also made on photography, marketing videos and social media marketing. We want to do everything possible to have TUCP on the calendar of previous attendees and new ones. An event that registers in the mind of all.
3 | Post Card Concept: The idea behind the post card concept is to create a "wish you were here postcard" attached with The Unofficial Chronicles and forward to companies who were not able to make it for TUCP 2015 and companies we are targeting for TUCP 2016. It was also suggested that another magazine should be done which shows in full details the excitement, thill and fun of TUCP 2015 and reasons not to miss TUCP 2016.
4 | Google Form: A google form page was suggested to be created on the menu of the TUCP website. This is a questionnaire to enable us have the details of Tthe Unoffficial Chronicles subscribers and what they would like to see in upcoming editions of the magazine.
5 | The Future for The Unofficial Chronicles Magazine: The future for The Unofficial Chronicles is to make it a quarterly magazine to engage companies and keep TUCP converstaion going. Content plan for the magazine is very important as the focus should entail office culture and office related issues. Emphasis was also made on advert and sponsorship to finance the magazine. Then finally a superdupa end of the year magazine.
| NEXT STEPS | RESPONSIBILITIES
1 | PR Mrs Folawiyo is to send the concept note for The Unofficial Chronicles Magazine.
2 | INK Business Design team is to forward a draft of the Post Card Concept to the team.