## Sheet1
NS Project Overview | [10 empty] | Late Events
Ongoing Events
EVENT | BRIEF DESCRIPTION | VENUE | GUEST SIZE | START TIME | CLIENT | DATE | NS CONTACT | CLIENT CONTACT | STATUS | NEXT STEPS | Events on hold
ICCD (International center for communication design) | Training institute that serves to develop individuals and institutions in event planning, art, communications, photography, fashion and e-business. |  |  |  | OOTC | 2016-04-01 | Ope | Orby/FVO | ICCD is working towards affiliating with Event Management Training Limited UK. This affiliation will boost the reputation and prestige for the two day training on Special Event Management. A letter has been composed and forwarded to FVO through Orby Website is now live. Project has been included on NS project dashboard on Google Drive. Brief has been sent to the team; implementation plan has been sent to FVO for review. | Get approval of the letter from FVO, then forwarded to Event Management Limited
Alumni Awards Gala Event | International Education themed project which aims to celebrate Nigerian UK alumni who have successfully completed their courses in UK institutions (including via distance and online learning) and are making meaningful contributions to the development of their local environments in Nigeria | Intercontinental Hotel | 200 |  | TBD | March 4th | Seun D/Orby | Sephora Imomoh | The event will hold on the 4th of March at Intercontinental hotel. Reference letters have been sent and budget has been prepared and sent to client. | Follow up on client regarding payments. Follow up on Fara and Zara regarding the centerpieces to be used.
40th Birthday Party | A casual birthday party for Mr Ademola. Simple but classy event, nothing over the top | Villa Medici | 120-150 | 18:00 | Mrs Ajumogobia | 27th | Orby | Mrs Ajumogobia | Venu has been changed to Villa Medici. A walkthrough of the venue has been done by the decorator. | Follow up on client regarding payment.
Mania magazine Launch Party | Bi-monthly event to launch the lastest Mania magazine issue | LilyGate, Lekki | 150 | 18:00 | Mania | TBD | Seun I | Mr. Amadi-Obi | Last event held on Sunday 29th Nov, client is yet to give us a date for the next one. A follow up mail will be sent to client to confirm intended date. | The event will not hold for February launch but we look forward to April. Awaiting response from Mr Kelechi and FVO discussion.
A Day in The Life |  |  |  |  | British Council | 2016-02-01 | Orby/Seun D | Sephora Imomoh | A pitch has been done for this event but yet to receive feedback from the client. The event has been postponed but no new date has been communicated yet. | Send client NS Tax clearance, this should be done by the finance department
The Bridal Circle Event with Jeff Leatham | Workshop/Seminar for HNIs and industry related stakeholders to enable them explore fresh strategies, inspire and dream on new levels | Wheatbaker Hotel |  |  | OOTC | Mar 2016 (TBD) | Orby/FVO/ | Sade Awe | The event will take place at the Wheatbaker Hotel. A press conference and photoshoot for Sade held last week. Invitations are being printed out. Jeff Leatham will be in the country on the 20th of March. | Set up a meeting with decorator for a live presentation. Meet with Lanre Dasilva at the venue to run through the logistics
NBA Conference | [5 empty] | TBD | Orby/FVO
Human Capital Summit | A workshop/seminar for HR professionals. Its a three day event with an award show on the last day. | Landmark | 1500-2000 | 8am-5pm | Mrs Erefa Fynecontry-Coker | April 21st-23rd | Cecilia/Seun I |  | A second meeting was held with the client at the venue. Program has been sent in by the client and a budget has been prepared for this event. | Send budget to client and follow up on payment.
OBI WORLDPHONE | A mobile phone launch. It will consist of media,trade and consumer launch | Civic Center | 500 | TBD | Zainab | March but TBD |  |  | A pitch was done, yet to receive feedback from the client on a go ahead. A budget has also been prepared and sent to the client. | Follow up with client regarding a promt positive decision.
Oh So Nutrition |  | TBD | 40 |  |  |  | Ope |  | Presentation has been prepared by the team, waiting for sign off from FVO. | Prepare a budget and send to client.
Partner Connect Conference | A conference for top No Surprises consistence service providers for the purpose of networking, training and job referrals. | TBD | TBD |  | NS | June 2016 (TBD) | Seun I/Seun D |  | To pick a day in June and to select the venue for the event.
TUCP 2016 | Shared end of year celebration for corporates. Gives businesses a platform to reward their staff with a premium Christmas party without the expense of doing it alone on such a grand scale and with considerably more glamour and style than most companies can manage on their own. |  |  |  | NS | Friday, 16th Dec | Orby/FVO | FVO/Orby | A meeting was set up with a Creative Consultant - Niyi to join forces with TUCP team to create a campaign strategy including content development to foster engagement, exciting and thrill for TUCP 2016 and in the process create lead generation and customer rentention for the brand. | Send magazines with postcards inserted in them to prospective companies that would like to attend TUCP 2016 - Following the meeting we should expect a brief presentation from Niyi and further discuss will be done based on engagement and online conversation.