## JLE
THE JEFF LEATHAM EXPERIENCE PRODUCTION SCHEDULE
21ST AUGUST
THE WHEATBAKER LAGOS
DATE | TIME | ACTION | RESPONSIBLE
20th March | 11pm | Band crew to move equipment (including sound) into the venue | Adey/JLET
| 11pm | Décor crew moves in equipment (stage pedestals for flowers) | Sara O/JLET
| 11pm | Aralia by Nature moves in equipment | Aralia/JLET
| 11pm | DJ moves in equipment | DJ/JLET
| 11pm | Hotel staff move in equipment (rectangular tables and white table cloth) | DJ/JLET
| 11pm | JLE team to move to site and supervise | JLET
21st March | 12am | Setup Begins | Aralia/Adey/Lucere/JLET/DJ
| 6am | AAA sets up screens in main hall | Wale/JLET
| 6am | GEMs arrive at the venue | Cecilia/JLET
| 6am | Brief and coordinate security | Oliver/JLET
| 6am | Set up of Registration Desk and sorting of name badges per table | Cecilia/JLET
| 7am | Final training and walk through with hostesses | Cecilia/JLET
| 7am | Ensure guest list is received and sorted and guests are called to RSVP | Cecilia/JLET
| 7AM | Equipment check; ensure all gadgets and screens are tested and working | Lucere/JLET
| 7AM | DJ arrives | Lucere/JLET
| 7:45am | Ushers take position | Cecilia/JLET
| 8am | Guests arrive and registration begins | JLET
| 9:45am | Transitioning from tables setting to Jeff's floral masterclass setting | Aralia/Angelika's/JLET
| 10am | Grillroom is setup for press conference and book signing | Oliver/JLET
| 1pm | Sara O begins décor setup; black carpet area inclusive | Sara O/JLET
| 2pm | Aralia by Nature begins floral setup | Aralia/JLET
| 2pm | Angelika's begins table setup | Angelika's/JLET
| 2pm | Mannequins and outfits arrive | LDA/JLET
| 3pm | Mannequins and outfits are setup | LDA/JLET
| 3pm | Follow through with feeding plan for ushers and crew | Cecilia/JLET
| 5pm | Sound check | Lucere/DJ/Band
| 6:30pm | GEMs are positioned
| 7pm | Check In begins
| 11pm | Oversee event shutdown | JLET