## Checklist
Jeff Leatham Experience Quick checklist/Status
Item | Task | Responsibility | Status | Comments
Ticket Sales
| Following up with prospects, phone calls, social media monitoring, bulk smses etc. | JLE |  | All guests who have been previously contacted have been sent emails and smses regarding the event. 97 industry guests have been called and informed about the subsidized rate, out of which 7 have paid
| Invitation card addressing | JLE |  | VIP Invitations are being addressed as payment is made. 20 invitations have been addressed
| Invitation card delivery | JLE |  | Deliveries are being made as invitations are being addressed. 12 VIP invitations have been delivered and 7 industry invitations have been emailed
| Invitation letter personalising | JLE |  | All the invitation letters have been personalised and sent to Mrs. Folawiyo. A general letter was also created and shared with Mrs. Ashiru
| Compiling a guest list | FVO/JLE |  | A list has been compiled and shared with FVO. 41 names are currently on the guest list, out of which we await payment from 3
Jeff Leatham's hospitality
| Obtain Jeff Leatham's hospitality rider | Sade/JLE |  | This is yet to retrieved from Sade, we have requested for this repeatedly, JLE to escalate to FVO
| Obtain Jeff Leatham's measurements from Sade | Sade/JLE |  | Initally, The Okunoren Twins Ltd was to prepare a traditional outfit for JL, however, Sade would prefer a suit being made for Jeff rather than a traditional attire. Sade still hasn't sent the measurements, and the Okunorens are not around however Vanguard is to handle his wardrobe for the photoshoot. JLE to finalise on Jeff's wardrobe management
| Ensure Jeff's needs are met | JLE |  | Olaide is the contact person for the hotel and has been informed in an email about Jeff's needs and requirements. JLE team is in sync with the hospitality team
| Finalise Jeff's airport and pick up | Ata/JLE |  | JLE to get feedback from Mrs Ashiru on this latest BCOB on Wednesday, 16th March
Event Staffing
| Determine and secure staffing for the event | JLE |  | 4 GEMs have been selected to work with the efficient Wheatbaker staff for this event. Pictures of the GEMs have been sent to FVO for approval.
| Determine outfits for Morning and evening event | JLE |  | Cecilia has been briefed about who GEMs are and the outfits they will be wearing. Suggestions made were: Morning - T-shirt, black blazer and jeans trouser. The blazers will have JLE badge. Evening - Black and white jumpsuit. Pictures have also been sent to FVO for approval
| Determine registration/check in methods, positioning etc. | JLE |  | Check in area will be positioned just before the Grillroom, where guests will be checked in before they go in for breakfast. Registration for VIPs: Admittance through the pass in their invitation. Time: 8am Registration for Industry: Admittance through the verified QR code on their invitation. Time: 9:30am
Branding and printing
| Determine what to be printed Signs "Welcome to the Jeff Leatham Experience Lagos, Backdrop, Brochures with Partner logos and speakers photos? | FVO/JLE |  | Photos and bios have been gathered from partners and ambassadors. Mrs. Ashiru has designed the profiles that will be placed in the brochures. Rollup banner to be used (tentatively) at the entrance of the venue. Jimmy has been informed about the backdrop and other requirements for the event. Branding information has been discussed and finalised
| Discuss invite method for industry class | JLE |  | Invitations are being sent as emails containing information about the event and unique QR codes. Both VIP and Industry masterclass will be merged. The Industry folks will be informed that the time for the event is 9:30am in order to disinvolve them from the panellist session
| Confirm all logos of partners | FVO/JLE |  | This has been confirmed and various formats saved in a folder
| Obtain design for certificate of attendance | Ata/JLE |  | Ata to produce this and has been reminded, however, another reminder will be sent to her
| Reconfirm partners logo and categories | JLE |  | Partner List has been sent to FVO and we requested the partners be categorized for the brochure and backdrop
| Printing of place cards and escort cards | Ata/JLE |  | Mrs. Ashiru has confirmed this, all branding will be retrieved by the weekend (between 18th and 20th March)
Determine and confirm décor details
| Confirm that Dior chairs have been booked | Sara O/JLE |  | The Dior chairs has been booked and confirmed with Sara O
| Confirm floor plan | All Partners/JLE |  | It has been finalized on. It is an E shaped floor plan for the dinner. Masterclass will be a classroom setting with an aisle in the middle. 1D and 3D floorplan has been shared with FVO
| Confirm morning and evening arrangement | FVO/JLE |  | 1D and 3D floorplan has been shared with FVO. Wheatbaker staff (tables), Sara O (flower pedestals on stage) and Aralia by Nature (flowers for delegates) will create the morning set up
| Confirm setting for Morning masterclass | FVO/JLE |  | Bar stools have been included to the set up for the panel. Pictures, 1D and 3D floorplan has been shared with FVO
| Confirm red carpet and lighting | FVO/JLE |  | Red Carpet (to be provided by NS) will be stationed outside the building. Sara O has confirmed to provide black carpet. Mr Mark Osho will also supply lighting for the black carpet arena
Entertainment/Technical
| Determine sound, mics lights etc. | FVO/JLE |  | A technical meeting between the JLE Lagos team, Mr. Yemi Amusan and Mr Mark Osho for Monday 14th March, 12pm at the Wheatbaker held. Details have been discussed with FVO. The band (Adey) will provide sound and PA system for the morning and evening event
| Confirm MC and Entertainment | FVO/JLE |  | Banky W's service will not be required anymore. Bovi will be contacted by FVO. Adey will be putting a band together, and he's been in touch with Dr. Amusan, the technical director
| DJ | FVO/Ata/JLE |  | Background music in the morning will be provided by the Wheatbaker; Mrs. Ashiru to provide the DJ for the evening event
| Design first draft of event flow | JLE |  | A draft event flow for both morning and evening event is now available and has been shared with FVO
| Projectors and plasma screens to show Jeff's work | Sade/FVO/JLE |  | Sade to share 300 pictures of Jeff's work to be selected from, however JLE Lagos has shared folder containing selection with FVO. 1 projector screen (to be provided by hotel and 4 44-inched plasma screens) will be provided by NS to loop photos of Jeff's work
| Content for Jeff's presentation | JLE |  | The only projection will be pictures of Jeff's work.
| Content for other speakers | FVO/JLE |  | Mrs. Amusan has supplied this to FVO and other speakers are in sync
Food and Beverage
| Make a list of all the drinks from Bollinger and confirm if they are bringing bars, how many etc. | Bollinger/JLE |  | A meeting with Bollinger held on the 14th of march. They will be providing one bar and the following drinks:  Welcome drink: Carolans Irish Cream 48 Bottles and Bollinger 30 Bottles  Dinner: Thomas Barton Bordeaux 30 Bottles and 18 Bottles of Thomas Barton Graves Blanc  After Dinner Drink: Bollinger 30 Bottles.
| Reconfirm menu details and guest size | JLE |  | A revised invoice has been retrieved from the Wheatbaker. Cost has been shared with FVO. Guest size is 50
| Obtain breakfast and tea break menu and costing | JLE |  | This has been obtained and shared with FVO
SWAGs
| Confirm status of gift items with Temidayo | JLE |  | Mystique lounge will be providing candles, scrubs and chocolates. She will also have a stand at the entrance/exit of the venue to display the items, and a large placard on an easel to help with brand visibility
| Confirm gift bags and design | Jimmy/JLE |  | Jimmy to send designs of all items on Thursday, 16th March. There will be a little card in each bag with thank you note her company name and contact number
Archival
| Confirm photography | Yasmine/JLE |  | Jide Alakija to cover this with Bayo Lawson. Bayo Lawson has been briefed on all three event days and their requirements; however Jide Alakija is AWOL and efforts and continuously being made to reach him
| Videography | Sade/JLE |  | Sade Awe has engaged a videographer at no cost to cover the event
Fashion show/presentation
| Meet with Lanre Da Silva to determine needs | LDA/FVO/JLE |  | Mrs. Da Silva hasn't taken JLE calls recently. JLE to escalate to FVO. Make up artist, models and outfit will be provided by LDA. The Wheatbaker will not be providing a room for the models to change unless payment is made, and there is no need for a backstage as all the models will come in at the same time. What shows on screens during fashion show will be confirmed with her (although JLE suggests photos of the outfits alone should be projected) Playlist will also be retrieved from her.
Flowers and stuff for masterclass
| Determine needs for masterclass | Aralia/JLE |  | All the requirements are on the rider provided by Ms. Awe. JLE to sync with Mrs. Adedoyin of Aralia by Nature
Photoshoot
| Fix date for photoshoot | Yasmine/JLE |  | Photoshoot is on Sunday, 20th March at the Wheatbaker Lagos for 2-4pm
| Ensure all branding items are confirmed and produced | Yasmine/JLE |  | Jimmy has been briefed. He will be given a go-ahead once the designs are approved
| Confirm wardrobe details for shoot | Yasmine/JLE |  | Vanguard to provide wardrobe for the shoot
| Confirm and book photographer | Yasmine/JLE |  | Bayo Lawson has been booked. Efforts are still being made to Jide Alakija
| Book finger foods for photoshoot | Yasmine/JLE |  | Kots has been informed, but hasn't been booked

## Guestlist
Jeff Leatham VIP Guest list
Name | Invitation card status | Comments
Mrs Gbemi Shasore | Addressed and Delivered
Mrs Winihin Jemide | Not yet addresssed and delivered
Titi Maybug | Not yet addresssed and delivered
Mrs Juyin Demuren | Not yet addresssed and delivered
Mrs. Mo Abudu | Not yet addresssed and delivered
Mrs Daisy Danjuma | Addressed but not delivered
Mrs Deola Bali | Not yet addresssed and delivered
Mrs Ifeoma Williams | Addressed and delivered
Mrs. Bola Balogun | Not yet addresssed and delivered
Mrs Chioma Ekeh | Not yet addresssed and delivered
Mrs Gozy Ijogun | Not yet addresssed and delivered
Ms. Mosun Ogunbanjo | Not yet addresssed and delivered
Mrs. Osayi Oruene | Not yet addresssed and delivered
Kelechi Amadi Obi
Kelechi Amadi Obi's wife
Jennifer Obayuwana's mom?
DJ Caise's mom?