## OPERATIONS
Exceed target
Date: Monday 14th March 2016 - Friday 18th March 2016 |  |  | On target
Department: Operations Department |  |  | Below target
Weekly tasks /targets | Measurement | Actual | Status | Comments
Quarterly event to appreciate suppliers/partners and request referrals | Present weekly progress report to director until event date (to include venue selection, guest list, program) |  |  | A venue has not been decided yet, we are considering Landmark but still open to more ideas.
| Ensure the event takes place on time and on schedule |  |  | A date has not yet been decided but event will hold in June
| Execute supplier appreciation event at no cost | N/A |  | Vendors have not been shortlisted for this event yet. This will be done after the venue has been booked
| Obtain at least 80% satisfaction on appraisal done by attendees | N/A |  | This will be done not less than 48 hours after the event.
Carry out post event evaluation of all suppliers engaged | Supplier/Partner evaluation form sent not more than 48 hours post event | N/A |  | No post event suppliers' evaluation yet
Venue recce/database /synergies | Recce 2 venues per week (one purpose built venue and one restaurant/diner); establish relationship with venues/diners |  |  | No recce was done this week.
Post evaluation meeting with team no later than 48hrs post event |  |  |  | Post evaluation meeting for British council event has been held.
Upload all project status on google drive | 1 | Done daily
Reduce time required to prepare quotation | 48 hours after presentation has been concluded |  |  | Human Capital summit quote was revised this week
Reduce turnaround time for client's needs from one week to 3 days (if applicable) | 48 hours after brief has been received |  |  | No brief was received this week
Send to team 1 interesting link or industry related article every week | 1st and 4th Fridays |  |  | Operations to sent an interesting link for 1st Friday of the month of March
Engage suppliers in brief interpretation and ideation (if applicable) | 48 hours after brief has been received |  |  | No brief was received this week
Reduce overhead/production cost by 20% without compromising on quality | Present vendor schedule 24 hours after budget sign off |  |  | Vendor schedule for British council was prepared and forwarded to the accounts department. Part payments have been made. Vendor to get their balance once client banlace up with NS.
Training | Facilitate training once in preselected quarter of the year and update team on progress weekly |  |  | Training is yet to be done
Departmental Punctuality Margin | 5 out of 5 | 8 of 10 |  | Seun Daley was absent on Thursday and Friday
Note on A4: @nsadmin@nosurprisesevents -seun