## Contact Report
Meeting date:
Attendees:
Event Date: December 15, 2017
Venue: Landmark Center, Oniru
Item | Comment | Next Steps | Responsibility | Deadline | Next steps | 14th June Update
What | TUXP is a large and often spectacular end of year party to which you can buy tickets. The idea is that companies of any size can throw a stunning end of year party without the underlying hassle of having to organize it themselves. The benefits are: An end of year celebration rewards that motivates the hard-working individuals in the company and provides a much-needed sense of closure for the year’s activities. A scalable “pay-as-you go” system that allows corporates go as big or as small as they desire, from departmental parties to full scale enterprise events. A fun atmosphere and entertainment of a big event - and even meet new people. The chance to party in unusual and stunning locations. Affordable and incredible value for money. A good night out into a truly memorable occasion. Raised staff morale by doing something different. Gorgeous themes, fabulous entertainment, big and elaborate show!
Objective | To create an unforgetable experience for the 700-1000 guests that will walk through the Landmark door on the 15th of Dec. From the invitation card, to the guest management, to the venue design, to the content. All must speak to the world class standards of No Surprises. There has to be a connecting thread tying everything together and all event elements and logistics must be carefully thought through and seamlessley executed. The magic we create for our clients will hit a cresendo at TheUXparty. It should also act as a teaser of what our clients and prospects should expect in terms of innovation and ideas from No Surprises in 2018
Theme/concept Ideas | Party-In-White/ Celebrating Nigerian businesses/Work hard, play harder/Celebrating work while we play?
Event look and feel | It's an all white party, all white parties have been done to death, our venue design must stand out, it cannot be like all other white parties
Venue design | 4 distinct areas to include the guest check in/welcome area, cocktail area, Dinner and formal events and the after party area. Each area should have a personality of it's own and encourage guest engagement and interaction in a different way, I'd like the areas to be named differently from the obvious names
Guest size/Guest management | Minimum 600, max 1,000
Seating | Banquet at formal event and lounge/free seating at after party
Catering | 3 course meal; Kots catering
Drinks | Soft drinks, alcohol, champagne and cocktails
Lighting | Nice and simple/clean at dinner and effects and party lighting at after party, new innovation and display
CEO class of 2017 photoshoot
Team photo ops
Desserts | Creative; Salt Lagos + Hans and Rene
DJ | DJ Obi, DJ Cuppy and DJ Big N
Entertainment | Tiwa Savage
Other Entertainment | Small band, up and coming singer Arese Voice Nigeria winner for dinner entertainment?
Surprise performance | Kaffy/SPAN
Sound equipment | Emeka
Video | Asurf?
Guest management | One usher per table, we need to start selecting and compiling names asap, get Juliana on this
Photographer | Emmanuel Oyeleke + Obi Somto + Blawz?
Videographer | Asurf?
MC | Bovi
Invitation Card | Concept by Osione, production by Ata/Inkheart
Traffic and parking | Yes
Other props and LED wristbands | Yes
LED dance floor, balloon drop, disco ball | Yes
Photobooth | Blow my mind please!
Greenroom | Lily Greenroom?
Hampers and gifts | For all attendees from FMCG partners and others
CEOs Gifts and souvenirs | Special premium gifts for CEOs
*Measurement for success* 1.Strong/creative event concept and execution 2. Unforgetable guest experience 3. Flawleess/seamless production 4. High profile attendees 5. Sales of no less than 60 tables 6. Excellent guest management /concierge service 7. Excellent and prompt service from all service providers (Food and drinks served on time, plates cleared after guests have finished eating, attention to guests' needs and attention to detail) 8. Innovative idea presentation 9. Clients should be relaxed throughout the planning process and on event day, feel comfortable to sit and mingle with guests knowing that all is being taken care of by the organisers 10. Quality of service providers/partners

## I2E Doc
No Surprises IDEA to EXECUTION Process Document (12E Doc)
DONE
Stage | Tasks | Deadline | Responsible | Status | Comments | IN PROGRESS
Engage + Initiation | [5 empty] | LATE
| Receive event brief from client. Notify BD/Do an intro email | N/A | Anyone/All
| Send/reply intro email, attaching corporate profile, website link and EDNA form. Follow up with phone call. | N/A | Biz Dev
| Client fills the form and/or responds to the email | N/A | Client
| Prepare list of questions based on the form responses and client brief | 2017-08-30 | Anyone/All + BD
| Schedule first meeting with client to discuss event brief and identify stakeholders. | 2017-08-30 | Biz Dev
| Prepare contact report and: Share with client, including clear next steps for both NS and client Share with team, including clear next steps for each department and/or individual | 2017-08-30 | Biz Dev
| Prepare professional fees with finance, share with FVO for approval | N/A | Biz Dev |  | N/A
| Obtain FVO’s feedback/sign off | N/A | Finance + BD |  | N/A
| Send approved professional fees quotation to client | N/A | Finanace |  | N/A
| Negotiate, review quotation and identify areas for adjustment | N/A | Finance + BD + Client |  | N/A
| Issue invoice and contract to the client | N/A | Finance |  | N/A
| Send client receipt acknowledge payment and communicate admin budget cap to TEO | N/A | Finance |  | N/A
| Ops is introduced to client and officially brought into the loop | N/A | Biz Dev |  | N/A
Ideation
| Schedule brainstorming with team | 2017-09-29 | Biz Dev
| Draft a word/text document of the ideas generated from the team brainstorming and send to FVO within 48 hours | 2017-09-29 | Biz Dev |  | Sent
| Obtain FVO’s feedback/sign off | 2017-09-29 | Biz Dev
| Develop word document into prezzy and share concept design with client | 2017-09-29 | Biz Dev
| Client gives feedback/signs off | 2017-09-29 | Client
Implementation
| Send approved prezzy to Ops to generate a quotation | 2017-09-29 | Biz Dev
| Prepare workplan | N/A | Ops
| Send client the workplan schedule with timelines and evaluation criteria | N/A | Biz Dev
| Create PSD for CEO’s approval. Create M.Doc as well. | 2017-09-29 | Ops
| Request for costs from vendors, put together initial quote and share with Accounts | 2017-09-29 | Ops
| Send internally approved quotation to client (1 week after) and reminder for 20% balance payment | N/A | Finance
| Negotiate, review quotation and identify areas for adjustment | 2017-09-29 | Ops + Finance
| Issue invoice and reiterate vendor clause in the contract | N/A | Finance | NA
| Client pays of ALL fees (100% of vendor fees and and 20% balance of professional fees) | N/A | NSE | NA
| Share admin budget with Accounts department | 2017-11-17 | TEX
| Give a bargaining margin and payment policy to Ops to use to negotiate with their vendors. | 2017-11-10 | Finance
| Approve admin budget | 2017-11-24 | Finance
| Send a formal brief to selected suppliers and book them | 2017-10-31 | Ops
| Ideate with suppliers. Meet with them if necessary and tap into their creative minds. | 2017-11-06 | Ops |  | This has been done with some finalized suppliers but not all and is ongoing
| Request for quotes from vendors. Relay payment plan with them as communicated by Accounts team. | 2017-11-10 | Ops
| Negotiate costs with vendors along with the Accounts Team. | 2017-11-17 | Ops
| Request for reviewed invoices and share with Accounts. | 2017-11-17 | Ops |  | This is ongoing, has been finalized with some suppliers
| Prepare vendor schedule, get FINAL invoices from Ops and process payment | 2017-11-20 | Finance
| Ensure that deposits are made to vendors after client makes payment. | 2017-11-24 | Ops |  | Some vendors have been paid deposits, instalmental payment plans underway
| Actively manage vendors and receive constant progress on their work progress. Share all necessary creatives with them. | Leading up to the event | Ops |  | Ongoing
| Share weekly project progress and updates with BD to share with the client. | Leading up to the event | Ops |  | Ongoing
| Act as client liaison in sending designs, weekly updates, samples etc. for sign off. | Leading up to the event | Biz Dev
| Request list of event personnel for set up and D-Day and prepare ID (wristbands/tags) | 2017-11-27 | Ops
| Conduct walkthrough/production meeting with all event stakeholders. Identify issues and solutions. | 2017-11-29 | Ops
| Ensure master document has been properly populated (nothing left out) and share production schedule with vendors. | 2017-11-27 | Ops
| Facilitate in-house production meeting. | 2017-11-24 | Ops |  | Follow up meetings will be held
| Manage event team to ensure all tasks are done according to timeline and expectations. | Leading up to the event | Ops
Event Live!
| Ensure all vendors, suppliers, GEMs are at the venue at pre-agreed time | 2017-12-14 | Ops
| Ensure all event staff are properly accredited and that they follow NS Partner Guide. | 2017-12-14 | Ops
| Use task checklist to ensure that vendors have delivered all that was promised/agreed on. | 2017-12-15 | Ops
| Conduct final run-through and security checks. | 2017-12-15 | Ops
| EVENT LIVE! Supervise vendors during the event, manage the event flow, identify issues before they bloom and troubleshoot them. | 2017-12-15 | Ops
| Manage and ensure proper event shut down THEN sleep! #ToWhatEnd | 2017-12-16 | Ops
Closure
| Send thank you note, evaluation form and schedule post mortem meeting with client (48hrs after) | 2017-12-19 | Biz Dev
| Facilitate in-house post-event meeting to discuss event. | 2017-12-19 | Ops
| Send feedback emails/forms and/or thank you cards to vendors and suppliers. | 2017-12-19 | Ops
| Share evaluation forms with contacts in all the companies in attendance/all guests | 2017-12-19 | PM
| Send thank you emails/calls/Instagram and social media shoutouts to sponsors and partners, press all guests in attendance | 2017-12-19 | PM
| Send thank you emails/notes/packages to all guests and companies in attendance | 2017-12-19 | PM
| Send post event meeting report to client (48hrs after) | 2017-12-22 | PM
| Send thank you newsletter, save the date for TUXP2018 | 2017-12-22 | PM
| Create report from internal post event meeting and share with team. | 2017-12-20 | Ops
| Send post event deliverables to the client i.e. videos/photos/drinks (depending on nature of the event) | 2017-12-22 | Ops + BD
| Process balance payments to vendors as agreed after client pays balance. | 2017-12-22 | Finance
| Ensure Accounts makes balance payments to vendors as agreed after client pays balance. | 2017-12-22 | Ops
ON TO THE NEXT ONE!
Formulas:
Deadline = DATE(YEAR([Deadline, row above]),MONTH([Deadline, row above]),DAY([Deadline, row above]))

## Client work plan
The UX Party Workplan | [5 empty] | Done
Category | Tasks | Responsibility | Deadline | Status | Comments | In the process
Late Task
Archival | Send event briefs and request for costs | Julianah/Yvette | 2017-08-08
| Confirm Photographer and Videographer for entire event | Julianah/Yvette | 2017-09-15
| Make a photography list of shots | Julianah/Yvette | 2017-09-20
| Agree on list of photoshots with client and share with supplier | Julianah/Yvette + Chinwe + FVO | 2017-10-05
Branding | Determine venue branding, way finders, signages etc. | Ayo | 2017-08-08
| Shortlist branding company (s) based on needs | Ayo | 2017-08-09
| Send brief and request for costs from shorlisted company | Ayo | 2017-08-10
| Present design creatives with FVO for approval | Ayo + FVO | 2017-08-11
Catering and Beverages | Finalise menu | Lanre + Chinwe + FVO + KOTS | 2017-10-15
| Determine drinks/ cocktails/sponsorships/needs | Chinwe + FVO | 2017-08-25
| Co-ordinate food and drink tastings with client (if necessary) | Vendors +Account Team + FVO | 2017-10-31
Decor/Venue Design | Agree theme/direction for décor | Ayo + Olabisi + FVO | 2017-08-08
| Determine/obtain floor plan for dinner area, party area, stage, CEO lounge, cocktails area etc. | Ayo + Olabisi + FVO | 2017-08-31
| Shortlist decor company based on needs | Ayo + Olabisi + FVO | 2017-08-10
| Send brief and request for costs from shorlisted company | Ayo + Olabisi + FVO | 2017-08-11
| Finalise decor pieces,placement and general look and feel | Ayo + Olabisi + FVO | 2017-09-23
Entertainment | Determine MC and/or comedian | Account Team + FVO | 2017-08-08 |  | MC - Bovi
| Book and finalise talks with all talent. | Seun + Chinwe | 2017-09-14
| Schedule and hold briefing with FVO and MC | Seun+ FVO + Chinwe + Bovi | 2017-09-22 |  | FVO is still in talks with Bovi
| Determine set up times and soundcheck and share with talent managers. | Seun + Angie | 2017-11-15
Event day | Set up, event goes live and tear down | Team TUXP | 2017-12-15
Event flow | Determine event flow; awards, raffle draw, performances, lipsync battle mashup, photos for Employee of the Year Awards photos for winners etc. | Account team+ FVO | 2017-08-08 |  | Ongoing
| Determine games and competitions among the companies,etc. | Account Team + FVO | 2017-08-09
| Share draft event flow with Stage Manager for finetuning + creation of cue sheet | Seun | 2017-11-16
| Recieve finalised event flow and share with FVO for final approval + implementation | Seun | 2017-11-20
Event Management | Share moodboard with FVO | Chinny + Es | 2017-08-25
| Request for costs from suppliers to aid creation of budget | Chinny + Es | 2017-08-09
| Share suppliers quote with client + finance team | Chinny + Es | 2017-08-31
| Agree on suppliers quote | Finance + FVO | 2017-09-20
| Get final budget sign off from client | Abolore + Chinny | 2017-09-20
Finances | Create vendor schedule of payment | Abolore | 2017-09-27
| Agree on payment terms and communicate to all vendors/suppliers | Finance Team + Account team | 2017-10-02
Guest Experience Management | Populate the guest list | Orby + Mo + Chinny | 2017-10-24 |  | Ongoing as companies purchase tables
| Audition for hostesses | Orby + Mo + Julianah | 2017-11-08 |  | Done on 25/11/17
| Final selection, briefing and training of hostesses | Orby + Mo + Julianah | 2017-11-22
| Determine and finalise on outfits for hostesses | Orby + Mo + Julianah | 2017-10-24
| Determine guest experience management processes and procedure and assign managers | Orby + Mo | 31/11
| Commission the production/purchase (where necessary) of outfits | Orby + Mo | 2017-11-15
| Finalise on seating plan using guest list | Orby + Mo | 2017-12-01
Logistics | Finalise all accommodation, feeding and transport plans for the team and create admin budget document accordingly | Julianah + Abolore | 2017-11-29
| Determine support staff (casual staff + temps) needs and hire additional staff as is needed | ChinnySeun + Julianah + Abolore | 2017-10-15
Post Event | Post event meeting with client | Chinny + Seun | 2017-12-20
| Share videos from the event with client/stakeholders | Asurf + Chinny + Julianah + OrbyMo | 2017-12-25
| Share pictures from the event with client/stakeholders | JideOdukoya/ ClementOgoh + Chinny + Julianah + OrbyMo | 2017-12-18
Print Production | Determine invitation style/concept | TUXP Design Team + FVO | 2017-08-08
| Formally brief creative agency (InkHearts) based on FVO's needs to request for quote/design | Chinny | 2017-08-10
| Present first draft of invitation creatives to client for approval | InkHearts + Chinny | 2017-08-18
| Deliver invitations to the office | Chinny + Ayo | 2017-11-13
| Deliver invitations to the guests | Olaide + Ayo + Chinny | 2017-11-15
Production Meeting/Walkthrough | Conduct an event walk-through with tech and design suppliers and troubleshoot | Chinny + Seun | 2017-11-24
| Conduct an event walk-through with all suppliers and troubleshoot | Chinny + Seun + TUXP Team | 2017-11-28
| Conduct production meeting on site with FVO, NS team and suppliers | Chinny + Seun + TUXP Team | 2017-12-06
Rentals | Determine rental needs | Ayo + Olabisi + Seun | 2017-08-08
| Shortlist rental company (s) based on needs | Ayo + Olabisi + Seun | 2017-08-25
| Send brief and request for costs from shorlisted company | Ayo + Olabisi + Seun | 2017-08-28
Security/Parking | Brief and book security company | Julianah | 2017-08-28
Souvenirs/Goody Bags | Determine gift items for goody bags, gifts, brochures etc | Natasha | 2017-08-08
Technical | Determine Technical director | Seun + FVO | 2017-10-15
| Brief Technical Director on Event Objective | Seun + FVO | 2017-10-18
| Determine technical needs, stage positions, lighting, sound requirements etc | Seun | 2017-08-25
| Ensure stage manager is briefed and has the event flow/program | Seun | 2017-11-15
| Obtain all riders from entertainers and share with sound company + TD | Seun | 2017-11-01
| Agree terms and possible partnerships with venue; sign contract | Modupe | 2017-08-31
Venue | Pay 1st installment of venue cost | Finance Team | 2017-08-18
| Pay 2nd installment of venue cost | Finance Team | 2017-09-18
| Pay 3rd installment of venue cost | Finance Team | 2017-10-18
| Pay 4th installment of venue cost | Finance Team | 2017-11-18
| Venue recce with suppliers | Modupe + Seun | 2017-11-23
| Pay final installment of venue cost | Finance Team | 2017-12-29

## Team Lip sync Playlist
Team Lip Sync TUXP Playlist for DJ
Name of Company | Artiste | Song Choice
First EPDC
Interactive CT
Sanofi
HC Bonum
RnB PR
Cobranet
Cobblestone
Award | Name of company | Comments/Notes

## Supplier contact sheet + Accred
Supplier Contact Sheet + Accreditation
Category | Service | Name of Company | Contact person | Formal Engagement Yes or No? | Final Invoice received? | Next steps | Comments | Cell phone number | Total crew on site | Crew for set up | Crew for live event | Agreed arrival time | Actual arrival time
Archival | Detailed photography for marketing/social media | Ifebusola | Ifebusola | Yes | No | Followup to get invoice latest 9am |  | 7032459046
| Photography | Clement Ogoh | Clement Ogoh | Yes | No | Followup to get invoice latest 9am |  | 9038067606
| Photography | Jide Odukoya | Jide Odukoya | Yes | No | Get final invoice |  | 8033999286
| Photobooth | Cinematics | Nnanna Adim | Yes | N/A |  | Its a partnership | 8060903561
Celebrate What You Do Photobooth
| Pre event videography | Tolu | Tolu | Yes | No | Get final invoice |  | 9098780450
| Event Videography | Asurf/Seyi | Seyi | Yes | Yes | Pay a deposit |  | 7033330810
Entertainment | MC | Bovi | Bovi | Yes | Yes | Pay a deposit |  | 8028288792
| Music | DJ Obi | Asa Asika | Yes | N/A |  |  | 8186541676
| Music | DJ Cuppy | Rachel | Yes | Yes | Pay final instalment |  | 9092133614
| Music | DJ Big N | Nonso | Yes | Yes | Pay final instalment |  | 8164908331
| Live performance | Tiwa Savage | Tiwa | Yes | Yes | Pay final instalment |  | 8038393594
| Greenroom | Lily greenroom? | lily | No |  |  |  | 9094993376
Technical | Technical Director | Lucere | Dr Yemi | Yes | Yes | Pay a deposit |  | 8129920110
| Lighting Design | Godwin | Godwin Emefe | Yes | Yes | Pay a deposit |  | 7064552555
| Sound | Pro Audio | Emeka Michael | Yes | Yes | Pay a deposit |  | 8128233178
| Trussing/Stage etc | Center techniques ltd | Seun Owoaje | Yes | Yes | Pay a deposit
| Discoball | Sydeninteractive/Atlantis
| Lighting | Megavision in Landmark/AEC | Mark Osho | Yes | Free | Use lights
| AV | AV Edge | Lolu Durojaiye | Yes | Yes | Pay a deposit
| Stage/Trussing/Power Distribution/Lighting | AEC | Jesse Wang/Demola | Yes | Not yet | Prompt Jesse again for invoice
| Scenefab/Show Designer | Jesse Wang | Jesse Wang/Demola | Yes | Yes | -
| Generator | Rapid Rentals | Fejiro | Yes | Yes | Pay a deposit
| - LED dancefloor - Balloon drop | Atlantis by Eventecture | Oreoluwa Famoriyo | Yes | Yes | Pay a deposit
Catering | Catering | Kots catering | Osaretin | Yes | yes | Pay a deposit Send formal brief with details of events, attend walk through and send KPIs too by 4th Dec |  | 8023125583
| After party gourmet snacks for CEO lounge | Chef Benedict | Benedict | Yes | yes | Make payments, send formal brief with details of events, attend walk through and send KPIs too by 4th Dec |  | 8184484168
| Burgers and grills for CEO's lounge | Grind Grills | Francis | Yes | yes | Make payments, send formal brief with details of events, attend walk through and send KPIs too |  | 8025015336
| Finger foods/small chops | Vincent/Artisan | Vincent | Yes | yes | Make payments, send formal brief with details of events, attend walk through and send KPIs by 4th Dec |  | 8033281984
| Menu card(Design + Printing) | Osione/Doculand | Ayo +Olaide | Yes | No | Make payments, send formal brief with details of events, attend walk through and send KPIs by 4th Dec
| Desserts (Gelato) | Hans & Rene | Busayo | Yes | Yes | Make payments, send formal brief with details of events, attend walk through and send KPIs too |  | 9091635707
| Desserts | SALT Lagos? | Mrs Dupe | Yes | yes | Make payments, send formal brief with details of events, attend walk through and send KPIs too by 4th Dec |  | 8097423996
Beverage | All drinks | Diageo | Joe | Yes | N/A | Follow up with Client via FVO to confirm quantity of drinks and date of delivery of drinks promised |  | 9029067626
| Moet/Veuve Champagne | Hennessy | Emmanuelle/Owen | Yes | No | Follow up with Fvo to confirm quantity of drinks to be provided for the event |  | 90339816960
| Soft drinks/Water/Cocktails/juice | Lucky cocktails? | Lucky | yes | yes | Pay a deposit Make payments, send formal brief with details of events, attend walk through and send KPIs too by 4th Dec |  | 08039396741, 08174698200
| Wines | Owen | Owen | yes | no | Pay a deposit
| After party late night coffee | Cafe Neo | Fikayo | Yes | No | Follow up to revised invoice |  | 9099160017
Rentals | Clear Napoleon Chair | Ceaderwood | Mrs Fehintola | Yes | Yes | Pay a deposit |  | 8095100008
| Cocktail tables | Stylista | Aunty B | No | No |  |  | 80230027315
Sofas and lounge
| Cue breakers | KSquare | Davies | Yes | Yes | Pay a deposit |  | 8027167111
| - Cutlery - Charger plates - Napkin rings - Napkins - Table no stands | Gigshire? Rental By Lasting Memories | Adeola Nkem | No | No | Finalise Items to be rented 1st Dec. |  | 9099991470 08037596228
Venue design | Demarcation/false walls and branding | Ola/Ace | Ola | Yes | No | Renegotiate cost by 1st Dec |  | 8023945491
Other props
| Red carpet/ laying | AAA/ Dayo | Juliana / Dayo | Yes | No | Receive invoice - 1st Dec |  | 7084398300
| Front of House console cover | Engaged technical supplier with do this
| Signage | Ola/Ace | Ola | Yes | No | Renegotiate cost by 1st Dec |  | 8023945491
| - Cutlery - Charger plates - Napkin rings - Napkins - Table no stands | Gigshire/tablesetters | Adeola Nkem | No | No | Finalise Items to be rented 1st Dec |  | 9099991470 08037596228
| Venue drapery and prop assistant | IK | Ik | Yes | No | Renegotiate cost - 1st Dec |  | 8097553680
| Centrepieces | IK | Ik | Yes | No | Renegotiate cost - 1st Dec |  | 8097553680
Guest Experience | Ushers/GEMs | AAA | Julianah |  |  | Pay a deposit |  | 7039329344
| GEM outfits | Promo print ventures | Ms Elizabeth | Yes | No | Receive invoice |  | 0803-0444686
| Balloon drop | Atlantis by eventecture | Mr Niyi Olatunji-Daniel | Yes | Yes | Pay a deposit |  | 234 803 343 1415
| Glow Foosball for After Party | Games at event & Godwin (For lights) | Mr Godwin Emefe | Yes | No | Receive invoice - 2nd dec
| After party experience props and glows | Party props store, party props shop, naija essential store |  |  |  | Still searching for vendors
| "Man's not hot" booth | Cinematics | Mr Adim | Yes | N/A | N/A | Its a partnership | 8060903561
| Team badges | Seward productions | Mr Adebayo Segun | Yes | No | Receive invoice
| Wristbands | Sec bands | Secband | Yes | Yes | 100% payment has been made |  | 0861 974 789
| Invitation cards | Inkhearts | Mrs Ashiru | Yes | Yes | 100% payment has been made
| Access cards | Access cards NG | Mr Deji Taiwo | Yes | Yes | 70% payment has been made |  | 2348128452645
TUXP Creative design | Creative design | Osione | Osione | Yes | Yes | Pay final instalment |  | 8091432722
| Invitation card production | Ink Hearts | Mrs Ashiru | Yes | Yes | Receive printed Invitation | Full Payment Made | 8074783309
| Access Cards | Access cards Ng/Osione | Dami | Yes | Yes | 70% payment has been made
| Menu Card and Other Stationery printing | Doculand | Doculand | Yes | No | Finalise Items to be rented 1st Dec
| Invitation card delivery | MAXng | MAXng | Yes | No | Send an excel sheet with all addresses, phone numbers and names for delivery
| - Table names - Table numbers - Table number cards - Menu cards - "5 senses" cards - Cinematics cards - Complimentary cards - Gift redemption cards - Drink vouchers? | Osione (Light Design Team) | MAXng | Yes | Yes | Pay final instalment |  | 8091432722
Gifts | Team Gifts | Swish Ideas/Lucy Gifts | Olive/ Lucy | Yes | No | Finalize on gift items
CEO gifts
| Gift bags | Gift FairyNG | Dami | Yes |  |  |  | 8080261314
Employee of the year Certificates/plaque?
Trophy and crown for Lip sync battle
Media | VVIP Events | Ebony life? | Queen/Michael
| 53 Extra coverage | African Magic/Dstv | Dami
Security | Corporate security | K-Square | Kunle Akomolafe | Yes | Yes | Pay a deposit |  | 08027167111 08035825617
Internet | Internent service providers | Cobranet | Engineer Ayo | Yes | N/A |  | Its partnership | 8057098430

## Signage planner + Printing brea
Directional/Event info signage Breakdown
Location | Text for Signage | Signage style | Dimension
Landmark Main Gate | Welcome to The Unofficial Christmas Party (logo) #PartyInWhite #CelebrateWhatYouDo #TheUxParty | Branding Wall | 8 by 8ft wall
Drop off | The Unofficial Christmas Party (logo) Drop Off here #TheUXPartyInWhite
Check In Area | Check In Here A, B-J, K-N, O, P-Z #TheUXPartyinWhite | Match Box
Check In Area | Executive Check In Here
Coctail/ Red Carpet Area | Sip, Socialize and Pose for the Camera Here #TheUXPartyinWhite | Match Box
Dinner Area | This way to the Dining Area: Let's Celebrate and Eat #TheUXPartyinWhite
After Party | Turn Up in White Here #TheUXPartyinWhite | On the the tunnel wall
VIP Entrance to The After Party | Silver Wristbands Only | A5 landscape foam board
Regular Entrance to the After Party | Black Wristbands Only | A5 landscape foam board
Restroom | This way to the restrooms | A5 landscape foam board
Printing breakdown
Item | Content/Text | Dimension | Quantity
Invitation cards + Envelopes |  |  | 700
Menu cards |  | A5 card | 700
Table names |  | 4.5inches by 11inches Tent Card | 70
Table numbers |  | A5 card | 70
Table number cards for guests |  | Complimentary card | 700
Gift redeeming vouchers |  | Complimentary card | 700
Table Place Cards |  |  | 700
Wristbands |  |  | 700
Envelope for menu options |  |  | 700
Wristband color coding
Menu option cards |  |  | 700
Internet cards |  | Complimentary card | 70
Access cards + Envelopes (Blue, White and Purple)
Gift vouchers |  | Complimentary card
Gift Bags
Placards | Office Clown, Best Couple, Workaholic, Besties. | 1 by 2 feet
Employee of the year certificate |  | A4 Card
Badges
Backdrops
Notes for Cinematics | [Logo]- Do your best shoki, Jiggle all the way, Who run the world?! Girls, Sparkle like you mean it, Cheers to the team. | Complimentary card
Welcome notes + envelopes |  | Complimentary card
Wrapping papers
Ribbons
VIP parking stickers |  | 3 by 6 inches
Cue Card |  | A5
Branding Break down

## Event flow
TUXP 2017- Party In White
Event name: TUXP
Event date: 15 December, 2017
Set up time: 00:00 14 Dec - 3pm 15 Dec
Sound check time: 2pm 15 Dec
Event time: 6pm 15 Dec
Activity | Time | Duration

## Event Cue sheet
TUXP Party In White
Event name:
Event date:
Set up time:
Sound check time:
Event time:
Activity | Time | Duration | Location | Music | Lighting/Effect | Cue/Props | Responsibility | Comments

## Non-Paid Guestlist
Company | Client | Email Address | Colour code for card
Olam | Ade Adefeko | adex90@yahoo.com, ade.adefeko@olamnet.com
Diageo | Adenike Adebola | adenike.adebola@diageo.com
Kantar | Adeola Tejumola | adeola.tejumola@kantar.com
Google | Affiong Osuchukwu
She Leads Africa | Afua Osei Yasmine Belo-Osagie
Sanofi | Agbolade Oladimeji | Oladimeji.Agbolade@sanofi.com
Private | Ajo Balogun | ajobalogun@gmail.com
Clickatell | Alaba Ephraim
PZ Cussons | Alex Goma | Alex.Goma@pzcussons.com
MTN | Alexander Ibehre | Alexander.Ibehre@mtn.com
Terragon | Anuoluwapo Sanya | asanya@terragonltd.com
Private | Bella Adenuga
LSFPR | Bidemi Zakariyau | info@lsfpr.com
R n B PR | Bobo Omotayo | adeoye,omotayo@rb-pr,com
Diageo | Bodam Taiwo | bodam.taiwo@diageo.com
Uhuru | Bola Balogun | bola2920@gmail.com
Diageo | Bola Otubu | bola.olajomi-otubu@diageo.com
Buki HQ | Bukola Sawyerr Izeogu | me@bukihq.com
Multichoice | Busola Tejumola | busola.tejumola@ng.multichoice.com
Flytime | Cecil Hammond/Keke Hammond/Feran
First E & P | Cees and Daniella Uijlenhoed
British Council | Chiamaka Ndika
Afri Invest | Chioke Ike | ichioke@afrinvest.com
General Electric | Clara Bot-Mang | clara.bot-mang@ge.com
Accelerate | Colette Otuesho | colette.otusheso@acceleratetv.com
FH Nigeria | Dara Ogunsehinde | Dara.Ogunseinde@fhnigeria.com
Union Bank | Dayo Odulate
First E & P | Demola Adeyemi-Bero | ademola.ade-bero@first-epdc.com
Private | Dudun Peterside | d.peterside@gmail.com
Emmanuel Onyeje
Moet | Emmanuelle Baroux | emmanuelle.baroux@gdnetter.com
Interswitch | Emuobosa Akpene | emuobosa.akpene@interswitchgroup .com
Dohenney Services | Erefa Fynecontry-coker
Old Mutal | Ezinne Obinna-Uma
Landmark | Fadi Jarmakani | fadi@groupalfa.com
Private | Folabi Esan | folabi@gmail.com
Honeywell Group | Foluke Oyeleye | foluke.oyeleye@honeywellgroup.com
H B Consult | Habiba Balogun
Bavent Street Live | Hakeem Condotti
Fruition | Ifeoma Williams | ceo@thecerebrallemon.com
Alpha African | Ijeoma Taylaur | i.taylaur@alphaafrican.com
Cobranet | Jamil Chaptini | jamil.chaptini@cobranet.ng
FCO Limited | Jane Maduegbuna | jane@fcolimited.com
Air France | Jean Raoul Tauzin | jrtauzin@airfrance.fr
Private | Josephine Sarouk | ejiro8@hotmail.com
Aluko Oyebode | Jumoke Oshunlaja | Jumoke.oshunlaja@aluko-oyebode.com
Yellow Brick Road | Kaliko Olowole | kaliko@yellowbrickroad.com.ng
Karman Cards | Karishma | karmancards@gmail.com
Kots Catering | Kehinde Daniel | kod@kotscatering.com
Noah Ark | Lanre Adisa | lanre@noahsark.com.ng
Private | Lere Awokoya
Comfu | Mark Khoury
DSTv Mobile | Martin Mabutho | Martin.Mabutho@dstvmobile.com
ELTV | Mo Abudu
Private | Moon Najjar Sawaya | moonnajjar@hotmail.com
The Wheatbaker Lagos | Mosun Ogunbanjo
Bollinger | Motunrayo Abiona | tunrayoraheem@rumon-org.com motunrayodomain@gmail.com
Private | Moyo Aderemi | moyo.aderemi@gmail.com
Private | Mrs Tinubu
Nestle | N'dee Uwadoka | Victoria.Uwadoka@nestle.com
Diamond Bank | Ngozi Dozie | ngozi@kaizenventurepartners.com ngozi@kvpafrica.com
Money Matters | Nimi Akinkugbe | info@moneymatterswithnimi.com
Pan Ocean Oil | Nkem Emezie-Ejinima | nkemee@gmail.com
Stanbic IBTC | Nkiru Olumide-Ojo | Nkiru.Olumide-Ojo@stanbicibtc.com
Nestle | Nwando Ajene | Nwando.Ajene@ng.nestle.com
Union Bank | Ogo Okoyeuzu | osekezie@unionbankng.com
Jumia | Ojuola Asuquo | ojuola.asuquo@jumia.com
Cranium One | Olaotan Towry-Coker | olaotan@gmail.com
Templars Law | Olu Akpata
Private/MTN/Olive Branch | Onyinye and Emeka Ikenna-Emeka
Diageo | Otome Oyo | otome.oyo@diageo.com
Moe | Papa Omotayo | papa@moeaa.com
Landmark | Paul Onwanibe | Paul@landmark-offices.com
La Liga | Philip Diwan | philip@legacysports-ng.com
Microsoft | Rimini Makama | rimaka@microsoft.com
Clickatell | Samson Isa | samson.isa@payd.co
SPAN Nigeria | Sarah Boulous | sarahboulos@spanigeria.org
YAGG | Segun Adeniyi
Elekroncorp | Segun Demuren | sd@elektroncorp.com
Zircon Marine | Seyi Ajibola | Seyi.ajibola@zirconmarine.com
The Wheatbaker Lagos | Simon Grindrod
Guardian | Toke Ibru | toke.ibru@guardian.ng
Air France | Tola Aluede | ataluede@airfrance.fr
BD Consult | Tola Bademosi | tola@bdconsult.net
Interactive CT | Tola Obi | tola.obi@interactivect.net
British Council | Tomi Soyinka | adetomi.soyinka@ng.britishcouncil.org
Cakes By Tosan | Tosan Jemide
Private | Toyin Odulate
Interswitch | Tunji Ashiru | tunjiashiru@yahoo.com; tunji.ashiru@interswitchgroup.com
IBM | Uzo Nwani | Uzoonwani@ng.ibm.com
Talentwise | Vitus Ezinwa | vezinwa@talentwiseonline.com
YAGG | Wale Irokosu
Eko Pearl Towers | Fola Niyi-Duale | fola.fowowe@ekopearls.org
Uhuru | Yemi Osindero | yemi.osindero@uhurucap.com
Private | Yomi Awobokun | yawobokun@gmail.com

## Venue readiness checklist
Venue Readiness Checklist
Location | Activity | Requirements | Props/Décor | Personnel | Company/Supplier responsible
Landmark Main Gate | Arrival and tagging for parking | 1 welcome signage | 400 parking tags
Car park/Entrance area | Drop offs Car parking | 1 drop off signage | NIL | 2 Security personnel | KSquare NSE
Venue Entrance | Check in for -Regular -VIP | 1 checkin signage for achievers 1 checkin signage for executives |  | 4 security personnel 7 hostesses | Ksquare AAA
Tunnel | Connection to all areas | False wall | Flourescent lights on wall | 2 hostesses 2 securities | ACE AAA Ksquare
Terrace | Red carpet/cocktail | -1 signage reading "Sip, Socialize and Pose for the Camera Here #TheUXPartyinWhite" -Photobooth -Backdrop -Vintage office set design for team photo | -Cocktail tables and stools -Black carpet - | 3 hostesses | AAA
Dining area | -Dinning -Team Activities | -Table setting -Stage -Pianist corner -Front of house | -Round tables -White criss cross chairs -Candle (Amber) centrepices -White amber lighting -Table number stands -Crockery -Personalised cards with notes -White grand piano | -65 hostesses -3 security personnel -Waiters -NS team -Event host | -AAA -KSquare -KOTS, SALT Lagos, Lucky Cocktails -NSE -Bovi
After party area | -Dj battle -Artiste performance -Networking -Dance! Dance! Dance! | -CEO/Executive lounge -Ciroc lounge -Bar(s) -Stage -Dancefloor | -Disco ball -Lounge furniture -Ambience light | -Hostesses -5 security personnel -Waiters -
Green room | Artiste holding room | -Refreshment - | -Lounge furniture | -1 hostess -1 security | -AAA -KSquare

## Team task allocation
Role | Description | Team member | Team member questions | Daily Update by team member in charge | Next Steps
Stationery/collateral/Welfare
| Stationery, Invitations, Table numbers, Table no allocation, Menu cards, client/vendor wristband, wristbands,crew tags, colour coding, invitation delivery and documentation. Work with whoever is in charge of press to ensure the right number of crew tags are printed, same goes for suppliers. Make sure they are handed over to the people in charge of accreditation Determine team needs days before the event, feeding, hotel accommodation etc. Ensure you source for the best options and negotiate, ensure all plan are seamless. Manage all that the team need for onsite office, secure the room in advance and ensure that all needs are met. Manage admin template and ensure all teams fill out their needs before set up/event day. | Olaide + Ayo |  | GiftFairyNG is making the white crepe bottle bag which will contain the Johnnie Walker, Ciroc or Baileys wine. We are also getting our branded ribbons from them. We are waiting on them to us send us some more creative samples of giftbags. | To create admin budget and share with Abolore. Followup with branding vendors to get creative designs for various printables. Finalise on the choice of sample wrappers (crepe material) and giftbags sent by the vendor & also the invoice.
Security/Parking+ Venue Readiness
| Determining number of personnel, positioning, outfits/uniform specification, entry processes/flow, troubleshooting, damage control,personnel alignment with the different wristbands and boundaries Ensuring that set up is completed and the venue is ready in due time. Create venue readiness checklist and production schedule and ensure it is adhered to. | Julianah |  | Ksquare has been booked for the day, however we are negotiating to 10k per personnel as against 15k. Venue readiness checklist has been created and adherance will be endused on the day | The accountant will get back before 2pm to comfirm whether or not we are good on the price
Technical/Talent Management/Event Flow/Stage Production
| Be the contact person between Dr Yemi/tech suppliers and NS. Ensure all quotes are received and compiled in time to make a decision, ensure all that is finalised and agreed on is delivered Design event flow incorporating all the elements as sold to guests, ensure all is aligned and communicate with Dr Yemi Laiase with all talent and have all their contact details, manage all their schedules and arrival times, ensure they are comfortable and are backstage on time for their performace, work closely Dr. Yemi | Seun + Angie |  |  | Finalise time for meeting with Godwin.
Guest Experience and Management
| Detailed and well thought through check in process to limit guest wait time to a minimum, ensuring the welcome area is well lit especially when it gets dark, ensuring there are at least 6 check in points with cue breakers, seating and seats assignments, templates and processes for guest experience/usher appraisal, photobooth sourcing, props, placards and placement, gift/voucher sourcing, picking up of vouchers and pitching to prospective partners, handling invitations and distribution to guests, team competition logistics and coordinating with show producer Determine number of ushers and auditions, outfits design and sourcing, make up and personal hygiene, training, event alignment and venue orientation | Orby + Mo + Seun |  | Hostesses: 1st hostess auditions held last Saturday with 45 ladies. 2nd auditions to hold Friday 1st December 2017. Broadcast messages have been sent out. Guest flow: - Hostesses have been allocated to areas. Welcome area and requirements - Wristbands, cue breakers - A well thought out check in process has been created and the security team has been informed about the required quantity of cue breakers. Secband to produce the wristbands and the wristbands to be delivered by 4th December 2017 Invitations: Inkheart has started invitation card production. To be ready by Friday 1st December 2017. Props: Vendors to provide the props have been shortlisted. Photobooth: An email has been sent to Cinematics to follow up on partnership. Printables: A list of printables have been sent to FVO to approve. Team distribution: - Guest seating assignments: - | Hostesses: Hold auditions on Friday. Guest flow: - Creat flow chart Welcome area and requirements - Wristbands, cue breakers - Follow up on wristband delivery. Invitations - Follow up with Inkheart on invitation production and Diageo with drinks. Props: Emails to be sent to partypropsstore, partypropsshop, naija party essentials. A message to be sent to Wadami to help purchase the props. Photobooth: Share ideas for the photobooth with Cinematics by 28/11/2017. Printables: Prompt FVO for feedback on printables and prompt collateral team to share with Osione for designing. Team distribution: Team to be distributed by 28/11/2017 Guest seating assignments: Sync with Chinwe on total list of guests by 28/11/2017 and begin guest seat allocation.
Press/PR/Achival (Photography and videography)
| Compile shot list and share with FVO, Confirm all photographers and play to their strengths, ensure all necessary shots are captured for social media and PR, Ensure there is a dedicated photographer for red carpet, ensure there is adequate lighting for the red carpet | Yvette + Juliana
Venue Design/Decor and branding
| Venue design, mood board, Floor planning, chair selection and sourcing, table setting, VIP/CEO lounge planning, tablescaping, napkins, napking rings, centrepieces, table and chair alignments, cocktail area, photobooth, bar placing, props etc. | FVO + Ayo + Olabisi |  | Walk through has been done with branding supplier, Ace Concept. Cocktail stools and tables have been booked. Alternative access to the dinner area has been created to avoid distraction late comers during event. 200 Crossback chairs have been booked for the event. IK has been booked for decor. | To follow up with Jesse for his cost. Source for 500 more Crossback chairs. Finalise on decor idea for the event and formally engage IK. Get invoice from Ola.
Sponsor/Partner Management and Gifting Logistics
| Obtain all agreements with sponsors and ensure all agreements are met in terms of logo usage on media wall, magazines etc. Liaise with sponsors before event day to ensure there is alignment especially with vouchers and gifts etc. Ensure all raffle tickets have a process and this is clear and communicated with all concerned. Ensure sponsors get their data capture and database for those that apply as agreed. Ensure there is brand visibility for all brands however without compromising on TUCP's image and venue design...no roll up banners! Ensure sponors are given their mentions as agreed post event, in the magazines, on the media walls etc as agreed | Natasha + Bukola |  | NACK Store is coming on board as one of our partners. Concluded partnership agreement with Yomi Casual and Oasis MedSpa. Contacted two gift shops as regards partnering with us for TUXP. | Send partnership agreement letters. Meeting with representatives from the gift shops to conclude on partnership.
Food and Beverages
| Obtaining the menu for food and desserts, finalising with the suppliers and designing the menu, designing artwork and getting sign off, ensuring they are printed on time and align with brand values, confirm all arrangements with suppliers Taking stock of all drinks and ensuring they are properly stored and chilled, put proper process in place to secure drinks Hans and Rene Cafe Neo Chef Benedict Salt Lagos Kots Catering Artisan Grind grill Diageo Lucky cocktails | Lanre + Felicia |  | We have received a final invoice and menu from Kots catering We have also confirmed our booking with H &R for the party. A list of drinks have been shared with us from diageo to be supplied for the event A revised invoice is yet to be received from Artisan and SALT Lagos. Both Chef Benedict and Grind grill have sent in their invoices for the VIP lounge. Got in touch with lucky cocktails yet to receive an invoice for drinks for the event. | Make part payment to kots catering, follow up wih the printing of te menu card. Make part payment to H & R
Proposals, sales and invoicing, Accounting
| Ensuring prospects get the appropriate documentation/invoicing on time, following up to ensure all payments are made on time | Tim + Abolore + Chinwe |  | - All clients who have purchased tables have been sent receipts within 24 hours after receiving payments - All artistes have been paid deposits (updates in the quotation), instalmental payments were communicated to them. | - Ensure all receipts are sent to the clients upon receipt of payment within 24 hours - Payment plan for suppliers to be communicated by the finance team by Nov 28

## Production Schedule
Event : The Unofficial Christmas Party
Load in on: December 14th 2017 at 00H00
START DATE | DAY | START TIME | END TIME | TASK/ACTION | TEAM MEMBER RESPONSIBLE | SPECIAL NOTES | LOCATION | ORGANISATIONAL RESPONSIBILITY
THURSDAY 14TH DECEMBER 2017
2017-12-14 | THURS | 07H00 | 07H30 | ARRIVAL OF SECURITY PERSONNEL | JULIANAH & MO |  | HALL 1 | NSE + K-SQUARE
2017-12-14 | THURS | 07H30 | 08H00 | SECURITY SWEEP OF VENUE & VENDOR ACCREDITATION | JULIANAH & MO |  | HALL 1 | NSE + WRIST BANDS + FRITZ + WRIST BAND NG
2017-12-14 | THURS | 08H00 | 09H00 | PRODUCTION OFFICE ON SITE (BASE CAMP) | OLAIDE |  | HALL 1 | NSE +LANDMARK
2017-12-14 | THURS | 08H00 | 12H00 | MAIN STAGE CONSTRUCTION | SEUN |  | HALL 1 | NSE + EVENTECTURE
2017-12-14 | THURS | 08H00 | 11H00 | DELIVER MONITORS, BACKLINES AND MICS | SEUN |  | HALL 1 | NSE +
2017-12-14 | THURS | 08H00 | 12H00 | DELIVERY AND OFF LOADING OF ALL LIGHTING AND RIGGING EQUIPMENT | SEUN |  | HALL 1 | NSE +
2017-12-14 | THURS | 08H00 | 13H00 | FALSE WALL INSTALLATION | AYO |  | HALL 1 | NSE + EVENTECTURE
2017-12-14 | THURS | 10H00 | 12H00 | INSTALLATION OF SCREENS | SEUN |  | HALL 1 | NSE + AEC
2017-12-14 | THURS | 10H00 | 10H30 | GENERATOR ARRIVES | SEUN |  | HALL 1 | NSE +
2017-12-14 | THURS | 10H00 | 13H00 | SET UP OF AUDIO EQUIPMENT, SET UP MAIN LINE PA AND AUDIENCE FILLS | SEUN |  | HALL 1 | NSE + AEC
2017-12-14 | THURS | 12H00 | 15H00 | ASSEMBLE ALL TRUSSES | SEUN |  | HALL 1 | NSE +
2017-12-14 | THURS | 12H00 | 15H00 | INSTALLATION OF DISCO BALL | SEUN |  | HALL 1 | NSE + ATLANTIS + SYDENINTERACTIVE
2017-12-14 | THURS | 12H00 | 15H00 | INSTALLATION OF DANCEFLOOR | SEUN |  | HALL 1 | NSE + ATLANTIS
2017-12-14 | THURS | 12H00 | 15H00 | AFTER-PARTY STAGE CONSTRUCTION | SEUN |  | HALL 1 | NSE + AEC
2017-12-14 | THURS | 14H00 | 18H00 | BRANDING OF THE FALSE WALL | AYO |  | HALL 1 | NSE + EVENTECTURE
2017-12-14 | THURS | 15H00 | 18H00 | HANGING OF LIGHTS | SEUN |  | HALL 1 | NSE +
2017-12-14 | THURS | 15H00 | 18H00 | VIP LOUNGE CONSTRUCTION | SEUN |  | HALL 1 | NSE +
2017-12-14 | THURS | 16H00 | 20H00 | ARRANGEMENT OF TABLE AND CHAIRS | AYO |  | HALL 1 | NSE + LANDMARK + POSH RENTALS + NAPHTALI + KFA
2017-12-14 | THURS | 16H00 | 17H00 | SUPPLIER INSPECTION/SECURITY PERSONNEL ON SITE FULL STRICT ENFORCMENT OF ACCREDITATION | JULIANAH & MO |  | HALL 1 | NSE + K-SQUARE
2017-12-14 | THURS | 16H00 | 18H00 | SETUP OF WELCOME BACKDROP | AYO |  | HALL 1 | AYO +
2017-12-14 | THURS | 17H00 | 19H00 | TEST ALL LIGHTING CIRCUITS | SEUN |  | HALL 1 | NSE +
2017-12-14 | THURS | 17H00 | 20H00 | STAGE TO BE CARPETED | SEUN |  | HALL 1 | NSE + DAYO
FRIDAY 15TH DECEMBER 2017
2017-12-15 | FRI | 07H00 | 07H30 | ARRIVAL OF SECURITY PERSONNEL | JULIANAH |  | HALL 1 | NSE + K-SQUARE
2017-12-15 | FRI | 07H30 | 08H00 | SECURITY SWEEP OF VENUE & VENDOR ACCREDITATION | JULIANAH & MO |  | HALL 1 | NSE + WRIST BANDS + FRITZ + WRIST BAND NG
2017-12-15 | FRI | 08H00 | 15H00 | TABLE SCAPING AND DECOR | AYO |  | HALL 1 | NSE + STYLISTA + DINING & STYLE
2017-12-15 | FRI | 09H00 | 12H00 | INSTALLATION OF PHOTO BOOTH | YVETTE |  | HALL 1 | NSE + CINEMATICS
2017-12-15 | FRI | 09H00 | 11H00 | ALL COMMS TO BE INSTALLED | SEUN |  | HALL 1 | NSE
2017-12-15 | FRI | 10H00 | 11H30 | DELIVERY OF ALL SIGNAGE AND PLACEMENT | AYO |  | HALL 1 | NSE +
2017-12-15 | FRI | 10H00 | 20H00 | VIP LOUNGE FURNITURE TO BE POSITIONED | AYO |  | HALL 1 | NSE
2017-12-15 | FRI | 11H00 | 13H00 | TESTING OF INTERNET | JULIANAH |  | HALL 1 | NSE + COBRANET
2017-12-15 | FRI | 11H00 | 13H00 | INSTALLATION OF RED CARPET AT THE TERRACE | AYO |  | HALL 1 | NSE + DAYO
2017-12-15 | FRI | 12H00 | 12H15 | ARRIVAL OF ALL CATERING & DRINK SUPPLIERS | LANRE |  | HALL 1 | NSE + DIAGEO + CAFE NEO + BOLLINGER + KOTS CATERING + GRIND GRILL + ARTISAN + HANS & RENE + SALT LAGOS + LUCKY
2017-12-15 | FRI | 12H15 | 12H30 | ACCREDITATION OF ALL CATERING, DRINKS AND MEDIA SUPPLIERS FOR SET UP | LANRE & Yvette |  | HALL 1 | NSE + DIAGEO + CAFE NEO + BOLLINGER + KOTS CATERING + GRIND GRILL + ARTISAN + HANS & RENE + SALT LAGOS + LUCKY + ASURF + OBI SOMTO
2017-12-15 | FRI | 12H30 | 14H30 | SET UP OF ALL CATERING, DRINKS AND MEDIA SUPPLIERS | LANRE & YVETTE |  | HALL 1 | NSE + DIAGEO + CAFE NEO + BOLLINGER + KOTS CATERING + GRIND GRILL + ARTISAN + HANS & RENE + SALT LAGOS + LUCKY + ASURF + OBI SOMTO
2017-12-15 | FRI | 13H00 | 14H00 | FINISHING TOUCHES ON ALL MATTERS OF SET AND PROPS | SEUN |  | HALL 1 | NSE + STYLISTA + BEAUTIFUL IDEAS
2017-12-15 | FRI | 13H00 | 14H00 | FINISHING TOUCHES TO ALL BRANDING | AYO |  | HALL 1 | NSE + EVENTECTURE
2017-12-15 | FRI | 13H00 | 14H00 | SET UP OF ALL QUEUE CHUTES, INVITATION CHECK POINT | JULIANAH |  | HALL 1 | NSE
2017-12-15 | FRI | 13H00 | 13H30 | CALL TIME FOR HOSTESSES AND SECURITY PERSONNEL | MO & JULIANAH |  | HALL 1 | NSE + AAA + K-SQUARE
2017-12-15 | FRI | 14H00 | 14H30 | SECURITY ON SITE FULL STRICT ENFORCMENT OF ACCREDITATION | AYO & MO |  | HALL 1 | NSE + K-SQUARE + WRIST BANDS + FRITZ + WRIST BAND NG
2017-12-15 | FRI | 14H00 | 15H00 | SCRUB AND CLEAN THOROUGHLY EVENT SPACE | AYO & MO |  | HALL 1 | NSE + LANDMARK
2017-12-15 | FRI | 14H00 | 15H00 | MC, DJ AND ARTISTE SOUND CHECK | SEUN |  | HALL 1 | NSE + BOVI + DJ CUPPY + DJ OBI + DJ BIG N + TIWA SAVAGE
2017-12-15 | FRI | 15H00 | 16H00 | SECURITY MEETING ON SITE TO DISCUSS LAYOUT AND GUEST FLOW | AYO |  | HALL 1 | NSE + K-SQUARE
2017-12-15 | FRI | 15H00 | 16H00 | WALKTHROUGH WITH HOSTESSES + LIVE FASHION MODELS ARE DRESSED | MO |  | HALL 1 | NSE + AAA
2017-12-15 | FRI | 16H00 | 17H00 | LAST CHECKS, TIDY UP, LAST FOCUS LAST LAST | AYO & MO & SEUN |  | HALL 1 | NSE
2017-12-15 | FRI | 16H00 | 16H30 | DIESEL CHECK | SEUN |  | HALL 1 | NSE
2017-12-15 | FRI | 17H00 | 17H30 | ACCREDITATION OF ALL VENDORS FOR EVENT | MO |  | HALL 1 | NSE + K-SQUARE + WRIST BANDS + FRITZ + WRIST BAND NG
2017-12-15 | FRI | 17H30 | 18H00 | SECURITY PERSONNEL, HOSTESSES AND NS TEAM AT THEIR POSITION | MO & JULIANAH & EVERYONE |  | HALL 1 | NSE + K-SQUARE + AAA
2017-12-15 | FRI | 18H00 | 2H00 | EVENT GOES LIVE/SHOW RUNNING HANDLED BY STAGE MANAGER | SEUN |  | HALL 1 | NSE + LUCERE
SATURDAY 16TH DECEMBER 2017
2017-12-16 | SAT | 3H00 | 5H00 | AUDIO/BACKLINE/FLOOR LIGHTS/LOAD OUT | SEUN |  | HALL 1 | NSE
2017-12-16 | SAT | 3H00 | 6H00 | CASUAL STAFF MOVE IN; TEARDOWN OF TABLE SCAPE AND FALSE WALLS AND PSEUDO DEMO AREAS | SEUN & AYO & JULIANAH |  | HALL 1 | NSE + EVETECTURE
2017-12-16 | SAT | 3H00 | 6H00 | LOAD OUT ALL SUPPLIERS | JULIANAH |  | HALL 1 | NSE
2017-12-16 | SAT | 6H00 | 6H30 | ALL GENERATORS AND DIESEL TANKS TO BE REMOVED FROM SITE | SEUN |  | HALL 1 | NSE

## List of shots
Major aspects to capture:
A. SETUP DAY | Capture event setup day( Friday, December 14, 2017), photo of *The hall in its empty state *The hall after partitioning into different areas without furniture arrangement *The different areas being set up with furniture arrangement *The different areas without decor and technical *The different areas being set up with decor and technical elements *NS team during set up
B. EVENT DAY | Capture event day, photo of
1. All hostesses dressed up
2. Each group of hostesses positioned at their different areas.
3. NS crew together, before the event goes live.
4. The venue without guests (aerial or panorama).
5. All security in position
6. Check-in area *Guests during check-in process. *Hostesses during check-in process. *Guest list verification. *Photos of arriving guests. *Up close photos of a hostess attending to/receiving a guest.
7. Guest interacting with the tunnel
8. Capture moments at the red carpet/cocktail area. *Team photos of each company *Guests photos on red carpet *Team photos with set design
9. Dining Area *Employee award *Lipsing battle *Grand Pianist and area
10. After Party *Dancefloor with guests dancing

## AdminBasecampTeam Hospitality
Basecamp request sheet
Event name:
Event date:
Project Manager:
Basecamp location:
Event time:
Item | Quantity | Requester | Comment
TV SCREENS & STANDS | -
PRINTER
A4 PAPER
STAPLER & STAPLE PIN
CREW TAGS
EXTENSION CABLE/CABLE REELS
CLIPBOARDS
INTERNET
SCISSORS
VENDORS WRISTBAND
PENS
MARKERS
HOSTESS NAME TAG JACKETS
TABLE NUMBER | -
RESERVED SIGNS
CELLOTAPE
TABLE NUMBER STANDS | -
LETTER LABELS
COCKTAIL TABLES/CHAIRS | -
CUE BREAKERS | -
TABLE COVERS
FIRST AID BOX
EXTRA WALKIE TALKIES
Umbrellas
Kettle
BIN BAGS
HOSPITALITY SCHEDULE, EVENT DAY.
CALL TIME
ONSITE OFFICE/BASE CAMP
| TIME | BATCH 1 | BATCH 2 | BATCH 3
MEAL 1 (20 minutes)
MEAL2 (20 minutes)
CHANGING SHIFTS (30 minutes)
ACCOMMODATION PLAN
TEAR DOWN/GO HOME:

## Guest management + casual staff
GEMs and supervisor allocation
Quantity | Location | Task | GEM | Supervisor/NS team member | GEM contact/phone number
2 | Just before the check-in point | Direct guests to their assigned check-in table
7 | Regular check-in area | Check and highlight guest's names on the provided computer
Wear wristbands for guests
3 | VIP check-in area | Check and highlight guest's names on the provided computer
Wear wristbands for guests
1 | Entrance of the tunnel | Direct guests to the cocktail area
3 | Cocktail area (After cocktails and guests have moved into the dining area, the GEMs will move into the afterparty area to welcome afterparty guests and ensure they are served) | Ensure guests are served and direct guests to video booth
Ensure guests are served and direct guests to the "Celebrate your 2017" wall
Ensure guests are served and direct guests to photo props and photo area
1 | Stage - MC's assistant | To assist the MC on stage with gifts and any other thing
1 | Green room | Ensure the artistes are well taken care of
65 | Dining Area (A GEM to be assigned to a table) | Ensure every person on the designated table is well taken care of | Table 10 -
Table 11 -
Table 12 -
Table 13 -
Table 14 -
Table 15 -
Table 16 -
Table 17 -
Table 18 -
Table 19 -
Table 20 -
Table 21 -
Table 22 -
Table 23 -
Table 24 -
Table 25 -
Table 26 -
Table 27 -
Table 28 -
Table 29 -
Table 30 -
Table 31 -
Table 32 -
Table 33 -
Table 34 -
Table 35 -
Table 36 -
Table 37 -
Table 38 -
Table 39 -
Table 40 -
Table 41 -
Table 42 -
Table 43 -
Table 44 -
Table 45 -
Table 46 -
Table 47 -
Table 48 -
Table 49 -
Table 50 -
Table 51 -
Table 52 -
Table 53 -
Table 54 -
Table 55 -
Table 56 -
Table 57 -
Table 58 -
Table 59 -
Table 60 -
Table 61 -
Table 62 -
Table 63 -
Table 64 -
Table 65 -
Table 66 -
Table 67 -
Table 68 -
Table 69 -
Table 70 -
Table 71 -
Table 72 -
Table 73 -
Table 74 -
2 | Extras
Total = 85 GEMs
Afterparty GEM Allocation (To be chosen from the 85 GEMs)
10 | Afterparty
Casual Staff

## Gifts
Gift/memorabilia | Gift/memorabilia type | Gift/memorabilia instructions

## Invitation Distribution Record
Invitation Distribution Record Sheet
Delivered
Not Delivered
Individual/Company Name | Individual/Company Address | Contact Person Taking Delivery | Phone No of Contact Person | Content of Invitation Suite | Courier Company | Dispatch Date | Delivery Status | Comment
DSTV/Africa Magic
EbonyLife TV
Sanofi
Interactive CT
Cobranet
First EPDC
RnB PR
HC Bonum
Business Day
Landmark
Diageo | 24, Oba Akran Avenue, Ikeja, Lagos
SAS
Wheatbaker
Oasis Medspa | No 21 Cameron road,Off Kingsway road, Ikoyi
Inkhearts | 9b, Ige Shonubi Crescent, Parkview Estate, Ikoyi
Yomi Casual | 16, Caroline Atuonah street, Lekki Phase 1, Lekki, Lagos.
Megavision | 12A, Atinuke Ologunde Street, Pako B/stop, Ogudu GRA.
Guardian Life
KOTS Catering
Light Design | Light Design Studios, Oniru, Victoria Island, Lagos
Play TV/Glitz
Sweet Kiwi | Admiralty way, opposite Stanbic IBTC, Lekki Phase 1
NACK Store | Road 1, Ikota Shopping Complex, Lekki, Ajah, Llagos.
Cinematics NG | The Garnet Building, Lekki Epe Express way, by Igboefon, Lekki.

## Mo and Orby Only!!!
First Name | Last Name | Email Addresses | Phone Number | Company Name | Wristband Color | Table Number | GEM | Contact Person Taking Invitation Delivery | Phone No of Contact Person | Content of Invitation Suite | Courier Company | Dispatch Date | Invitation status | included in bulk sms database
Andrew | Daudu | andrew@cobblestone-ng.com | 8055577085 | Cobblestone | Red | 37/38 | Orby
Adenike | Oghuvbu | adenike@cobblestone-ng.com | 8055577046 |  | Red | 37/38
Martin | Ejekam | martin@cobblestone-ng.com | 8055577090 |  | Red | 37/38
Harpreet | Maann | harpreet@cobblestone-ng.com | 8055577089 |  | Red | 37/38
Olayinka | Obitayo | olayinka@cobblestone-ng.com | 8055577087 |  | Red | 37/38
Bayo | Oyenuga | adebayo@cobblestone-ng.com | 8055577006 |  | Red | 37/38
Olufemi | Ajayi | olufemi@cobblestone-ng.com | 8055577068 |  | Red | 37/38
Peter | Agbaoye | peter@cobblestone-ng.com | 8055577086 |  | Red | 37/38
Temitope | Omojola | temitope@cobblestone-ng.com | 8055579783 |  | Red | 37/38
Oluwatimilehin | Oni | timi@cobblestone-ng.com | 8055578473 |  | Red | 37/38
Olusola | Odukoya | olusola@cobblestone-ng.com | 8055577083 |  | Red | 37/38
Ezekiel | Ayo-Ayorinde | ayo@cobblestone-ng.com | 8055577008 |  | Red | 37/38
Adeniyi | Solarin | adeniyi.solarin@gloworld.com | 8055577613 |  | Red | 37/38
Mofoluwaso | Akindele | akindelefolu@gmail.com | 8055577094 |  | Red | 37/38
Emmanuel | Bello | emmanuelbello76@gmail.com | 8055577045 |  | Red | 37/38
Bella | Disu |  |  |  | Gold | 37/38
Yeside | Doregos |  |  |  | Gold | 37/38
Benita | Awosanya |  |  |  | Gold | 37/38
| Kolawole 19 |  |  |  | Gold | 37/38
| Kolawole 20 |  |  |  | Gold | 37/38
20
Lilian | Williams | lilian.williams@interactivect.net | 8158942726 | Interactive CT | Gold |  | Orby
Ajoke | Baruwa | ajoke.baruwa@interactivect.net | 9095326293 |  | Red
Temitope | Bright | temitope.bright@interactive.net | 8101180207 |  | Gold
Sarat | Abdulwahab | sarat.abdulwahab@interactivect.net | 8034250404 |  | Red
Temitayo | Salawu | temitayo.salau@interactivect.net | 8108156235 |  | Red
Henry | Igwe | henry.igwe@interactivect.net | 8068084995 |  | Red
Dorcas | Ekanem | dorcas.ekanem@interactivect.net | 8033302162 |  | Red
Edmund | Adegbotolu | edmund.adegbotolu@interactivect.net | 8104270053 |  | Red
Victoria | Olaifa | victoria.olaifa@interactivect.net | 8134531477 |  | Red
Ololade | Okunoren | ololade.okunoren@interactivect.net | 8080808026 |  | Red
Adebimpe | Odulana | bimpe.odulana@interactivect.net | 8083779272 |  | Red
Blessing | Abeng | blessing.abeng@interactivect.net | 7062522662 |  | Red
Babatunde | Okunuga | babatunde.okunuga@interactivect.net | 8069844847 |  | Red
Fortune | Ikemefuna | fortune.ikemefuna@interactivect.net | 8067366601 |  | Red
Adejoke | Adegoke | joke.adegoke@interactivect.net | 8155196615 |  | Red
Chris | Apegbua | chrisgbua@gmail.com | 7066344901 |  | Red
Olaitan | Ahmed | olaitana.ict@gmail.com | 8085175868 |  | Red
Imisi | Sulaiman | imisis.ict@gmail.com | 8139551542 |  | Red
Oluwatimilehin | Omotoso | timilehino.ict@gmail.com | 8123411196 |  | Red
Agboola | Solomon | agboolas.ict@gmail.com | 8094825622 |  | Red
Kelly | Onyeogi | lilian.williams@interactivect.net | 8158942726 |  | Red
Olatayo | Baruwa | ajoke.baruwa@interactivect.net | 9095326293 |  | Red
Feso | Bright | temitope.bright@interactive.net | 8101180207 |  | Red
23
Olarewaju | Ojo | ojo.o@cobranet.ng | 8079292281 | Cobranet | Red |  | Orby
Ifeanyi | Obasi | ifeanyi.o@cobranet.ng | 8079292289 |  | Red
Ifeanyi | Kafayat Anibi | kaffy@cobranet.org | 8079292294 |  | Red
David | Ovuworie | david.ovuworie@cobranet.ng | 8079292252 |  | Red
Abimbola | Lawanson | bimbola.lawanson@cobranet.ng | 8079292275 |  | Red
Kayode | Adeniyi | adeniyi@cobranet.org | 8079292295 |  | Red
Victory | Adebanjo | victory.adebanjo@cobranet.ng | 8079292277 |  | Red
Chatru | Moorjani | chatru.moorjani@cobranet.ng | 8079292286 |  | Red
Joseph | Minas | joe_minas@cobranet.org | 8079292244 |  | Red
Jamil | Chaptini | jbc@cobranet.org | 8079292222 |  | Red
10
Demola | Adeyemi-Bero |  | 8035567990 | First EPDC | Gold |  | Orby
Yemisi | Bero (Dr Mrs) |  |  |  | Red
Abdulganiyu | Salako |  |  |  | Red
Modupe | Salako (Mrs) |  |  |  | Red
Anita | Edo-Osagie |  |  |  | Red
Anita | Edo-Osagie Plus 1 |  |  |  | Red
Carol | Anim |  |  |  | Red
Anulika | Mojekwu (Ms) |  |  |  | Red
Cees | Uijlenhoed |  | 07094250548 08131176225 |  | Gold
Daniella | Uijlenhoed (Mrs) |  | 8023134451 08092852004 |  | Red
Defolu | Olufon |  |  |  | Gold
Funke | Olufon (Mrs) |  |  |  | Red
Emmanuel | Maduawia |  |  |  | Red
Loretta | Maduawia (Mrs) |  |  |  | Red
Emmanuel (Dr) | Enu |  |  |  | Gold
Rita | Enu (Mrs) |  |  |  | Red
Francis | Onuorah |  |  |  | Red
Francis | Onuorah Plus 1 |  |  |  | Red
Mathilda | Ovuru |  |  |  | Red
Mathilda | Ovuru Plus 1 |  |  |  | Red
Olatunbosun | Oni |  |  |  | Red
Funmi | Oni (Mrs) |  |  |  | Red
Olayide | Williams |  |  |  | Red
Olayide | Williams Plus 1 |  |  |  | Red
Ololade | Adesalu |  |  |  | Red
Abayomi | Adesalu (Mr) |  |  |  | Red
Rasheedat | Ninalowo |  |  |  | Red
Adetola | Yosouph (Ms) |  |  |  | Red
Ronke | Niagwan |  |  |  | Red
Naanma | Niagwan (Mr) |  |  |  | Red
Rotimi | Adefarasin |  |  |  | Red
Jacqueline | Adefarasin (Mrs) |  |  |  | Red
Stevens | Komolafe |  |  |  | Red
Happiness | Stevens-Komolafe (Mrs) |  |  |  | Red
Titilayo | Niyi-Abodunrin |  |  |  | Red
Niyi | Abodunrin (Mr) |  |  |  | Red
Uchenna | Nwokafor |  |  |  | Red
Uchenna | Nwokafor Plus 1 |  |  |  | Red
Aderemi | Gbolagade |  |  |  | Red
Mulikat | Yusuf (Mrs) |  |  |  | Red
Odein | Ajumogobia |  | 8033231126 |  | Gold
Awuneba | Ajumogobia (Mrs) |  | 8022951600 |  | Red
Lawrence | Sawyer |  |  |  | Red
Abiola | Sawyerr |  |  |  | Red
Godwin | Udott |  |  |  | Red
Toye | Tamuno Mr |  |  |  | Red
Niyi | Sanyaolu |  |  |  | Red
Temitope | Sanyaolu (Mrs) |  |  |  | Red
Adeoye | Adefulu (Mr) |  |  |  | Red
Adeoye | Adefulu (Mrs.) |  |  |  | Red
50
|  |  |  | DSTV |  |  | Modupe
|  |  |  | RnBPR |  |  | Orby
|  |  |  | HCBonum |  |  | Modupe
|  |  |  | Business Day |  |  | Orby
|  |  |  | Landmark |  |  | Modupe
|  |  |  | Diageo |  |  | Orby
Donna | Makebe | Donna.Mokebe@sas.com |  | SAS | Red |  | Modupe
Donna | Makebe (Plus 1) |  |  |  | Red
Donna | Makebe (Plus 2) |  |  |  | Red
3
Mohammed | Jalloh | Mohammed.Jalloh@sanofi.com | 8174600440 | Sanofi | Red |  | Orby
Adetunji | Olusegun | Adetunji.Olusegun@sanofi.com | 8174600359 |  | Red
Abel | Bamiduro | Abel.Bamiduro@sanofi.com | 8174600521 |  | Red
Philip | Ikeme | Philip.Ikeme@sanofi.com | 8174600441 |  | Red
Chukwuemeka | Enyimba | Chukwuemeka.enyimba@sanofi.com | 8174600458 |  | Red
Oscar | Imomoh | Oscar.Imomoh@sanofi.com | 8174600404 |  | Red
Folake | Odediran | Folake.Odediran@sanofi.com | 8174600389 |  | Red
Olayemi | Johnson | Olayemi.Johnson@sanofi.com | 8174600451 |  | Red
Obiora | Ofoegbu | Obiora.Ofoegbu@sanofi.com | 8174600405 |  | Red
Olaniyi | Taiwo | Olaniyi.Taiwo@sanofi.com | 8174600510 |  | Red
Oluwatomi | Fakolade | Oluwatomi.Fakolade@sanofi.com | 8174600459 |  | Red
Raphael | Ekeh | Rapheal.ekeh@sanofi.com | 8174600488 |  | Red
Abiodun | Oladapo | Abiodun.Oladapo@sanofi.com | 8174600438 |  | Red
Oluwaseyi | Awosanya | Oluwaseyi.Awosanya@sanofi.com | 8174600473 |  | Red
Sherriff | Ayinde | Sherriff.Ayinde@sanofi.com | 8174600487 |  | Red
Oluwole | Dotun | Oluwole.Dotun@sanofi.com | 8174600553 |  | Red
Babatunde | Aderele | Babatunde.Aderele@sanofi.com | 8174600362 |  | Red
Adamson | Gbenga | Gbenga.adamson@sanofi.com | 8174600383 |  | Red
Bukola | Aguddah | Bukola.Aguddah@sanofi.com | 8174600358 |  | Red
Uzoamaka | Amatokwu | Uzoamaka.Amatokwu@sanofi.com | 8174600370 |  | Red
Agbolade | Oladimeji | Agbolade.Oladimeji@sanofi.com | 8174600361 |  | Red
Ndirangu | Simon | Ndirangu.Simon@sanofi.com | 8174600478 |  | Red
Mojisola | Ogedengbe | Mojisola.Ogedengbe@sanofi.com | 8174600382 |  | Red
Clementina | Ugwu | Clementina.Ugwu@sanofi.com | 8174600455 |  | Red
Temitope | Osobu | Temitope.Osobu@sanofi.com | 8174600534 |  | Red
Elizabeth | Kolade | Elizabeth.Kolade@sanofi.com | 8174600 |  | Red
Kikelomo | Ayanbadejo | Kikelomo.Ayanbadejo@sanofi.com | 8174600445 |  | Red
Mayowa | Ajayi | Mayowa.Ajayi@sanofi.com | 8174600480 |  | Red
Amarachi | Jonas- Okoro | Amarachi.Jonas@sanofi.com | 8174600363 |  | Red
Idowu | Olabintan | Idowu.Olabintan@sanofi.com | 8174600434 |  | Red
30

## Planning status
TUXP Team Status Update
Done
Pending
Category | Tasks | Responsibility | Deadlines | Status | Comments | Late
Finance and Budgeting |  | Abolore
| Prepare/draft costs estimates | Abolore |  |  | Please also create scenario for extension for guests in a marquee for after party however this must make financial sense
| Obtain real costs based on industry price | Abolore |  |  | Determine break even point without sponsors, event costs not to exceed tables sales. Pre determine profit target also considering last year's sales
| Break costs down based on sponsorship ideas | Abolore/Chinwe
| Facilitate negotiations to save costs | Abolore
| Raise the necessary cheques and communicate terms of payment to all suppliers/partners | Abolore
Table sales & sponsorships |  | Chinwe + Esther
Table Sales | Articulate value add to guests, new and improved additions to 2015 edition and table/add on costs
Draft/Prepare letters for prospects and get sign off
Create prospect list for table sales
Send emails/newsletter to prospects A and B, starting with A first
Follow up emails with phone calls where applicable and get some form of committment and create a list /table as you engage prospects
Table sales end
Sponsorship drive | Create a table/articulate sponsorship opportunities
Send emails/letters to shortlisted prospective companies with detailed and clear requests and ROI
Follow up letters/emails with phone calls
Create a document of sponsors who have gone on board and list all the deliverables both ways
Design/create agreements and send to sponsors
Engage the accounts departement to sync
Sponsorship souvenirs sourcing |  | Chinwe
| Determine the different opportunities for gifting |  |  |  |  | 22
Create a list of gifting companies we can partner with
Engage/meet with them to share value proposition
Confirm all arrangements and document all agreements
Guest Experience Management |  | ORBY/JULIANAH
Team selection/audition/job desciptions based on deliverables | Create job profiles based on role needs
Place ad/call for audition
Selection of team members
Create training materials and train selected team members
Set up process for monitoring team members managing the different accounts
Guest management | Determine which team member manages what account
Communicate changes and plans to the team as they come and standby to be creative as challenges arise
Hostesses outfit | Share ideas for outfit for hostesses
Confirm and finalise final outfit, source and obtain costs
Obtain invoices, sign off and make necessary payments
Guest experience | Determine fun ideas and activities for guests
Share thoughts and ideas with team
Make a selection and obtain a quote
Order the necessary props as early as possible
Take delivery of the props
Goody bags | Work with team to determine number of goody bags and when they'd be available
Determine strategy for gift distribution and advise as necessary
Plan for transportation of the gifts to the venue and storage
Assign distribution of gifts to hostesses
Venue Management |  | Julianah
Check for hall availability and book the venue
Obtain invoice and terms of agreement
Thoroughly go through the terms and raise any issues/concerns
Ensure deposit is paid against the venue to secure the booking
Confirm set up lines and communicate our plans to venue as they change to ensure alignment
Make complete payment
TUCP Campaigns |  | Chinwe
Identify the different campaigns
Break down the tasks for each campaign
Assign the different roles and ensure all deliverables are met on time
Venue layout & design |  | Ayo
Study overall presentation of the event to have an understanding of the venue layout
Create a floor plan based on event flow and get a sign off
Share plans and ideas with venue designers and send a formal brief stating the different areas, functions and needs
Receive feedback and initial ideas from venue designers
Schedule first site meeting for a walk through
Share venue designer's ideas with team and send feedback
Obtain quote/invoice from supplier
Negotiate and reach an agreement with the supplier
Work with accounts to make a deposit payment
Agree and communicate with the venue designers the set up times and any other info from the venue managers
Schedule pre event sampling of every aspect of the venue layout
Communicate changes and plans to the team as they come and standby to be creative as challenges arise
Schedule final site meeting
Supervision of all supplies and construction for the venue layout
Source for industrial confetti blaster and/or bubble thrower
Catering & tablescaping |  | Lanre
Catering | Confirm guest estimate
Contact KOTS the caterer for a discussion on event brief, menu and budget determination
Obtain menu from KOTS based on the budget communicated and sign off with FVO
Confirm/agree costs with KOTS and obtain invoice
Work with accounts to pay a deposit against the costs
Schedule first site meeting for a walk through
Confirm/agree on logistics and planning on site with KOTS
Communicate and changes and plans to the team as they come and standby to be creative as challenges arise
Schedule final site meeting
Tablescaping | Determine style and needs
Shop around for rental companies that can provide plates, cutlery, chargers and napkins of high quality
Schedule inspection of the rentals to ensure they are of the best quality and that we have enough
Obtain quote and negotiate based on market rate and budget
Confirm and agree on logistics and transportation etc
Make a deposit payment
Make final payment
Drinks & Bar |  | Abolore/Wale
Source for drinks company and send them a VERY CLEAR brief, please include cocktails for pre event
Decide who to go with depending on quote, quality of service, experience and overall presentation
Meet with supplier to discuss the detailed logistics
Schedule first onsite visit
Make payment deposit
Communicate changes and plans to the team as they come and standby to be creative as challenges arise
Schedule final onsite visit
Talent engagement and management |  | Seun
Shortlist and determine the different artistes and performers
Confirm the acts based on availability and fit
Make enquiries on availability and costs
Negotiate and agree on costs based on available funds and budget
Obtain invoices from all performers
Make deposit payments
Send a detailed brief to all talent informing them of the expectations and timing
Communicate changes and plans to the team as they come and standby to be creative as challenges arise
Determine green room needs and obtain a quote also determine which rooms to allocate
Technical/Stage Production |  | Seun
Shortlist technical production company
Determine mobile screen company
Determine company or sponsor for plasma screens for Bond effect
Send a detailed brief to all technical crew based on the needs as created in the presentation
Obtain quotes from all technical team based on needs
Negotiate and agree terms based on budget
Draft an agreement will all technical companies including deliverables
Make deposit payment
Schedule a first site visit
Schedule a final site visit
Cue sheet and event flow
Create a draft event flow based on event elements
Meet with the technical director to see how the event flow works against what is expected
Create a cue sheet and sign off with team
Ensure all the elements work and all the performers are aligned
Archival |  | Esther
Photography | Determine photography needs
Source and speak to different photographers and make a presentation of your top 3 with your personal selection and why
Finalise on choices and send a more detailed brief to the photographers
Work with the GEMs to ensure group/company photos are well organised, create schedules as companies purchase tables
Videography | Book videographer
Meet with video team and agree on overall theme and style of the video
Communicate changes and plans to the team as they come and standby to be creative as challenges arise
Team welfare/Admin |  | Olaide
Study event tasklist and determine team member roles
Create a document/table to show who needs to be where at what time to determine needs
Draw up a budget based on the needs and discuss with accounts for approval
Communicate changes and plans to the team as they come and standby to be creative as challenges arise
Ensure team mates are well taken care of so they can be productive without distractions
Ensure team mates are well taken care of so they can be productive without distractions
Security + Traffic |  | Julianah
Discuss with team to determine security and traffic needs for the event
Source different security companies and shortlist/ present your top 3 to the team with reasons
Select security and traffic team and obtain invoices to present to accounts
Schedule a walkthrough of the venue with the heads of the security and traffic team
Send a very detailed brief to the service provides detailing deliverables and time
Ensure execution is as planned
Inter company competitions |  | Tori
Discuss with team to determine the various competitions
Discuss ways to communicate the info to the companies/attendees
Brainstorm on appropriate prizes for winners
Make a list of all the prizes for the evening to help organise for sponsorship partners
Make a list of all the participating companies as they register, work with the GEMs on this

## Decor Cost Breakdown
Areas | ITEMS | UNIT COST | QUANTITY | SUB TOTAL
Registration Area | Table Cover | 1000 | 6 | 6000
| Skirting | 10000 | 1 | 10000
| Centerpiece | 5000 | 1 | 5000
| Red Carpet | 0 | 1 | 0
Cocktail/Red Carpet | Cocktail Tables | 8000 | 6 | 48000
| Coctail Table Covers | 1000 | 6 | 6000
| Center Piece | 2000 | 6 | 12000
| Red Carpet | 0 | 1 | 0
Dining Area | Table Linen | 1000 | 65 | 65000
| Centerpiece with candles | 5000 | 65 | 325000
| Flower arrangements | 2000 | 65 | 130000
VIP Lounge | Drapes on Cabana | 30000 | 1 | 30000
Entire Hall | White on black drapes to cover the panels around the venue | 700000 | 1 | 700000
| Rental of lift for draping (Set up & Tear down) | 50000 | 2 | 100000
| Transportation | 70000 | 1 | 70000
| Service charge | 250000 | 1 | 250000
Total |  |  |  | 1757000
ITEMS | UNIT COST | QUANTITY | SUB TOTAL
Napkins
Napkin Rings
Charger Plates
Wine Glass
Water Glass
CutlerIies

## Guest Activity
Guest Activity Tracking Sheet
S/N | Name of Company | Table Number | Checking in in seconds | Champagne with candy floss on arrival | Cocktails and canapes at red carpet | Red carpet photos | Team photos | Guest experience card (“5 senses”) | All 3 course meals | Desserts | Wine and soft drinks/Water | Gourmet after party snacks and champagne at after party | Gourmet after party snacks and champagne at after party | Hamper at check out
1 | No Surprises Events | 11
2
3
4