## Sheet1
Client Post Event Report
Item | What Worked | What Didn't Work | Action Taken | Lesson Learned
Payment schedules and vendor management |  | Due to the delay in receiving the final confirmation of the list of SLAY vendors, final list of rented items could not be finalised which affected the delay in the budget approval and payment came 2 days to the event. This caused a bit of pressure and difficulty in managing some vendors. | New suppliers had to be sourced and engaged as some cancelled on us as they got booked by other clients | All vendors are to be confirmed and payments made at least one week to event date to avoid rush and cancellations
Guest management - Check-in | Athough there was a delay in the start of the check-in process, when it eventually kicked off, it was quick | There was a delay in the arrival of the wristbands for guests & speakers at the check-in points when the event started. This caused a 30 min delay in the start time as guests & speakers could not access the venue immediately they arrived. | Client suggested we improvise by tagging the guests that had arrived with the vendor wrist bands while we waited for the wristbands to arrive. There was a 30 min delay | ALWAYS have the wristbands for guests/speakers on site at least an hour to kick off.
and there were no long queues at either of the check-in stations. The decision to have 2 registration points (one for general admission and the other for speakers was a good call. We had a total of 10 check-in points manned by our hostesses)
Power Distribution | All the areas got power as initially agreed; all the 4 stages, 2 master classes, marketplace, food court, leadership circles, creche and premium lounges/green rooms | There was power outage in the Market Place for about an hour. | Another generator was delivered to replace the damaged generator and power was restored in these areas, as well as an attempt to regulate the power placement on the different generators. | In future, specific appliance should be requested from the vendors, specifying the voltages of the appliances, rather than just informing them of what will be provided. They should also be told to communicate with the team other special ELECTRICAL requirements in advance
This was because the generator supplying power here tripped off, vendors connected appliances with higher voltages than was specified. It was earlier communicated via SLACK that each tent would get a 13amp socket, a bulb and a fan.
This resulted in an unbalanced power distribution and caused certain stalls in the
Food Court to have frequent power trip-offs.
Tent Distribution for vendors | Agreed number of tents for the marketplace was on ground and mounted before the vendors started arriving. | There was a slight delay in the allotment of vendor tents as the final plan was not shared with the NS team until the morning of the event. The marketplace was set up to accommodate the number of vendors evenly following the instruction to not have any tents empty. | Additional tents were set up to accommodate the repositioning of the vendor allotment in the market place. | Have a booking of extra tents to pre-empt extra orders and to avoid running out of tents.
|  | The Leadership Circles area did not get the number of tents required for the area as we had to use the tents originally allocated for the LC area here to make up for the extra positioning in the marketplace(2) and the TRACE tent (1). It was too late to order more tents from out suppliers. | The leadership circles area was rearranged to make use of the tents that were left. | Confirm all tent requirements no later than 72 hours before event
goes live to avoid last minute changes
Security | During the event, there was no crisis or harassment from touts or external miscreants | Bomb sweep did not happen as at when slated, so it was difficult to ensure everyone not related to the event was flushed out, especially the market women hawking and those that tore down for the church event on the previous day. | When the event started, everyone was sent out and the vendors were accredited when the replacement wristbands arrived. | For a venue that big, sweep should be done from the day before and immediately after set up, to control unwanted entry.
Security deployment started late.
Also, the vendor wristbands for the guests that was swapped delayed the live accreditation for the vendors.
Branding/Signage | All branding and signage were produced and placed before the event started. Early payment to the supplier allowed enough time for production | N/A | N/A | N/A
Sound | The sound was distributed to all the agreed areas: performance stage, 2 masterclasses and 3 other stage. | The sound supplier came 2 mics short so 2 of the stages were one mic short. | The sound supplier was able to rectify the fault in short time | Ensure that all technical equipments supplied for the event are verified on time during set up.
There was a period at the beginning of Show Dem Camp's performance when the mics on the performance stage stopped working
Lighting | Set up for lights in the | N/A | N/A | N/A
performance area and the 3 other stages were completed before the event started. We generally had good lighting at the venue
Stage design and execution | The stage design was created according to agreed specification and set up was completed in good time. | There was a last minute change with the spandex covering agreed with client. The spandex was substituted with a marquee covering due to last minute cancellation by an earlier engaged supplier | N/A | Better management of supplier
Also the performance stage was not covered in spandex due to the supplier's last minute cancellation.
Sponsors/Activation area | The set up of this area completed according to the agreed layout. | Power connection in this area was not completed in due time. | The power distribution team eventually connected power to all the tents in this area and was on ground throughout the event to reconnect power to every tent with power outage. | A separate generator should have been provided for the air conditioner or to ensure that the capacity for the designated generator for the Baby Lounge area be not less than 300 KVA
There was also power outage in this area a few times during the event
The air conditioner provided for the Baby Lounge didn't work because of overload on the generator provided for the area. However, mistfans were deployed to the area.
Food court | The benches, ottoman and the parasols were set up in good time before the event started. | N/A | N/A | N/A
The layout was presentable, and worked for guest flow between areas.
Greenrooms and speaker hospitality | All the green rooms had the agreed furniture and 2 hostesses managing the guests upon arrival. Catering was handled by the Goldielux Catering with the help of designated hostesses in each of the green rooms | Only two of the three green rooms were set up before the event started due to late set up start time | Pressure was mounted on suppliers to ensure that the third greenroom was eventually set up and completed. | Air conditioners should be strongly recommended to the client for any tents requiring full side covers.
|  | The greenroom was hot as the mistfans provided in these tents were not sufficient. The weather was hotter than anticipated | Other side openings were created in the greenroom tents to create proper ventilation.
Parking | LASTMA officials were on ground to assist with traffic and parking around the venue. This created an ease of movement for guests who came with their cars. | N/A | N/A | N/A
Overall design and layout as agreed in the floor plan | The overall layout of the event was based on the agreed floor plan. However, the media room was moved to the side of the creche as requested by the client. | N/A | N/A | N/A
Information Booth |  | Only one tent was set up and was used as the SLA stand in the food court area. | N/A | Have a booking of extra tents to pre-empt extra orders and to avoid running out of tents.
Mobile Toilets | The 2 luxury mobile toilets were provided and positioned close enough to the greenrooms. They were also adequately cleaned during the course of the event | N/A | N/A | N/A
Ambulance | The Ambulance arrived the venue in due time | N/A | N/A | N/A
Event set up | We were able to finish most of the set up in record time especially as we started set up very late due to the church event the day before that finished later than expected |  |  | Set up should start at least 24 hours before event starts to allow time for full set up and avoid mistakes