## Contact Report
Meeting date: 3rd April 2018
Attendees: Phone call meeting between Ms Folake(Client) and Ronke Adeneye(GIW)
Event Date: 30th June, 2018
Event Time: 7am- 10pm
Event Venue: Akiita Hall and April Room Ilupeju
Item | Comment | Next Steps | Responsibility | Deadline | Update
Event look and feel | Fun and Glamourous. Guests should feel relaxed throughout the event. Client's event budget is N8million (which is subject to change) and theme is "little bit of old school ". For traditional wedding: calm, classy and Africanish | Design mood board for client to sign off | GIW | 13/4/2018
Guest size | 300/400. Age range is 25-70, comprising of family, friends and colleagues. | Plan to cater for 700 guests | GIW + Client | N/A
Invitations | Paper and E-invitations will be sent to guests and handled by the GIW. It must be vetted by Bride's Father before it is sent out and should be ready as soon as possible. Not strictly by invitation | *Send invitation card designs to client for approval *Client to finalize on design | GIW | 13/4/2018
Guest's experience | *GIW suggested a backdrop/step and repeat wall at the entrance *GIW suggested a photo-booth with polaroid cameras for guests to take pictures and print polaroids on site. GIW also suggested a guest book for kind words and photos to be placed in. *A little bit of old school themed Slomo video booth can also be considered *Hostesses were suggested to help manage guests experience during the event | *GIW to propose photo-booths and guest book to client | GIW | 13/4/2018
Décor | Candles and flowers as centre piece instead of elaborate flowers only | *Décor Vendor to send décor mood board *GIW to follow up with décor vendor | 360 Events GIW | 17/4/2018
Pyrotechnics | Smoke, fog, fire works, | *GIW to propose options of grand reception entrance *Client to give a feed back on how the entrance will look like | GIW Client | 13/4/2018
Seating | 10 seater Banquet tables | *Confirm type of chairs and table available at the venue and share photos with client *Other options to be included in mood board *Options of seating styles should be included in mood board | GIW | 2018-11-04
Catering | Client will want us to check with her sister, Funmi and welcomes recommendation for Menu. | *GIW to liase with Funmi on number of course meal, menu options, serving style, menu cards, chargers and cutleries *Contact Adetutu of Pretty Dreams Events Limited for Desserts | GIW | 2018-11-04
Drinks | Client would like us to check with Kola on this | GIW to liase with Mr Kola on types of drinks, serving style and glasswares | GIW
Lighting | 360 Decor would provide a purple, black and white a bit dim lightening | Contact 360 Events to share their lighting plan | GIW | 2018-11-04
Overflow | The hall for traditional wedding would be served for overflow | *Propose a guest movement plan for the overflow *Design a seating style for the overflow as well as the logistics involved | GIW | 24/04/2018
DJ | Songs with vulgar words should not be played. A requested song to be played during father and daughter's dance (one of bride's favorite old school song). GIW provides an easy to learn short video for choreography for bride and her sister's dance. 'Who runs the world' by Beyonce should be played. it should be mixed with the ending part of Formation'. Dj ensures it is properly mixed and sent to the bride before the day. Yoruba and Phyno songs should be playing knowing it is a mix wedding. The parents should also not be left out of the music. Every age group should be considered. | Contact Mr Kola and communicate the cliemt's wish | GIW | 2018-11-04
MC | Mr Kola is handling this | Contact Mr Kola to get the contact of the MC | GIW | 2018-11-04
Surprise performance | No surprise performance or video will be done | N/A | N/A | N/A
Sound equipment | GIW should get a very good sound and equipment vendor | *Recce venue to confirm the sound items available *Get suppliers and get quotes to compare costs | GIW | 2018-11-04
Cake | Client contacted Splendidsplash for the traditional and reception cake. The traditional cake should be diced and shared during reception. | Follow up with Splendidsplash to further communicate client's vision | GIW | 2018-11-04
Photographer | Client wants photographs to be excellently captured but not too pricey and is open to suggestions based on who we've worked with. | Propose photographers and share instagram handle with client to view work | GIW | 2018-06-04
Videographer | Client is open to suggestions | Share options with client to view work | GIW | 2018-06-04
MC | Contact Kola | Follow up with Mr Kola on MC booking and confirmation | GIW | 2018-11-04
Security | Security should be considered | GIW to source and book security personel for the event | GIW | 30/4/2018
Keepsakes | Client would like every adult to have a pack of keepsake. Keepsake must be durable and relevant in usage. Carrier bag | GIW to recommend and send photos of samples to client. | GIW + Client | 17/04/2018
Accomodation | Client welcomes recommendation from GIW. Hotel must be within Ilupeju. To cater for Bride, Groom, bride's maids and groom's men and atleast 10 guests that will be travelling down. Family will take care of themselves. | GIW to propose affordable accomodation around Ilupeju | GIW | 17/04/2018
Transportation | Cars should be available for outstation guests | GIW to rent cars | GIW | 28/06/2018
Logistics | The description of the venue must be well communicated. Guest staying in the hotel must be enlightened about the hotel environ and also know how to Use Uber for movement.
Logistics | The description of the venue must be well communicated. Guest staying in the hotel must be enlightened about the hotel environ and also know how to use Uber for movement. | GIW to ensure address on invitation cards is well descriptive | GIW
Measurements for success 1. Excellent quality of food and food service, prompt service from all service providers and event organiser 2. Flawless and seamless event, food and drinks should always flow 3. Guests should feel relaxed throughout the day and have fun and should be well catered for 4. Great quality of all service providers 5. Great photos and memories captured.