## Client work plan
Folake and Emmanuel's Wedding Party Work Plan | [5 empty] | Done
Ongoing
Late task/Pending
Category | Tasks | Responsibility | Deadline | Status | Comments
Event Management | Share Professional fees + Letter of Engagement with client | GIW | 6th April
| Client agrees on professional fees | Client | 12th April
| Payment of first instalment of Professional fees | Client | 30th April
| Sign the contract/Letter of engagement | Client | 7th May
| 2nd Instalment of professional fees to be paid | Client | 30th May
| Last instalment of professional fees to be paid | Client | 21st June
Catering and Beverage | Finalise dessert options with client and share scope of work with suppliers | GIW + Client | 30th April
| Finalise on drinks options and costs | GIW + Client | 12th April |  | This was done before the deadline at the sync meeting with Mrs. Funmi (Client's sister)
| Finalise on menu options with client and share with suppliers | GIW + Client | 12th April |  | This was done before the deadline at the sync meeting with Mrs. Funmi (Client's sister)
Décor | Do a walk through of the venue with the decor vendor | GIW | 25th April
| Finalise decor pieces and placement | GIW + Client | 25th April
| Client to sign off on all materials to be printed + graphic designs | GIW + Client | 30th April
Entertainment | Book DJ | Client | 16th April
| Client shares the contact of her preferred MC | Client | 16th April
Event day | Set up, dress rehearsal, event goes live and tear down | GIW + Suppliers | 29th - 30th June
Guest Experience Management | Finalise on style of hostess' outfits with client | GIW + Client | 16th April |  | This was done before the deadline at the sync meeting with Mrs. Funmi (Client's sister)
| Meet with client to finalise on seating plan using client's guest lists | GIW + Client | 22nd June
Production Meeting | Do a final run through at the production meeting | GIW + Client + Suppliers + Stake holders | 26th June
| Client sign off on final event documentation i.e. list of photo shots, event flow/cue sheet + live décor presentation | GIW + Client | 15th June
| Final dress rehearsal with technical director | GIW + MC | 20th June
Security/Parking | Meet with venue security head to plan venue security, bouncers, LASTMA, discuss logistics for drop offs and parking | GIW | 25th April
Technical | Finalise all arrangements with the technical supplier | GIW + Client + Supplier | 20th June
Venue | Technical venue recce | GIW | 25th April
| Vendors meeting at venue | GIW + Suppliers | 26th June
Archival | Retrieve client's final selection of photographer | GIW | 12th April |  | This was done before the deadline at the sync meeting with Mrs. Funmi (Client's sister)
| Share a list of photography shots with client, receive approval, then share with photographer | GIW + Client | 14th July
| Share pictures from the event | GIW | 14th July
Post Event | Post event meeting with client | GIW + Client | 6th July