## Contact Report
Meeting date: 3rd April 2018
Attendees: Phone call meeting between Ms Folake(Client) and Ronke Adeneye(GIW)
Event Date: 30th June, 2018
Event Time: 7am- 10pm
Event Venue: Akiita Hall and April Room Ilupeju
Item | Comment | Next Steps | Responsibility | Deadline | Update from meeting with Funmi(client's contact on 11/4/2018 in client's resident) | Next Steps | Responsibility | Deadline
Event look and feel | Fun and Glamourous. Guests should feel relaxed throughout the event. Client's event budget is N8million (which is subject to change) and theme is "little bit of old school ". For traditional wedding: calm, classy and Africanish | Design mood board for client to sign off | GIW | 13/4/2018 | - | *A mood board is not required as all the vendors have been communicated witrh and booked. *Communicate client's vision with vendors in charge of look and feel | GIW | 17/4/2018
Guest size | 300/400. Age range is 25-70, comprising of family, friends and colleagues. | Plan to cater for 700 guests | GIW + Client | N/A | - | - | - | -
Invitations | Paper and E-invitations will be sent to guests and handled by the GIW. It must be vetted by Client's Father before it is sent out and should be ready as soon as possible. Not strictly by invitation | *Send invitation card designs to client for approval *Client to finalize on design | GIW | 13/4/2018 | "All a bride needs" is producing and printing 200 copies. Funmi will be distributing paper copy. | *Follow-up with Funmi to ensure design and context approval from bride's father *Funmi to do an intro email email between GIW and A"All A Bride Needs" | GIW Funmi | 16/4/2018
Guest's experience | *GIW suggested a backdrop/step and repeat wall at the entrance *GIW suggested a photo-booth with polaroid cameras for guests to take pictures and print polaroids on site. GIW also suggested a guest book for kind words and photos to be placed in. *A little bit of old school themed Slomo video booth can also be considered *Hostesses were suggested to help manage guests experience during the event | *GIW to propose photo-booths and guest book to client | GIW | 13/4/2018 | *The venue space cannot accommodate a photoboth *GIW proposed photoprops and wish cards instead *Six hostesses have been engaged from Vudi Ushers to manage guest experience and their outfit will be Black dress on a silver shoe and a touch of purple | *These will be communicated to the client and decisions will be made *Funmi to do an intro email email betwteen GIW and Vudi Ushers *GIW to request for pictures of the girls and their outfits from Vudi Ushers | GIW Funmi | 17/4/2018
Décor | Candles and flowers as centre piece instead of elaborate flowers only | *Décor vendor to send décor mood board *GIW to follow up with décor vendor | 360 Events GIW | 17/4/2018 | *360 Events has been booked *Reservation cards will be printed by Funmi. | *Funmi to do an intro email email between GIW and 360 Events and send the list of the deliverables agreed | Funmi | 16/4/2018
Pyrotechnics | Smoke, fog, fire works, | *GIW to propose options of grand reception entrance *Client to give a feed back on how the entrance will look like | GIW Client | 13/4/2018 | The HSE Policy of the hall does not permit smoke in the hall. 360 Event will be making an interesting grand entrance for the couple | *360 Events to share the grand entrance option with GIW | GIW | 20/4/2018
Seating | 10 seater Banquet tables | *Confirm type of chairs and table available at the venue and share photos with client *Other options to be included in mood board *Options of seating styles should be included in mood board | GIW | 2018-11-04 | *Bride side and Groom side will be strictly adhered to. *Seating style option for the traditional has been concluded on. *GIW to propose seating style option for the reception | *Send seating style options to Funmi | GIW | 21/4/2018
Catering | Client will want us to check with her sister, Funmi and welcomes recommendation for Menu. | *GIW to liase with Funmi on number of course meal, menu options, serving style, menu cards, chargers and cutleries *Contact Adetutu for Desserts | GIW | 2018-11-04 | Hafusa will be managing the food. Menu list is ready. For traditional wedding, small chops and beverage/water will be served. | *Funmi to do an intro email email between GIW and Adetutu | Funmi | 16/4/2018
Drinks | Client would like us to check with Mr Kola on this | GIW to liase with Mr Kola on types of drinks, serving style and glasswares | GIW |  | Alcohol will be served on request, while soft drinks and water would be served generally. | - | - | -
Lighting | 360 Decor would provide a purple, black and white a bit dim lightening | Contact 360 Events to share their lighting plan | GIW | 2018-11-04 | 360 Decor is providing both lighting, fogs and fire works. Funmi's trust is on 360 event and GIW need not insist on items with them. Rather GIW should just follow up with them. | *Follow-up with 360 Events to ensure details of light are in check | GIW | N/A
Overflow | The hall for traditional wedding would serve for overflow | *Propose a guest movement plan for the overflow *Design a seating style for the overflow as well as the logistics involved | GIW | 24/04/2018 | - | - | - | -
DJ | Songs with vulgar words should not be played. A requested song to be played during father and daughter's dance (one of Client's father favorite old school song). GIW provides an easy to learn short video for choreography for Client and her sister's dance. 'Who runs the world' by Beyonce should be played. it should be mixed with the ending part of Formation'. Dj ensures it is properly mixed and sent to the Client before the day. Yoruba and Phyno songs should be playing knowing it is a mix wedding. The parents should also not be left out of the music. Every age group should be considered. | Contact Mr Kola and communicate the client's wish | GIW | 2018-11-04 | *The choreography song will be changed. Funmi would like to avoid the client from being emotional. | *Get DJ's contact from Mr Kola *Mr Kola to do an intro email email between GIW and DJ | GIW Mr Kola | 21/4/2018
MC | Mr Kola is handling this | Contact Mr Kola to get the contact of the MC | GIW | 2018-11-04 | Mr Kola is incharge of MC | *Get MC's contact from Mr Kola *Mr Kola to do an intro email email between GIW and MC | GIW Mr Kola | 21/4/2018
Surprise performance | No surprise performance or video will be done | N/A | N/A | N/A | - | - | - | -
Sound equipment | GIW should get a very good sound and equipment vendor | *Recce venue to confirm the sound items available *Get suppliers and get quotes to compare costs | GIW | 2018-11-04 | The Dj will be providing sound equipment. | *Recee venue with DJ | GIW | 2018-02-05
Cake | Client contacted Splendidsplash for the traditional and reception cake. The traditional cake should be diced and shared during reception. | Follow up with Splendidsplash to further communicate client's vision | GIW | 2018-11-04 | Follow up with Splendidsplash to further communicate client's vision | *Funmi to do an intro email email between GIW and SplendidSplash | Funmi | 16/4/2018
Photographer | Client wants photographs to be excellently captured but not too pricey and is open to suggestions based on who we've worked with. | Propose photographers and share instagram handle with client to view work | GIW | 2018-06-04 | Michael Bolaji has been hired. | *Funmi to do an intro email email between GIW and Micheal Bolaji | Funmi | 16/4/2018
Videographer | Client is open to suggestions | Share options with client to view work | GIW | 2018-06-04 | Morgan Films has been hired. He must be reminded to come along with a USB Cord that is workable with Akiita hall projector. | *Funmi to do an intro email email between GIW and Morgan Films | Funmi | 16/4/2018
Security | Security should be considered | GIW to source and book security personel for the event | GIW | 30/4/2018 | Same as previously indicated | - | - | -
Keepsakes | Client would like every adult to have a pack of keepsake. Keepsake must be durable and relevant in usage. Carrier bag | GIW to recommend and send photos of samples to client. | GIW + Client |  | GIW to provide a list of durable items within the budget of the client. | *Share options with Funmi | GIW | 18/4/2018
Accomodation | Client welcomes recommendation from GIW. Hotel must be within Ilupeju. To cater for Bride, Groom, bride's maids and groom's men and atleast 10 guests that will be travelling down. Family will take care of themselves. | GIW to propose affordable accomodation around Ilupeju | GIW | 17/04/2018 | Funmi noted that the groom will have to take care of the accommodation for his out-statationed guests because he is not giving the information she needs to book the accomodation while she will book for the bride's guests | *Follow up with Funmi to get contacts of hotel manager and follow up with the booking | GIW | 20/4/2018
Transportation | Cars should be available for outstation guests | GIW to rent cars | GIW | 28/06/2018 | Rental of Coaster bus to convey guests from Akiita hall to church and back to the reception hall. | *Source for coaster bus, confirm availability and book | GIW | 2018-02-05
Logistics | The description of the venue must be well communicated. Guest staying in the hotel must be enlightened about the hotel environ and also know how to Use Uber for movement.
Logistics | The description of the venue must be well communicated. Guest staying in the hotel must be enlightened about the hotel environ and also know how to use Uber for movement. | GIW to ensure address on invitation cards is well descriptive | GIW |  | - | - | - | -
Measurements for success 1. Excellent quality of food and food service, prompt service from all service providers and event organiser 2. Flawless and seamless event, food and drinks should always flow 3. Guests should feel relaxed throughout the day and have fun and should be well catered for 4. Great quality of all service providers 5. Great photos and memories captured. 6. All adult must be welcomed with a keepsake.

## I2E Doc
Idea to Execution Process Document (12E Doc)
DONE
Stage | Tasks | Deadline | Responsible | Status | Comments | IN PROGRESS
Engage + Initiation | [5 empty] | LATE
| Receive event brief from client. Notify BD/Do an intro email | 2018-03-30 | CLIENT
| Send/reply intro email, attaching corporate profile, website link and EDNA form. Follow up with phone call. | 2018-04-04 | BD
| Client fills the form and/or responds to the email | 2018-04-03 | Client
| Prepare list of questions based on the form responses and client brief | 2018-04-03 | CLIENT CONTACT + BD
| Schedule first meeting with client to discuss event brief and identify stakeholders. | 2018-04-03 | BD
| Prepare contact report and: Share with client, including clear next steps for both NS and client Share with team, including clear next steps for each department and/or individual | 2018-04-04 | Chinwe
| Prepare professional fees with finance, share with FVO for approval | 2017-01-16 | BD
| Obtain FVO’s feedback/sign off | 2017-01-17 | FIN + BD
| Send approved professional fees quotation to client | 2017-01-18 | FIN
| Negotiate, review quotation and identify areas for adjustment | 2017-01-24 | FIN + BD + CLIENT
| Issue invoice and contract to the client | 2017-05-15 | FIN
| Send client receipt acknowledge payment and communicate admin budget cap to TEO | 2017-05-15 | FIN
| Ops is introduced to client and officially brought into the loop | 2017-02-03 | BD
Ideation
| Schedule brainstorming with team | N/A | BD
| Draft a word/text document of the ideas generated from the team brainstorming and send to FVO within 48 hours | N/A | BD
| Obtain FVO’s feedback/sign off | 2017-01-18 | BD
| Develop word document into prezzy and share concept design with client | 2017-01-18 | BD
| Client gives feedback/signs off | 2017-01-21 | CLIENT
Implementation
| Send approved prezzy to Ops to generate a quotation | 2017-01-21 | BD
| Prepare workplan | 2017-01-26 | OPS
| Send client the workplan schedule with timelines and evaluation criteria | 2017-01-26 | BD
| Create PSD for CEO’s approval. Create M.Doc as well. | 2017-02-03 | OPS
| Request for costs from vendors, put together initial quote and share with Accounts | 2017-02-06
| Send internally approved quotation to client (3 days after) | 2017-02-07 | FIN
| Negotiate, review quotation and identify areas for adjustment | 2017-02-10 | OPS + FIN
| Issue invoice and reiterate vendor clause in the contract | 2017-03-18 | FIN
| Client pays 1st installment of supplier fees | 2017-04-11 | FIN
| Share admin budget with Accounts department | 2017-07-12 | TEO
| Give a bargaining margin and payment policy to Ops to use to negotiate with their vendors. | N/A | FIN
| Approve admin budget | 2017-07-14 | FIN
| Send a formal brief to selected suppliers and book them | 2017-02-03 | OPS
| Ideate with suppliers. Meet with them if necessary and tap into their creative minds. | 2017-02-07 | OPS
| Request for quotes from vendors. Relay payment plan with them as communicated by Accounts team. | 2017-02-07 | OPS
| Negotiate costs with vendors along with the Accounts Team. | 2017-02-07 | OPS
| Request for reviewed invoices and share with Accounts. | 5th June | OPS
| Prepare vendor schedule, get FINAL invoices from Ops and process payment | 2017-03-28 | FIN
| Ensure that deposits are made to vendors after client makes payment. | 8th June | OPS
| Actively manage vendors and receive constant progress on their work progress. Share all necessary creatives with them. | Leading up to the event | OPS
| Share weekly project progress and updates with BD to share with the client. | Leading up to the event | OPS
| Act as client liaison in sending designs, weekly updates, samples etc. for sign off. | Leading up to the event | BD
| Request list of event personnel for set up and D-Day and prepare ID (wristbands/tags/Accrediatation) | 2017-07-05 | OPS
| Conduct walkthrough/production meeting with all event stakeholders. Identify issues and solutions. | 2017-07-12 | OPS
| Ensure master document has been properly populated (nothing left out) and share production schedule with vendors. | 2017-07-14 | OPS
| Facilitate in-house production meeting. | 2017-07-14 | OPS
| Manage event team to ensure all tasks are done according to timeline and expectations. | Leading up to the event | OPS
| Venue Prep and set up begins | 2017-07-18 | OPS
Event Live!
| Ensure all vendors, suppliers, GEMs are at the venue at pre-agreed time | 2017-07-19 | OPS
| Ensure all event staff are properly accredited and that they follow NS Partner Guide. | 2017-07-19 | OPS
| Use task checklist to ensure that vendors have delivered all that was promised/agreed on. | 2017-07-19 | OPS
| Conduct final run-through and security checks. | 2017-07-19 | OPS
| EVENT LIVE! Supervise vendors during the event, manage the event flow, identify issues before they bloom and troubleshoot them. | 2017-07-19 | OPS
| Manage and ensure proper event shut down THEN sleep! #ToWhatEnd | 2017-07-19 | OPS
Closure
| Send thank you note, evaluation form and schedule post mortem meeting with client (48hrs after) | 2017-07-21 | BD
| Facilitate in-house post-event meeting to discuss event. | 2017-07-21 | OPS
| Send feedback emails/forms and/or thank you cards to vendors and suppliers. | 2017-07-21 | OPS
| Send post event meeting report to client | 2017-07-22 | BD
| Create report from internal post event meeting and share with team. | 2017-07-22 | OPS
| Send post event deliverables to the client i.e. videos/photos/drinks (depending on nature of the event) | 2017-08-04 | OPS + BD
| Process balance payments to vendors as agreed after client pays balance. | 2017-07-28 | FIN
| Ensure Accounts makes balance payments to vendors as agreed after client pays balance. | 2017-07-28 | OPS
ON TO THE NEXT ONE!

## Quotation
www.NoSurprisesEvents.com
Q U O T A T I O N
Prepared for: Mrs Ajo Balogun |  |  |  |  | Company: The Baloguns
Telephone: 07061533400 |  |  |  |  | Email: ajobalogun@gmail.com
Event name: Mr Afolabi Balogun's 50th birthday |  |  |  |  | Date: July 19, 2017
Venue: Lagos Motor Boat Club, Ikoyi |  |  |  |  | Time: 6pm
Date quote prepared: | 2017-03-14 |  |  |  | Quote valid for: 2 weeks
Item | Description |  | Unit cost (Naira) | Quantity | Total (Naira) | Deposit | Company name | Bank name | Account no | Balance
Archival | Professional Photographer (Ibukun Williams) |  | 310000 | 1 | 310000 | 77500 | Ibukun Williams | GTB | 0106323464 | 232500
Venue | Lagos Motor Boat Club, Ikoyi |  | 0 | 0 | 0 | 0 | NA | NA | NA | 0
Collateral | Design and production of reserved signs
False walls for food court + Signages
| Design and production of accreditation wristbands for vendors |  | 20500 | 1 | 20500 |  | Micheal Isaac | GTB | 0052698100 | 20500
Venue Design | Overall décor elements for the venue - tea lights centre pieces, cocktail tables,cocktail table covers, lounge sitting |  | 1060000 | 1 | 1060000 |  |  |  |  | 1060000
Catering and Drinks | Barbecue - Chicken, Ribs and Asun by Grind Grill |  | 396000 | 1 | 396000 | 99000 | Grind Company LTD | GTB | 0218510576 | 297000
| Hors d'oeuvres + Nigerian dishes- 500 by Chef Eros |  | 2103000 | 1 | 2103000 | 420300 | Eros and Gourmet LTD | Diamond | 0084760374 | 1682700
| Dinner for 250 by Chef Benedict (to be handled by client) |  | 0 | 0 | 0 |  |  |  |  | 0
| Non-alcoholic drinks and water by LMBC Bar |  | 150000 | 1 | 150000 |  |  |  |  | 150000
| Drinks - Wines, Champagne, Spirits, Special Cocktails, Mocktails- Client to handle |  | 0 | 0 | 0 |  |  |  |  | 0
| Cocktails and Mocktails by Eventi Cocktails |  | 310500 | 1 | 310500 | 52500 | Eventi Verdi Limited | GTB | 0003635123 | 258000
| Dinner (Ofada, Swallow, Jollof rice) for 450 by TYKS + Driver's food for 150 |  | 699000 | 1 | 699000 |  |  |  |  | 699000
| Dessert by Salt Lagos |  | 550000 | 1 | 550000 |  |  |  |  | 550000
Rentals | Matrix Chairs, Lounge seaters |  | 322500 | 1 | 322500 | 176875 |  |  |  | 145625
| Tents |  | 240000 | 1 | 240000 |  |  |  |  | 240000
Rectangular tables
Guest Experience | Confetti blast |  | 80000 | 2 | 160000 |  |  |  |  | 160000
| Guest Experience Managers + Outfit - to be handled by client | [8 empty] | 0
| Wish Wall |  | 170000 | 1 | 170000 |  |  |  |  | 170000
Entertainment | KSA (to be handled by client) |  | 0 | 0 | 0 |  |  |  |  | 0
| DJ Wayne |  | 150000 | 1 | 150000 |  |  |  |  | 150000
Technical | Stage by Dejour (to be handled by client) |  | 0 | 0 | 0 |  |  |  |  | 0
| Ambient lighting + Stage light + Lighting design by Dejour (to be handled by client) |  | 0 | 0 | 0 |  |  |  |  | 0
| Screens for live feed and looping of AV content by Dejour (to be handled by client) |  | 0 | 0 | 0 |  |  |  |  | 0
| Crisp and clear sound system by Dejour (to be handled by client) |  | 0 | 0 | 0 |  |  |  |  | 0
| Power by LMBC |  | 0 | 0 | 0 |  |  |  |  | 0
Security + Parking | Parking attendants (to be handled by the client) | [8 empty] | 0
| Bouncers | [8 empty] | 0
| LASTMA (to be handled by the client) |  | 0 | 0 | 0 |  |  |  |  | 0
| Mobile and Marine Police (to be handled by the client) |  | 0 | 0 | 0 |  |  |  |  | 0
Keepsakes | Design and Production of tote bags, branded mugs and teabags, candles, drawer liners and portable umbrellas (to be handled by the client) |  | 0 | 0 | 0 |  |  |  |  | 0
Event Management Fees | Event management plus VAT |  | 1611225 | 1 | 1611225 | 1611225 |  |  |  | 0
Grand Total |  |  |  |  | 8252725 |  |  |  |  | 8252725
Prepared by: |  | Job title: | Event Operations
Telephone: |  | Email:
Optional Costs
Catering | Birthday Cake from Chef Eros
Cake to share to guests
Centre Pieces | Local lamps tinted matte black
Venue design

## Client Work Plan
Done
Ongoing
Late task/Pending
Category | Tasks | Responsibility | Deadline | Status | Comments
Event Management | Share Mood board + Professional fees + Letter of Engagement with client | NS | 19th Jan |  | These were all shared before the due date
| Client signs off on ideas and agrees on professional fees | Client | 30th Jan |  | Client approved the ideas but has made some changes to decor and doesn't want some elements. Professional fees have received sign off and have been paid
| Payment of first instalment of Professional fees | Client | 30th Jan |  | First instalment paid
| Sign the contract/Letter of engagement | Client | 7th Feb |  | This has been signed and signed copies have been returned to us
| Agree on suppliers quote and payment instalments | NS + Client | 8th Feb |  | Additional costs are being considered
| 2nd Instalment of professional fees to be paid | Client | 11th April |  | Paid in full and on time
| Last instalment of professional fees to be paid | Client | 8th June |  | Paid in full and on time
Catering and Beverage | Finalise dessert options with client and share scope of work (SoW) with suppliers | NS + Client | 5th April |  | Client and NS have agreed on options and cost
| Finalise on drinks options and costs | NS + Client | 26th April |  | Client and NS have agreed on options and cost
| Finalise on menu options with client and share with suppliers | NS + Client | 5th April |  | Client has approved catering options and they have been communicated with suppliers
| Finalise the costs for food | NS + Client | 26th April |  | All costs for food have been finalized
Décor | Do a walk through of the venue with the decor vendor | NS | 12th July |  | Walkthrough has been conducted
| Finalise decor pieces and placement | NS + Client | 12th July |  | Client has approved and finalized on decor pieces and placement
| Client to sign off on all materials to be printed + graphic designs | NS + Client | 14th July |  | NS to share all graphic design options and get client sign off
Entertainment | Book DJ Wayne | NS | 5th April |  | He has been booked and will be paid by July 14
| Client shares the contact of her preferred MC | Client | 26th April |  | Mrs Habiba Balogun is the MC
| Finalise on artistes booking | NS + Client | 11th April |  | KSA has been booked and payment made
Event day | Set up, dress rehearsal, event goes live and tear down | NS + Suppliers | 18th - 19th July |  | Set-up to commence on Tuesday 18th, dress rehearsal and event goes live on the 19th and tear down and complete venue clean-up on the 19th.
Guest Experience Management | Finalise on style of hostess' outfits with client | NS + Client | 8th June |  | Client to confirm her bringing her own hostesses, outfit options and get a preference from client.
| Meet with client to finalise on seating plan using client's guest lists | NS + Client | 12th July |  | NS to work with client on guest list and assign seating plan
Production Meeting | Do a final run through at the production meeting | NS + Client + Suppliers + Stake holders | 12th July |  | Production meeting with client, NS and all suppliers.
| Client sign off on final event documentation i.e. list of photo shots, event flow/cue sheet + live décor presentation | Client + NS | 14th July |  | - Decorator has arranged a live presentation of table setting for client's approval. - Client to approve shots list for photography - Client to approve favorite artists and songs for the DJ, NS to draw up DJ's playlist
| Final dress rehearsal with technical director | MC + NS | 18th July |  | Dress rehearsal with MC
Security/Parking | Meet with CSO to plan marine security, bouncers, LASTMA, discuss logistics for drop offs and parking | NS | 18th July |  | To ensure a flawless experience with parking, drop off and security for guests, a meeting with client's CSO to sync plans is inevitable.
Technical | Share suppliers quote with client | NS | 7th Feb |  | An estimate was drawn and shared with client on February 7. Supplementary budgets were shared and approved.
| Finalise all arrangements with the technical supplier | NS + Client + Supplier | 12th July |  | All arrangements have been discussed with Dejour
| Payment of suppliers' quote | Client | 8th June |  | Payment has been made
Venue | Technical venue recce | NS | 15th March |  | NS co-ordinated this process
| Share draft floor plan with client | NS | 13th July |  | This will be shared with the client on July 13 following changes to seating plan.
| Sign off on final floor plan | Client + NS | 14th July |  | The final floor plan to be signed off by client after implementing all tweaks
Archival | Share portfolios of photographers with client | NS | 8th June |  | This has been done
| Retrieve client's final selection of photographer, book supplier and share a list of photography shots | Client | 14th July |  | Awaiting client's final selection
| Share pictures from the event | NS | 26th July |  | Pictures of event to be shared with client.
Post Event | Post event meeting with client | Client + NS | 21st July |  | A meeting with client and NS to evaluate event and get feedback on NS performance and achievement of client's KPI

## Team Task Allocation
Team member name | Assignment/Role | Description | Update by team member in charge | Next steps | Issues
Chinwe | Floor management and team assignment+ Stakeholder management + Photography | - Coordination of all activities on the floor and ensuring the event runs smoothly in line with client's expectations - Manages the client's expectations before and during the event, ensures the client and all guests are well catered for - Coordination of event photographers. Create and share list of shots. - Ensure collection of pictures after the event on the due date. - Ensures accreditation of Ibukun Williams Crew | - Supplier communication emails have been sent to Chef Eros, Chef Benedict, TYKS, Dejour Mr Olu, DJ Wayne, Naphtali, Tent Events, Taiwo Ruby Creations, Eventi Cocktails, Grind Grill, SALT Lagos, Ibukun Williams - Ibukun Williams is coming with a 3-man team at 12pm. - Shared a list of shots with the photographer | - Map out the floor management with hostesses and team to manage guests experience and mitigate issues with negative feedback from guests - Ensure all team members are owning their tasks, and ensure all issues are sorted promptly - Ensure the photographer and team report and sort out a space for their equipment
Ayoola | Décor/Printing/Branding | - Coordination of decor supplier + proper placement of all agreed decor elements - Ensures accreditation of all decor suppliers - Ensures all printing and branding materials are printed and placed on time - Ensures a constant flow of non-alcoholic drinks and water from the LMBC Bar all night long - Ensures accreditation of all rental and drinks suppliers
Juliana | Venue readiness + Green room management | - Ensure the venue is ready for the event and the arrangement is as shown in the floor plan, all rentals and venue cleaning at all times - Ensures all rentals arrive the venue and are properly positioned and on time (Tents, False walls, Furniture. Signages design, printing and placement) - Ensures accreditation all rental crew members - Coordinate set up for the greenroom and hospitality (drinks and food etc.) for KSA and team - Ensures accreditation of DJ's crew and KSA's band crew members
Seun | Technical/Event flow/Cue sheet | - Works with Mr DuJour to ensure all technical requirements of the event are provided e.g screen, lights, stage, audio-visual and sound. - Ensures DJ's and KSA 's performances are seamless - Ensures accreditation of all technical suppliers
Debbie A | Guest experience/hostesses Photography | - In charge of overall Guest Experience and ensuring all guests are well catered for + Guest management - In charge of Guest Experience Managers, Briefing and coordination of GEMs and ensuring they deliver seamless guest experience management - Ensures seamless coordination of keepsakes distribution in line with client' wishes - Coordination of event photographers. Create and share list of shots. - Ensure collection of pictures after the event on the due date. - Ensures accreditation of Ibukun Williams Crew | List of shots have been shared with Mr Ibukun and the Pre-accreditation email sent by Ms.Chinwe. Mr Ibukun has replied and supplied the number of crew for setup and the event. He also made a few requests the enable him work effectively | I have requested the needed table and chairs on the basecamp checklist for his setup.
Lanre | Catering: Chef Eros + TYKS + Chef Benedict | - Coordinates Chef Eros and TYKS and ensures their catering requirments for the events are provided. - Ensures accreditation of all Chef Eros, Chef Benedict and TYKS crew - Coordinates Chef Benedict and SALT Lagos and ensures their catering requirements for the event are provided. | Supplier meeting was carried out Thursday, Cateres have been briefed on the requirements for this event. | communicate and follow up with rentals for tables needed. Communicate and get ready no of accreditation tags for each supplier and staff for live event.Print Tags for the orderly distribution of drivers food at live event.
Felicia | Catering: Grind Grill + SALT + LMBC Restaurant + Cake | - Coordinates Grind Grill, SALT Lagos, LMBC Restaurant and Cake and ensures their catering requirements for the event are provided. - Ensures accreditation of all Grind Grill, SALT, LMBC Restaurant and cake crew | Supplier meeting was carried out on Thursday, Cateres have been briefed on the requirements for this event. | Keep up Communication and follow up with the vendors, make sure that the requirements for vendors setup is
Umi | Team Hospitality/Admin/Basecamp | - Ensure all team members are well catered for during the event - Ensures all wristbands are ready before the event - Ensures all office supplies required for the event are ready and out of the office as at when required - Ensures basecamp is fully setup and all team members have access to required resources and on time
Wale | Drinks management | - Coordinate setup and distribution of all drinks - Eventi cocktails, non-alcoholic drinks from LMBC bar and alcoholic drinks and ensure quality assurance for drinks and ensuring all drinks keep flowing all night long. - Ensures proper coordination of Eventi Cocktails and ensures all cocktails and mocktails are served when guests arrive and during the event - Ensures accreditation of all drinks crew
Abolore | Finance + Drinks + Security + Parking | - Approve all expenses without over shooting the budget, ensure fast payment to vendors - Coordinate setup and distribution of all drinks - Eventi cocktails, non-alcoholic drinks from LMBC bar and alcoholic drinks and ensure quality assurance for drinks and ensuring all drinks keep flowing all night long. - Ensures proper coordination of Eventi Cocktails and ensures all cocktails and mocktails are served when guests arrive and during the event - Ensuring all security personnel and security equipment are parking is seamlessly done - Ensures accreditation of all drinks, security and parking crew

## Suppliers Contact Sheet + Accre
Supplier contact sheet + Accreditation
Name of Company | Service | Category | Contact person | Position/Role | Cell phone number | Email Address | Total number of team member expected on site | Number for set up | Number for live event | Agreed time of arrival on site | Actual arrival time | Signature
Lagos Motor Boat Club (LMBC) | To ensure that the hall meets Client's needs | Venue | Mr Segun | Manager, LMBC | 8034662601 |  | NA | NA | NA | NA | NA | NA
Dejour | To ensure all technical requirements (stage, sound, lights) | Technical | Mr Olu | Technical Director | 8033070747 | o3olowookere@yahoo.com
Effectiveness Consult | To co-ordinate and execute the programme on the event flow | Entertainment | Mrs Habiba Balogun | MC | 8034462408 | effectiveness@hbalogunconsult.com
DJ Wayne | To entertain guests | Entertainment | Mr Olu | DJ | 8188158578 | seunfagbemi94@hotmail.com
KSA | To entertain guests | Entertainment | Mr Olu | Entertainer | 8033070747 | o3olowookere@yahoo.com
Eventi Cocktails | To provide cocktails and mocktails for 250 guests | Beverages | Ms Lara | Welcome drinks, dinner drinks | 8038804264 | lararawa@yahoo.co.uk | 9 | 4 | 5 | 2.00pm
Eros & Gourmet | To provide hors d'oeuvres and dinner for 500 guests | Catering | Chef Eros | Dinner | 8188111160 | cheferos@iamcookiejar.net | 31 | 16 | 15 | 2.00pm
Chef Benedict | To provide dinner for 250 guests | Catering | Chef Benedict | Dinner | 8184484168 | benedictokuzu@gmail.com |  |  |  | 2.00pm
TYKS Catering | To provide Ofada rice, Jollof rice and swallow for 350 guests and driver's foodpacks for 150 | Catering | Ms Okunowo | Dinner | 8033539224 | tykscaterers@yahoo.com |  |  |  | 2.00pm
Grindgrill | To provide barbeque for 350 guests | Catering | Francis | Post-dinner | 8025015336 | grindconcepts@gmail.com | 12 | 6 | 6 | 2.00pm
Salt Lagos | To provide dessert for 500 guests | Catering | Ms Dupe | Dessert | 8097423996 | saltlagos@gmail.com | 14 | 8 | 6 | 2.00pm
Ruby Creations | To provide adire draping, centerpieces (fish bowls, tea light candles, seashells, lamps), Adire runners, cocktail tables, table covers for cocktail tables and rectangular tables, paper lanterns | Decoration | Taiwo | Decor | 8055515582 | rubycreations@gmail.com | 8 | 6 | 2 | 8.00am
Ibukun Williams | To deliver quality pictures | Archival | Ibukun Williams | Photographer | 8067712512 | Ibukunwilliams@aim.com | 4 | 0 | 4 | 12:00pm
Innovate Media | To provide confetti blast during KSA's + Celebrants performance | Rentals | Oshidi Kayode | Props | 8075288686 |  | 4 | 2 | 2 | 12.00am
Tent Events | To provide tents for the guests and suppliers and rectangular tables | Rentals | Tayo | Rentals | 8058028689 | info@tenteventonline.com |  | 5
Naphtali Rental | To provide matrix chairs and Lounge furniture | Rentals | Nicholas | Rentals | 7066076497 | info@naphtalirentals.com | 6 | 4 | 2 | 7.00am
No Surprises Events | To deliver a world class production | Event Agency | Chinwe Onuzo | Project Manager | 8162908378 | chinwe@nosurprisesevents.com

## Signage planner + Printing brea
Directional/Event info signage Breakdown
Location | Text for Signage | Signage style | Dimension
By The Main Gate | Drop Off Only For Non-Club Members | Match box
Restroom | This Way to The Restroom | Easel Stand
Welcome | Welcome to Afolabi's 50th | Match box
Printing breakdown
Item | Content/Text | Quantity | Dimension
Reserve Place Card | RESERVED | 10 | Tent Card

## Event flow
MR BALOGUN'S 50TH BIRTHDAY CELEBRATION - EVENT FLOW
Event name: Mr Balogun's 50th Birthday
Event date: 19th July, 2017
Set up time: 7.00am
Sound check time: 2.00pm
Event time: 7.00pm
Event | Time | Duration | Cue | Comments
DJ plays background music ahead of guests arrival | 6.45pm | On Going | Hostesses to receive guests Eros and TYKS on standby. Cocktail drinks on standby Cue Photographer
Guests arrive and are welcomed by drummers and background music from the DJ | 7.00pm | 1 hour
Guests mingle, are served hors d'oeuvres and welcome drinks and take photographs | 7.00pm | 45 minutes | Cue MC to be on standby to welcome guests.
MC welcomes guests | 7.45pm | 5 minutes | DJ on standby
More music from DJ | 7.50pm | 2 hours | Cue TYKS Cue Cocktail
TYKS serves guests swallow, Ofada and Jollof rice, more cocktails and drinks are served | 8.00pm | 30mins | Cue Dare, Derin and Aziza for speeches
Speeches by Mr Balogun's sons Dare, Derin and Aziza | 8.30pm | 15 minutes | Cue Mrs Balogun Cue KSA Cue confetti blast
Speech by mother of the celebrant, Mrs Balogun, a toast to the celebrant and confetti blast goes off, as KSA kicks off performance | 8.45pm | 15 minutes | Cue KSA for special birthday song performance
KSA performs | 9.00pm | Ongoing for ~2.5hrs | Cue Benedict
Chef Benedict begins serving guests, accompanied by drinks | 9.00pm | 30 mins | Cue Dessert
Dessert is served | 9.30pm | 30 minutes | Cue Barbeque, waiters with alcohol, cake
Barbeque is served alongside alcoholic beverages and cake | 10.00pm | 30 minutes | Cue DJ
DJ takes over after KSA for the after party | 11.30pm | 1.5 hours

## Cue sheet
Event name: Mr Balogun's 50th Birthday
Event date: 19th July, 2017
Set up time: 7.00am
Sound check time: 4.00pm
Event time: 7.00pm
Activity | Time | Duration | Location | Music | Cue | Responsibility
Final sound checks | 4.00pm - 6:00pm | 2hrs | LMBC Terrace | N/A |  | NS/ Du Jour
DJ plays background music ahead of guests arrival. Talking drummers begin playing at the entrance | 6.45pm - 7:45pm (DJ) | On Going | LMBC Terrace |  | Cue Cocktails from Eventi, champagne and wine from Mr Uche and hor d'oeuvres from LMBC | NS/LMBC
Guests arrive, are served hors d'oeuvres, engage at the wish wall and welcome drinks and take photographs. Once guests are seated, Chef Eros starts serving | 7.00pm - | 45 minutes | LMBC Reception area |  | Cue Chef Eros | NS/LMBC
MC welcomes guests TYKS serves guests swallow, Ofada and Jollof rice, more cocktails and drinks are served | 7.45pm - 7:50pm | 5 minutes | LMBC Terrace | N/A | Cue Eros and Cru Classe (drinks) | NS/MC/TYKS/UCHE/EVENTI
More music from DJ | 7:50pm - 8:30pm | 2 hours | LMBC Terrace | DJ |  | NS/ Eros
Speeches by Mr Balogun's sons Dare, Derin and Aziza | 8.30pm - 8:45pm | 15 minutes | LMBC Terrace | DJ | Cue Innovate Media. Cue KSA | NS/ DJ
Speech by mother of the celebrant, Mrs Balogun, a toast to the celebrant and confetti blast goes off, as KSA kicks off performance | 8.45pm - 9:00pm | 15 minutes | LMBC Terrace | DJ | Cue Children and friends for speech Cue Chef Benedict | NS/TYKS
KSA performs "special birthday song" and Mr Balogun and family dance and performance continues | 9.00pm - 11.30pm | Ongoing for 2.5hrs | LMBC Terrace | N/A | Cue Chef Benedict | NS
Chef Benedict begins serving guests, accompanied by drinks | 9.00pm - 9:30pm | 30 mins | LMBC Terrace | DJ | Cue Salt LAgos Cue KSA | NS
Dessert is served alongside alcoholic beverages | 9.30pm - 10:00pm | 30 minutes | LMBC Terrace | KSA | Cue Salt Lagos Cue Grind Grill | NS
DJ takes over after KSA for the after party | 11.30pm - 1:00am | 1.5 hours | LMBC Terrace | KSA | Cue Grind Grill, Uche and Felicia for cake | NS
Barbeque is served alongside alcoholic beverages and cake | 11.30pm -1:00am | 1.5 hours | LMBC Terrace | KSA |  | Ns

## Venue readiness checklist
Venue readiness checklist
Location | Activity | Requirements | Props/Décor | Personnel | Company responsible
Car park/Entrance area | Drop offs Car parking | Parking Signage | Matchbox signage Umbrella | LASTMA Police Umbrella Boys
LMBC Car Park | Parking for Club Members | LMBC Security Personel | N/A | 2 Security
Entrance to the Club | Welcoming of guests | 2 Owambe Talking Drummers Welcome signage | Welcome signage in match box | 2 drummers
Club Reception | Welcoming of guests Dispatching of Keep sakes (towards the end of the event) | 1 table (to place keepsakes) Wish wall 2 hostesses | Wish wall Restroom Signage | 4 hostesses |  | tablw
Club Terrace | Birthday celebration | 3 bars Lounge seats Tables and Matrix chairs Tents | Welcome backdrop Table linen Skirting | 6 hostesses
Restaurant (Upstairs) | Greenroom | Lounge seats Single seats Center table Drinks Finger foods | Table clothes Flora Centerpiece

## Production Schedule
| PRODUCTION SCHEDULE | [5 empty] | STATUS
Completed task
TEAM MEMBER | ROLE/FOCUS | TASK | DATE | TIME | COMMENTS | STATUS |  | Ongoing task
Ayoola | Technical | Ensure deposits are paid to Dejour | 2017-06-14 | 12:00
|  | Supervise technical setups and dry runs | 2017-07-19 | 12:00
|  | Ensure all audio visual, lighting and sound equipments have been completely set up and are performing optimally | 2017-07-19 | 11:00
|  | Conduct sound check for KSA | 2017-07-19 | 12:00
|  | Ensure DJ is set up and ready for the event | 2017-07-19 | 13:00
|  | Request technical requirements from all performing acts and confirm their call times. | 2017-07-19 | 8:00
|  | Ensure artistes and DJ are properly cued. | 2017-07-19 | Continous
|  | Ensure that Green room is well setup. | 2017-07-19 | 12:00
|  | Prepare and share ROCS and Event Flow | 2017-07-05 | 14:00
|  | Manage Event Flow and ensure the event goes seamlessly. | 2017-07-19 | Continous
Chinwe/Ayoola | Venue design and Décor | Brief decor supplier, negotiate in line with the client's budget, get their quotes and finalize payment plans with accounts | 31st Jan | 10:00
|  | Finalize decor plan and run it by the client, including any issues/concerns/recommendations | 7th March | 16:00 | Client is still making adjustments in the decor plan
|  | Ensure deposits are paid to the supplier | 11th April | 10:00
|  | Ensure that decor setup for the venue is completed on time | 2017-07-19 | 12:00
|  | Ensure the delivery o f all decir elements (lanterns, tea lights, adire fabrics) and ensure they are positioned appropriately | 2017-07-19 | 8:00
|  | Facilitate teardown and ensure all decor materials are intact and removed from site and return all client's property | 2017-07-20 | 12:00
Ayoola | Printing+Security | Brief vendors and negotiate in line with client's budget, get their quotes and finalize payment plans with accounts | 2017-01-31 | 13:00
|  | Share printing designs with the client for sign off | 2017-07-07 | 15:00
|  | Ensure all printing deliverables are received at the right time and is appropriately done | 2017-07-14 | 12:00
|  | Ensure deposits are paid to the suppliers | 2017-04-11 | 12:00
|  | Ensure security arrive the venue at the right time for setup. | 2017-07-19 | 8:00
|  | Ensure security arrive the venue at the right time | 2017-07-19 | 14:00
Chinwe/Juliana | Guest Experience Management | Ensure GEMs have been briefed on roles, call time and dress code. | 2017-06-20 | 10:00
|  | Ensure all hostess do a fitting for their outfits | 2017-06-28 | 10:00
|  | Do a walk-through with the hostess at the venue | 2017-07-19 | 14:00
|  | Set up post-it-note ahead of guests arrival | 2017-07-19 | 15:00
|  | Supervise and ensure all hostesses are at their post and are catering appropriately to the guest | 2017-07-19 | Continous
Abolore/Umi | Admin | Identify all administrative needs for the event including on-site office equipment | 2017-07-06 | 9:00
|  | Ensure all office equipment are transported to the site from the office | 2017-07-19 | 6:00
|  | Ensure all office equipment are transported back to the office from the site | 2017-07-20 | 12:00
|  | Draw up budgetary needs for the team's welfare all through event setup and event day | 2017-07-12 | 10:00
|  | Ensure cash needed for team welfare, accommodation and other logistics are obtained from Accounts on time | 2017-07-17 | 10:00
|  | Book for pay for accommodation for the team. | 2017-07-17 | 12:00
|  | Ensure that each vendor and crew sends the list of their team members for accreditation | 2017-07-03 | 9:00
|  | Facilitate accreditation of suppliers on setup day | 2017-07-19 | 8:00
|  | Ensure accreditation of crew and suppliers is done on time on event day | 2017-07-19 | 8:00
Abolore | Finance planning, management and procurement | Ensure all quotes are received on time and negotiations are done properly. | 2017-06-01 | 10:00
|  | Review admin budget and share with FVO for approval. | 2017-07-15 | 14:00
|  | Raise cheques/cash for all admin needs in line with budget and approval | 2017-07-18 | 14:00
|  | Manage budgetary requirements and financial plan for the project | 2017-05-12 | Continous
Ayoola | Rental | Brief vendor on requirements for canopies, chairs and tables pricing, delivery and setup schedule | 2017-05-15 | 15:00
|  | Manage vendor and ensure all items quoted and requested for are delivered | 2017-07-19 | 8:00
|  | Supervise tear down of tents, power equipment and all rentals and that all materials are returned to the suppliers | 2017-07-20 | 12:00
Lanre/Felicia/Umi/Wale | Catering and Beverages | Brief all catering suppliers about the needs of the event | 2017-01-31 | 10:00
|  | Brief all drinks suppliers for the event | 2017-01-31 | 10:00
|  | Request menu for catering suppliers | 2017-02-03 | 12:00
|  | Set up and supervise food tasting for the client | 2017-02-24 | 10:00
|  | Ensure deposits are paid to the catering and beverages supplier | 2017-04-11 | 11:00
|  | Ensure set up time is communiacated to all suppliers | 2017-02-10 | 13:00
|  | Ensure catering and beverages set up for the event is completed | 2017-07-19 | 15:00
|  | Ensure that all waiters are wearing the agreed outfits and color for the event | 2017-07-19 | 15:00
Debbie | Videography+Photography | Brief Photographers and videographers about the requirements for th event | 2017-01-31 | 11:00
|  | Ensure deposits are made to the selected photographer and videographer | 2017-04-11 | 12:00
|  | Share list of shots with photographer | 2017-07-14 | 11:00
|  | Communicate event set up time to suplliers | 2017-02-10 | 11:00
|  | Ensure photography and videography set up is completed | 2017-07-19 | 15:00
|  | Supervise photographer and ensure all important moments of the event are captured | 2017-07-19 | Continous

## List of Hostesses
Name | Number | Account details | Contacted and confirmed via What's app | early
Princess Odoffin | 08023558358 |  | Confirmed | not late
Irene | 08030513313 | Irene Ezemalu - 1961064022, Eco Bank | Confirmed | late
Confidence | 08166917318 | Confidence Imerhion - 0125769267, GTB | Confirmed
Bamidele | 08062857821 |  | Confirmed
Habibat | 07016764060 |  | Confirmed
Peculiar | 07062565102 | Peculiar Imerhion - 2208480046, Zenith bank | Confirmed
Ayo Adesanwo | 8035909166 | Esther Adesanwo - 0007440385, GTB | Confirmed
Mofiyinfoluwa Ogidon | 08168950545, 08124136177 | Mofiyinfoluwa Ogidon - 0213701467 | Confirmed
Jennifer Okorie | 08156559105, 08029829878 | Jennifer chigozie Okorie - 0229835928, wema bank | Confirmed
Nana Peters | 08064344425, 08090759589 |  | Confirmed
Joy Oikeh | 8130466707 |  | Confirmed
Mary Asuquo | 09051114481, 08120125873 | Mary Asuquo - 0141044184, GTB | Confirmed
Remi Dasho | 8125568030 |  | Confirmed
Matilda jerry | 8097167157 |  | Confirmed
Sarah Jatto | 7068331700 |  | Confirmed
Lisa nwokolo | 8146594792 |  | Confirmed
Ovie emmies | 8106752713 |  | Confirmed
ijeoma | 08128913978 |  | Confirmed
tomi | 08103195245 |  | Confirmed
Christopher onyinye | 08103195246 |  | Confirmed
Ada Azubuko | 8101920250 |  | Confirmed

## AdminBasecamp Checklist
Basecamp request sheet
Event name: | Mr Afolabi Balogun's 50th birthday
Event date: | Monday 19th, July 2017
Project Manager: | Chinwe Onuzo
Basecamp location: | Lagos Motor Boat Club, Ikoyi
Event time: | 6pm till 2am
Item | Quantity | Requester | Comment
TV SCREENS & STANDS | -
PRINTER | 1
A4 PAPER | 1 rim
STAPLER & STAPLE PIN | 1 stapler & pins
CREW TAGS | 20
EXTENSION CABLE/CABLE REELS | 3 extensions cables & 2 cable reels
CLIPBOARDS | 3
INTERNET | smile
SCISSORS | 1
VENDORS WRISTBAND
PENS | 10
MARKERS | 6 | Julianah | Different colours of markers please
HOSTESS NAME TAG JACKETS | 6
TABLE NUMBER | -
RESERVED SIGNS | 10
CELLOTAPE | 1
TABLE NUMBER STANDS | -
LETTER LABELS | The pack
COCKTAIL TABLES/CHAIRS | 1 Table and 4 chairs | Deborah A | Regular tables are fine
CUE BREAKERS | -
TABLE COVERS | 5 | lanre | preferably white
FIRST AID BOX | 1
EXTRA WALKIE TALKIES | 5
Umbrellas | 5
Kettle | 1
White board Stand | 1
Tea cups and saucers | 5 | Julianah
serviette and tothpicks | 15 packs & 6 packs respectively | lanre
Drivers food voucher | 150 | lanre

## List of photography shots
LIST OF SHOTS - MR BALOGUN'S 50TH BIRTHDAY PARTY
Aspects to capture should include but are not limited to:
Capture event set up (Tuesday 18th July 2017 and morning of Wednesday, 19th July 2017).
0
The tent while being set up, without the table and chairs arrangement.
The tent being set up, with table and chairs arrangement.
The club without any arrangement.
The club with all décor/technical arrangement in place, lights inclusive on the event day before event goes live.
The NS crew during set-up.
Photo of all hostesses dressed up.
Photo of each group of hostesses positioned at their different areas.
Shot of NS crew together, before the event goes live.
Shot of the venue without guests (aerial or panorama).
All security in position (LASTMA, KSquare, Police/MOPOL/ Marine Security).
Check-in area, capture...
Guests during check-in process.
Hostesses during check-in process.
Guest list verification.
Photos of arriving guests.
Up close photos of a hostess attending to/receiving a guest.
Signage wall before messgaes
Guests interacting with and around the wish wall
Wish wall after messgaes
Mr Afolabi Balogun with family
Mr Afolabi with Friends
Mr Afolabi Balogun in conversation with guests
Artistes
Capture KSA in the green room.
Capture KSA as they get on stage.
Capture KSA while performing special birthday song during confetti blast
Capture the MC getting on stage.
Event space: boat club
A potrait of Mr Afolabi Balogun against a remarkable background
A potrait of Mr & Mrs Afolabi Balogun
A portrait of Mr Afolabi Balogun's core family
A shot of the full venue with guests mingling around.
A shot of the stage, with no one on it.
A shot of the dancefloor, with no one on it.
Capture the front of the venue bulding
Shot of the venue space against the water
Guest as they move around the venue
Guests sitting in the venue
Waiters/Servers smartly positioned on standby to attend to guests.
Waiters serving guests food
Servers by the bar serving guests drinks.
Waiters offering guests drinks
Band as they perform and serenade the guests.
Guests as they move to the barge/marquee.
Guests’ expressions as the artistes perform.
Guests, as they meet and greet.
Guests with the celebrant.
Guests with the family of the celebrant.
Full shot of the guests at dinner.
MC as he ushers KSA on stage
Guests during the different meal courses.
The cake positioned.
The celebrant with the cake.
Cutting of the cake.
Celebrant and family/friends with the cake.
Shot of guests in focus.
Confetti as it is blasted
L. After Party
Picture of the DJ performing
The guests dancing on the dancefloor
Pictures of several guests in motion and having fun
The guests and DJ in the same frame
M. Food
Capture the different dishes and the chefs at work

## Team hospitality
HOSPITALITY SCHEDULE, EVENT DAY, WEDNESDAY, 19TH JULY 2017
CALL TIME | 7.00am
ONSITE OFFICE/BASE CAMP | LMBC (Restaurant Upstairs)
| TIME | BATCH 1 | BATCH 2
MEAL 1 (20 minutes) | 11:00 | Chinwe Umi Abolore Wale Seun | Blessing Ayo Felicia Julianna Lanre Debbie
MEAL2 (20 minutes) | 15:00 | Blessing Ayo Felicia Lanre Juliana Seun | Debbie Chinwe Umi Abolore Wale
CHANGING SHIFTS (30 minutes | 16:00 | Felicia Chinwe Blessing Seun Abolore Juliana | Debbie Ayo Wale Umi Lanre
ACCOMMODATION PLAN
TEAR DOWN/GO HOME: | Thursday, 20th July, 2017

## Post mor report
Event Post-mortem report
Event name: Mr BAlogun's 50th Birthday Celebration
Event date: 19th July, 2017
BD member on project: Chinwe Onuzo
Ops member on project: Kuku Ayoola
Project Overview
Original project goals and objectives
Original project success criterion?
How did the project end?
Key accomplishments
What went right/worked well?
What was found to be particularly useful?
Project highlights
Key problem areas
What went wrong?
What project processes didn’t work well?
What specific processes caused problems?
What were the effects of key problems areas (i.e. on budget, schedule, etc.)?
Technical challenges
Post Project Tasks/Future Considerations
Ongoing development and maintenance considerations
What actions have yet to be completed and who is responsible for them?
Is there anything still outstanding or that will take time to realize?
Lessons Learned:
Category | Description | Achieved? | Comments
Project Planning | Concept was appropriate to Business Objectives | Yes
| Project Plan and Schedule were well-documented, with appropriate structure and detail | No
| Project Schedule encompassed all aspects of the project | N/A
Task were assigned to team members promptly
Tasks were defined adequately
Stakeholders had easy access to Project Plan and Schedule
Stakeholders (e.g., Sponsor, Client) had appropriate input into the project planning process
Vendors were properly briefed and briefs were detailed and well documented
Vendor deliverables were gathered to sufficient detail
Vendor deliverables were documented clearly
External dependencies were identified, agreements signed
Project budget was well defined
End of Phase Criteria were clear for all project phases
Project Plan had buy-in from the stakeholders
Project Execution | Project stuck to its original goals
Proposed ideas were well executed
Changes in direction that did occur were of manageable frequency and magnitude
Project baselines (Scope, Time, Cost, Quality, Payment Plan) were well-managed (e.g., changed through a formal Change Control Process)
The payment plan communicated to vendors was adhered to
Basic project management processes (e.g., Risk Management, Issue Management) were adequate
Project tracked progress against baselines and reported accurate status
Procurement (e.g., RFP, Contract with vendor) went smoothly
Contracted vendor provided acceptable deliverables of appropriate quality, on time, and within budget
Stakeholders were satisfied with the information they received
The project had adequate Quality Control
Requirements – specifications – Test Plan were well-managed (e.g., Requirements Management System was used)
Human Factors | Project Manager reported to the appropriate part of the organization
Project Manager was effective (e.g managed the timelines well and showed leadership in delegating, following up and following through with tasks
Project Team was properly organized and staffed
Project Manager and team received adequate briefing
Project Team’s talent and experience were adequate
Project team worked effectively on project goals
Project team worked effectively with outside entities e.g suppliers
Project team worked with little or no supervision
There was good communication within the Project Team (communication was clear and well understood)
Resources were not over-committed
Resources were consistently committed to project aims
Conflicting departmental goals did not cause problems
Authority and accountability were well defined and public
Overall | Initial cost and schedule estimates were accurate
Project was delivered within amended schedule
Project was delivered within amended budget
Overall Change Control/management was effective
External dependencies were understood and well-managed
Technology chosen was appropriate
The project was a technological success
Client’s needs/requirements were met
Client was satisfied with the outcome
Project Objectives were met
Business Objectives were met
Team Welfare/Operations/Finance | Admin budget was prepared 2 weeks to the event
The admin budget was signed off on at least 1 week to the event
Welfare personnel was in possession of funds based on the admin budget at least 24 hrs before it was required
Adequate accommodation for team
Adequate transportation for team
Walkie talkie available, charged and used by team
Checklists printed, availabe and used by team
Logistics well thought through and managed for the team
New ideas and innovation for team welfare