## Contact Report
Meeting date: 3rd April 2018
Attendees: Phone call meeting between Ms Folake(Client) and Ronke Adeneye(GIW)
Event Date: 30th June, 2018
Event Time: 7am- 10pm
Event Venue: Akiita Hall and April Room Ilupeju
Item | Comment | Next Steps | Responsibility | Deadline | Update from meeting with Funmi(client's contact on 11/4/2018 in client's resident) | Next Steps | Responsibility | Deadline
Event look and feel | Fun and Glamourous. Guests should feel relaxed throughout the event. Client's event budget is N8million (which is subject to change) and theme is "little bit of old school ". For traditional wedding: calm, classy and Africanish | Design mood board for client to sign off | GIW | 13/4/2018 | - | *A mood board is not required as all the vendors have been communicated with and booked. *Communicate client's vision with vendors in charge of look and feel. | GIW | 17/4/2018
Guest size | 300/400. Age range is 25-70, comprising of family, friends and colleagues. | Plan to cater for 700 guests | GIW + Client | N/A | - | - | - | -
Invitations | Paper and E-invitations will be sent to guests and handled by the GIW. It must be vetted by Client's Father before it is sent out and should be ready as soon as possible. Not strictly by invitation | *Send invitation card designs to client for approval *Client to finalize on design | GIW | 13/4/2018 | "All A Bride Needs" is producing and printing 200 copies. Funmi will be distributing paper copy. | *Follow-up with Funmi to ensure design and context approval from client's father *Funmi to do an intro email between GIW and "All A Bride Needs". | GIW Funmi | 16/4/2018
Guest's experience | *GIW suggested a backdrop/step and repeat wall at the entrance *GIW suggested a photo-booth with polaroid cameras for guests to take pictures and print polaroids on site. GIW also suggested a guest book for kind words and photos to be placed in. *A little bit of old school themed Slomo video booth can also be considered *Hostesses were suggested to help manage guests experience during the event | *GIW to propose photo-booths and guest book to client | GIW | 13/4/2018 | *The venue space cannot accommodate a photoboth *GIW proposed photoprops and wish cards instead *Six hostesses have been engaged from Vudi Ushers to manage guest experience and their outfit will be Black dress on a silver shoe and a touch of purple. | *These will be communicated to the client and decisions will be made *Funmi to do an intro email between GIW and Vudi Ushers *GIW to request for pictures of the girls and their outfits from Vudi Ushers . | GIW Funmi | 17/4/2018
Décor | Candles and flowers as centre piece instead of elaborate flowers only | *Décor vendor to send décor mood board *GIW to follow up with décor vendor | 360 Events GIW | 17/4/2018 | *360 Events has been booked *Reservation cards will be printed by Funmi. | *Funmi to do an intro email between GIW and 360 Events and send the list of the deliverables agreed. | Funmi | 16/4/2018
Pyrotechnics | Smoke, fog, fire works, | *GIW to propose options of grand reception entrance *Client to give a feed back on how the entrance will look like | GIW Client | 13/4/2018 | The HSE Policy of the hall does not permit smoke in the hall. 360 Events will be making an interesting grand entrance for the couple. | *360 Events to share the grand entrance option with GIW. | GIW | 20/4/2018
Seating | 10 seater Banquet tables | *Confirm type of chairs and table available at the venue and share photos with client *Other options to be included in mood board *Options of seating styles should be included in mood board | GIW | 2018-11-04 | *Bride side and Groom side will be strictly adhered to. *Seating style option for the traditional has been concluded on. *GIW to propose seating style option for the reception | *Send seating style options to Funmi. | GIW | 21/4/2018
Catering | Client will want us to check with her sister, Funmi and welcomes recommendation for Menu. | *GIW to liase with Funmi on number of course meal, menu options, serving style, menu cards, chargers and cutleries *Contact Adetutu for Desserts | GIW | 2018-11-04 | Hafusat will be managing the food. Menu list is ready. For traditional wedding, small chops and beverage/water will be served. | *Funmi to do an intro email between GIW and Adetutu (vendor for dessert). | Funmi | 16/4/2018
Drinks | Client would like us to check with Mr Kola on this | GIW to liase with Mr Kola on types of drinks, serving style and glasswares | GIW |  | Alcohol will be served on request, while soft drinks and water would be served generally. | - | - | -
Lighting | 360 Decor would provide a purple, black and white a bit dim lightening | Contact 360 Events to share their lighting plan | GIW | 2018-11-04 | 360 Decor is providing both lighting, fogs and fire works. Funmi's trust is on 360 Events and GIW need not insist on items with them. Rather GIW should just follow up with them. | *Follow-up with 360 Events to ensure details of light are in check. | GIW | N/A
Overflow | The hall for traditional wedding would serve for overflow | *Propose a guest movement plan for the overflow *Design a seating style for the overflow as well as the logistics involved | GIW | 24/04/2018 | - | - | - | -
DJ | Songs with vulgar words should not be played. A requested song to be played during father and daughter's dance (one of Client's father favorite old school song). GIW provides an easy to learn short video for choreography for Client and her sister's dance. 'Who runs the world' by Beyonce should be played. it should be mixed with the ending part of Formation'. Dj ensures it is properly mixed and sent to the Client before the day. Yoruba and Phyno songs should be playing knowing it is a mix wedding. The parents should also not be left out of the music. Every age group should be considered. | Contact Mr Kola and communicate the client's wish | GIW | 2018-11-04 | *The choreography song will be changed. Funmi would like to avoid the client from being emotional. | *Get DJ's contact from Mr Kola *Mr Kola to do an intro email between GIW and DJ. | GIW Mr Kola | 21/4/2018
MC | Mr Kola is handling this | Contact Mr Kola to get the contact of the MC | GIW | 2018-11-04 | Mr Kola is incharge of MC. | *Get MC's contact from Mr Kola *Mr Kola to do an intro email between GIW and MC. | GIW Mr Kola | 21/4/2018
Surprise performance | No surprise performance or video will be done | N/A | N/A | N/A | - | - | - | -
Sound equipment | GIW should get a very good sound and equipment vendor | *Recce venue to confirm the sound items available *Get suppliers and get quotes to compare costs | GIW | 2018-11-04 | The Dj will be providing sound equipment. | *Recee venue with DJ. | GIW | 2018-02-05
Cake | Client contacted Splendidsplash for the traditional and reception cake. The traditional cake should be diced and shared during reception. | Follow up with Splendidsplash to further communicate client's vision | GIW | 2018-11-04 | Follow up with Splendidsplash to further communicate client's vision | *Funmi to do an intro email between GIW and SplendidSplash. | Funmi | 16/4/2018
Photographer | Client wants photographs to be excellently captured but not too pricey and is open to suggestions based on who we've worked with. | Propose photographers and share instagram handle with client to view work | GIW | 2018-06-04 | Michael Bolaji has been hired. | *Funmi to do an intro email between GIW and Micheal Bolaji. | Funmi | 16/4/2018
Videographer | Client is open to suggestions | Share options with client to view work | GIW | 2018-06-04 | Morgan Films has been hired. He must be reminded to come along with a USB Cord that is workable with Akiita hall projector. | *Funmi to do an intro email between GIW and Morgan Films. | Funmi | 16/4/2018
Security | Security should be considered | GIW to source and book security personel for the event | GIW | 30/4/2018 | Same as previously indicated. | - | - | -
Keepsakes | Client would like every adult to have a pack of keepsake. Keepsake must be durable and relevant in usage. Carrier bag | GIW to recommend and send photos of samples to client. | GIW + Client |  | GIW to provide a list of durable items within the budget of the client. | *Share options with Funmi. | GIW | 18/4/2018
Accomodation | Client welcomes recommendation from GIW. Hotel must be within Ilupeju. To cater for Bride, Groom, bride's maids and groom's men and atleast 10 guests that will be travelling down. Family will take care of themselves. | GIW to propose affordable accomodation around Ilupeju | GIW | 17/04/2018 | Funmi noted that the groom will have to take care of the accommodation for his out-statationed guests because he is not giving the information she needs to book the accommodation while she will book for the bride's guests . | *Follow up with Funmi to get contacts of hotel manager and follow up with the booking. | GIW | 20/4/2018
Transportation | Cars should be available for outstation guests | GIW to rent cars | GIW | 28/06/2018 | Rental of Coaster bus to convey guests from Akiita hall to church and back to the reception hall. | *Source for coaster bus, confirm availability and book. | GIW | 2018-02-05
Logistics | The description of the venue must be well communicated. Guest staying in the hotel must be enlightened about the hotel environ and also know how to Use Uber for movement.
Logistics | The description of the venue must be well communicated. Guest staying in the hotel must be enlightened about the hotel environ and also know how to use Uber for movement. | GIW to ensure address on invitation cards is well descriptive | GIW |  | - | - | - | -
Measurements for success 1. Excellent quality of food and food service, prompt service from all service providers and event organiser 2. Flawless and seamless event, food and drinks should always flow 3. Guests should feel relaxed throughout the day and have fun and should be well catered for 4. Great quality of all service providers 5. Great photos and memories captured. 6. All adult must be welcomed with a keepsake.