## Sheet1
Meeting date: 14th January 2017
Attendees:
Event Date: July 19th, 2017
Event Time: 7pm- 1:00am
Event Venue: Lagos Motor Boat Club, Ikoyi
Item | Comment | Next Steps | Responsibility | Deadline | 30th March updates & Food tasting | Most recent updates
Event look and feel | Casual, relaxed and fun, not stiff. Guests should feel relaxed throughout the event. Client's event budget is N5million and theme is "new school owambe". | Design mood board for client to sign off | No Surprises | 18th January | N/A | Client has finalized on this.
Guest size | 500. Age range is 30-60, comprising of family, friends, colleagues and professionals. | Plan to cater for 500 guests | No Surprises + Client | N/A | 600 realistic | 600
Invitations | Paper invitations will be sent to guests and handled by the client, indicating "new school owambe" as the dress code | Client to finalize and send invitations | Client | 30th April | N/A | All e-invitations have been sent by the client to guests
Branding | NS suggested a backdrop/step and repeat wall at the entrance but client doesn't want any branding | N/A | N/A | N/A | N/A | A wish wall with a selection of Mr Balogun's photos to be placed at the reception for guests to sign their best wishes
Guest's experience | - NS suggested a photo-booth with polaroid cameras for guests to take pictures and print polaroids on site. NS also suggested a guest book for kind words and photos to be placed in. - A dance motivator was suggested by Mrs Habiba Balogun to get guests excited during the after party and teach the guests old school dance moves and drummers to welcome guests - Hostesses were suggested to help manage guests experience during the event but client waved it off - Security was waved off as client said LMBC will handle | NS to find out great photo-booth and guest book suppliers and share with the client | No Surprises + Client | 7th February | Client no longer wants a photobooth and guest book. Client wants the drummers and a dance motivator | - A wish wall for clients to write their wishes for Mr Balogun - Dance motivator and drummers to be handled by client - Hostesses to be client's family and will be managed by the client (TBD) - Client to cater for security and parking through LMBC
Décor | Adire bunting and bunting lights across the venue, adire cushion covers for the rattan furniture at LMBC, | NS to suggest suppliers and share photos with the client | No Surprises | 7th February | N/A | - No more bunting lights. - Décor to include adire runners across the tables, tea light candles,local lamps. fish bowls with candles - Tree uplighting, partial adire draping across the tents - Paper lanterns
Seating | Informal, relaxed seating to comprise of some lounge furniture, cocktail tables and bar stools, some banquet tables for the older guests. LMBC has some furniture so some more will be brought in to supplement those already there. | Share photos of chairs and table types for the client to choose from. To be included in mood board | No Surprises | 7th February | Older guests will seat on banquet tables and others will be spread across cocktail tables and stools, lounge furniture and LMBC rattan furniture | Furniture: - LMBC Rattan furniture to seat 100 persons - 5 sets of lounge furniture - 40 cocktail stools and 15 cocktail tables - 30 rectangular tables for guests - 250 matrix chairs - 100 chiavari chairs
Catering | Client would like very good presentation of food, Nigerian Hors d'oeuvres presentated in a unique manner. KOTS was suggested and Chef Eros was suggested to provide some Nigerian hors d'oeuvres and dinner, client suggested Chef Tiyan. NS to source an additional caterer to complement Kemabom's catering provisions. Nigerian food to include small chops. Ram meat to also be provided | Source for good options for other caterers, present them to the client to choose from and agree on a date for food tasting | No Surprises | 26th April | Chef Benedict and Chef Imoteda both brough food for tasting in line with the theme. Mrs Habiba Baogun, Aziza Balogun and NS team gave comments. Chef Benedict was preferred | Chef Eros (hors d'oeuvres and Nigerian dishes)- 500 people, Chef Benedict - Dinner for 250 people TYKS (ofada rice, jollof rice and swallow) for dinner - 350 guests and 150 drivers food, SALT Lagos for dessert - 500 and Grind Grill for barbecue (chicken, ribs and asun)- 350 LMBC Restaurant - Hors d'oeuvres at 7pm and 11pm for 100
Drinks | Client would like cocktails served to guests and wants Eventi cocktails and any other recommendation. She'd want both to come in for a tasting as well. Client to provide alcoholic drinks | Recommend a second cocktails and mocktails supplier | No Surprises | 26th April | Eventi cocktails was finalized as supplier to serve cocktails and mocktails | - Eventi cocktails will be serving 300 cocktails and 50 mocktails - Alcoholic drinks from client - Uche - TBD - LMBC Bar - Non-alcoholic drinks and water
Lighting | Client would like some bunting lights and lighting by Dejour | NS to recommend another | No Surprises | 5th April | Dejour will be doing the lighting | Dejour will be doing the stage, sound, lighting, lighting inside the tents, food court and entrance/car park
Weather/Rain | Canopies and tents are not desired for this event, however because of it would likely rain on that day, a contingency plan is needed. Canopy/tents should be set up on the day. | Include canopies/tents in plan and budget | No Surprises | 7th February | 4 tents across the space will be mounted, taking into account the trees | 8 tents across the space will be mounted, taking into account the trees: - 20x40 (6) - 20x20 (2) - 10x15 (3)
Desserts | Client prefers Salt Lagos and would like a food tasting. | Brief Salt Lagos and get her to do something unique | No Surprises | After moodboard sign off | SALT Lagos will be serving desserts for 500 | SALT Lagos will be serving desserts for 500
DJ | DJ Obi was suggested as a possible DJ | Call and book the DJ for the date | Client to confirm who they prefer | After moodboard sign off | DJ Rude Boy was suggested by Dejour and booked | DJ Wayne has been selected as the preferred DJ for the event, briefed and booked. A playlist will be shared with him by 14th July
Entertainment | Beejay Sax was suggested by the client to perform during dinner before the after party. NS suggested a DJ instead due to the long period slated for dinner. King Sunny Ade (KSA) will be performing at the after party and has been booked by the client for the day | Connect with Dejour who has booked KSA already | Client + NS | 7th March | DJ Rude Boy has been booked | DJ Wayne will play during dinner(7pm-9pm) KSA during the after party - (9pm-11:30am) and then the DJ will take over till 1pm
Surprise performance | No surprise performance or video will be done | N/A | NS + Client | N/A | N/A | There will be no surprise video
Sound equipment | Dejour has already been contacted and is giving the client a good discount. Other options to be suggested by NS, but very good sound and equipment to be rented for the performances | Speak with other suppliers and get quotes to compare costs, client to introduce us to Dejour | NS + Client | 16th February | Dejour is handling stage, lights, screens and sound and dance floor | Dejour is handling stage, lights, screens and sound. There will be no dance floor
Cake | There will be no 50th birthday cake - Client to speak with Eros on getting a cake for them on the morning of the celebrant's birthday | N/A | N/A | N/A | N/A | Rosalitas will provide the cake, to be cut and shared with guests + popsicles
Photographer | Client wants photographs to be excellently captured but not too pricey and is open to suggestions based on who we've worked with | Share options of photographers showing work done with client to select In moodboard | No Surprises | 18th January | Ibukun Williams to handle photography | Ibukun Williams is the photographer for this event and he will be coming with a 3-man team.
Videographer | Client is open to suggestions | Share options and photos with client to select in moodboard | No Surprises | 18th January | Client does not want any videographer for this event | Client does not want any videographer for this event
MC | It was agreed that a friend or member of the family is preferred rather than a professional MC to keep the event informal and intimate | Client suggested her sister-in-law, Mrs Habiba Balogun to be the MC | Client | 7th February | Habiba Balogun will be the MC | Habiba Balogun will be the MC
Keepsakes | Client would like teabags and mugs and tote bags by Osione, wine bottles by the client's friend. NS to recommend and send photos of samples in the moodboard. | NS to find out other keepsakes and share with client | NS + Client | 5th April | Client to provide keepsakes: ankara bow ties, teabags and mugs and totes | Client to provide keepsakes: 600 tote bags, 600 mugs and teabags + scented sachets, 200 candles in boxes, 200 drawer liners for women
Other technicalities | Mistfans to be brought in if it gets warm at night | Include in the budget | No Surprises | 7th February | N/A | 26 industrial fans
Measurements for success 1. Excellent quality of food and food service, prompt service from all service providers and event organiser 2. Flawless and seamless event, food and drinks should always flow 3. Guests should feel relaxed throughout the day and have fun and should be well catered for 4. Great quality of all service providers 5. Great photos and memories captured.