## Sheet1
Activity | Time | Duration | Location | Cue | Responsibility
Pre set up | Before Mon 26th 6am |  | Barge, garden, everywhere | -Tech Crew (stage, sound, screens, lights) | All suppliers + NS team
- DJ
- Bands (Veentage and Cobhams)
- Caterers
- Venue designers
- Rentals (AC, generator, mobile toilets, chairs, tables, etc)
Set up | 6am - 3pm | 9 hours | Barge, garden, everywhere | Full tech team (Cobhams band, Veentage band, artiste managers, MC, photographer, videographer) | Seun, Demola
Final sound checks + final systems check | 10am to 3pm | 7.5 hours | Barge + Garden | -Guest list/Tablet | Seun, Demola, Mirian, Umi, Mr. Wale, Nwaru, Nora, Esther
-JAT's den
-Cocktail tables on pool
-Security
-Signage positioned
-Welcome personel/- Guest Experience Team
-Men in raincoats + umbrellas if it rains
-Band on the barge
-ou d'oeuvres/Drinks/Cocktails
-Hostesses/Waiters/bartender
-Veentage
-Photographer/Printer/Paper/ Photo lights/video
- LASTMA, Umbrella boys, Guest management team, MOPO
Doors open | 5:55pm to 6:00pm | 5mins | Main Gate/Home entrance | -Veentage band | Full NS Team
-Garden ambience lights
- Technical team/lights/sound
- Guest Experience Team/Hostesses
- ou d'oeuvres
- Veentage band
-Cocktail
- Technical team
- JAT's Den personnel, wishes notes and badges, photographer + team + printer + paper
-Catering team/waiters/napkins/trays etc
Guests arrive to background music from band playing on the barge/Hellos, ou d'oeuvres, drinks, cocktails and photographs (JAT’s den) | 6.00pm to 6:50pm | 50mins | Garden/On the pool/JAT's den | - Guest Experience Team/Hostesses | Mirian, Umi, Seun, Demola, Chinwe, Esther, Felicia, Steph O, Orby
- Veentage band
-Table names/menu cards/colour codes
-Microphones and sound
-Cocktail/waiters/bartenders
- Technical team
-Ambience lights/full decor
- Photographer + team + printer + paper
-Ou d'oeuvres/catering team/waiters/napkins/trays etc
-Cake table/cake/knife
-Order cards on table, menu cards
Guests proceed to barge for dinner/Hostesses get guests to make food selection/colour | 6:50pm to 7:00pm | 10 mins | Barge | - Guest Experience Team/Hostesses | Hostesses, Mirian, Orby, Umi, Seun, Demola, Esther
- IK's mic
- Plated meals/drinks on standby
- Technical team
- Photographer
- IK
-Colour coded envelopes
IK welcomes guests on barge/explains service, colour codes etc and interacts with guests/First course is served | 7.00pm to 7:10pm | 10 mins | Barge | - Guest Experience Team | Seun, Demola, Chinwe, Orby, Esther, Wale, Juliannah
-Lots of waiters/bartenders/Drinks team
- Hostesses
- Veentage band
- Photographer/videographer
More music from the band, guests’ interaction (low background music) Food/drinks is served/More music from Veentage band | 7.10pm to 8:00pm | 50 mins | Barge | - Guest Experience Team | Seun, Demola, Chinwe, Debbie, Wale, Juliannah, Orby, Felicia
-Lots of waiters/bartenders/Drinks team
- Hostesses
-All team to clear tables
-Desserts
- IK
IK comes back for more interaction/desserts is served | 8:00pm to 8:15pm | 15 mins | Barge | -Guests giving the speeches | Seun, Demola
-Microphones
- IK
-Mrs. Bola Tinubu, Dr. Iyabo Tinubu-Karch, Mr. Demola Akerele
-Champagne in every glass for toast
IK introduces speeches, Speeches to follow by 1.Mrs. Bola Tinubu, Dr. Iyabo Tinubu-Karch, 2. Mr. Demola Akerele to give the toast | 8:15pm to 8:30pm | 15 minutes | Barge | -Photographer/Videographer | Seun, Demola, Esther,
Fireworks display | 8:30pm to 8:35pm | 5 mins | Barge | - Cobhams band | Seun, Demola
-Full team in garden
-Cake
-IK
IK announces movement more music (Cobhams band) | 8.35pm to 8:45pm | 10 mins | Barge | - Cobham's band | Seun, Orby, Chinwe, Mr. Wale, Jullianah
- Hostesses
- Artisan team/small chops
-Maldesa/Drinks/Coco to go
-Cake
IK welcomes guests back to the garden/Small chops/drinks is served | 8.40pm to 8:45pm | 5 mins | Garden | - Tinubu kid | Chinwe, Debbie, Wale, Seun, Demola, Felicia
-Mic
-Cake knife
-Cake
IK introduces Tinubu kid to introduce dad to cut cake/cutting of the cake/Photos with friends and family | 8:45pm to 8:55pm | 10mins | Garden/Top of pool | -AV team | Seun, Demola, Uncle Lolu, Cobhams sound
-Video montage
-Sound
IK introduces video/15-minute video presentation/montage | 8:45pm to 9:00pm | 15 mins | Garden/Top of pool | - AV Team | Seun, Demola, AV team
- TT Troupe
-Full Cobhams band
-Stage lights and light effects
-IK/IK's mic
IK returns to interact? Give the TTT some time to get into the act?/Introduces a special guest performance | 9:00pm to 9:05pm | 5 mins | Garden | - AV Team | Seun, Demola
- TT Troupe
-Full Cobhams band
-Stage lights and light effects
-Sound and mics
Surprise presentation by The Tinubu Troupe/ JAT to join TT on the stage probably to do a song together? | 9:05pm to 9:25pm | 20 mins | Garden | - All celebrities artistes in green room | TTT, Seun, Demola
-All band members
IK interacts with guests and announces celebrity artistes | 9:25pm to 9:30pm | 5 mins | Garden | - Celebrities in green room | MC, Seun, Demola
-Wande Coal
-All band members
-After party food Woot to eat/Maldesa
- Transition music person?
Wande Coal performs | 9:30pm to 9:50pm | 20 mins | Garden | - DJ Obi | Seun, Demola, performers
- Glowsticks
-Ram Barbecue
IK comes back/band change | 9:50pm to 9:55pm | 5mins | Garden | - Runtown and band | Seun, Demola, performers
Run town performs | 9:55pm to 10:05pm | 10 mins | Garden | - IK | Seun, Demola, performers
IK comes back/band change | 10:05pm to 10:10pm | 5mins | Garden | - Wande Coal and band | Seun, Demola, performers
Reekado Banks performs | 10:10pm to 10:25pm | 15mins | Garden | - IK | Seun, Demola, Orby, Mirian, performers
- Hostesses
IK comes back and announces movement back to barge + after party/movement | 10:25pm to 10:30pm | 5mins | Garden | - DJ Bola Freshwaves | Seun, Demola, Chinwe, Felicia, Mirian
- Hostesses
- Guest experience team
-Ram barbecue
DJ Bola Fresh waves performs/party food/ram barbecue/drinks + Guest Dance | 10:30pm to 11:45pm | 1hr 15mins | Barge | - Full party lights (to confirm) | Seun, Demola, Chinwe, DJ
- DJ Obi
- Catering/Drink services
- Waitstaff
- Kemabom/Breakfast/trays
DJ Obi takes over//party food/ram barbecue/drinks + Guest Dance | 11:45am to 2:00am | 2hr 15mins | Barge | -Guests/drinks | Seun, Demola, Felicia, Debbie, DJ
-All food and drinks
-Full crew and team
- DJ Bola Freshwaves
DJ Bola Fresh waves performs/party food/ram barbecue/drinks + Guest Dance | 2:00am to 3:15 am | 1hr 15mins | Barge | - Full party lights (to confirm) | Seun, Demola, Chinwe, DJ
- DJ Obi
- Catering/Drink services
- Waitstaff
- Kemabom/Breakfast/trays
DJ Obi takes over//party food/ram barbecue/drinks + Guest Dance | 3:15am to end | till dawn | Barge | -Guests/drinks | Seun, Demola, Felicia, Debbie, DJ
-All food and drinks
-Full crew and team
- Gifts (if not already on table)
- Kembom
Breakfast is served! | 4.00AM | 1 hour | Barge |  | Chinwe, Felicia,