## Contact Report
Meeting date:
Attendees:
Event Date:
Venue:
Item | Comment | Next Steps | Responsibility | Deadline | Next steps
What
Objective
Theme/concept Ideas
Event look and feel
Venue design
Guest size/Guest management
Seating
Catering
Drinks
Lighting
CEO class of 2017 photoshoot
Team photo ops
Desserts
DJ
Entertainment
Other Entertainment
Surprise performance
Sound equipment
Video
Guest management
Photographer
Videographer
MC
Invitation Card
Traffic and parking
Other props and LED wristbands
LED dance floor, balloon drop, disco ball
Photobooth
Greenroom
Keepsakes
*Measurement for success* 1.Strong/creative event concept and execution 2. Unforgetable guest experience 3. Flawleess/seamless production 4. High profile attendees 5. Sales of no less than 60 tables 6. Excellent guest management /concierge service 7. Excellent and prompt service from all service providers (Food and drinks served on time, plates cleared after guests have finished eating, attention to guests' needs and attention to detail) 8. Innovative idea presentation 9. Clients should be relaxed throughout the planning process and on event day, feel comfortable to sit and mingle with guests knowing that all is being taken care of by the organisers 10. Quality of service providers/partners

## I2E Doc
IDEA to EXECUTION Process Document (12E Doc)
DONE
Stage | Tasks | Deadline | Responsible | Status | Comments | IN PROGRESS
Engage + Initiation | [5 empty] | LATE
| Receive event brief from client. Notify CM/Do an intro email |  | Anyone/All
| Send/reply intro email, attaching corporate profile, website link and questionaire. Follow up with phone call. |  | CM
| Client fills the form and/or responds to the email |  | Client
| Prepare list of questions based on the form respoGIWes and client brief |  | Anyone/All + CM
| Schedule first meeting with client to discuss event brief and identify stakeholders. |  | CM
| Prepare contact report and: Share with client, including clear next steps for both GIW and client Share with team, including clear next steps for each department and/or individual |  | CM
| Prepare professional fees with finance, share with JB for approval |  | CM
| Obtain JB’s feedback/sign off |  | Finance + CM
| Send approved professional fees quotation to client |  | Finanace
| Negotiate, review quotation and identify areas for adjustment |  | Finance + CM + Client
| Issue invoice and contract to the client |  | Finance
| Send client receipt acknowledge payment and communicate admin budget cap to TE |  | Finance
| PT is introduced to client and officially brought into the loop |  | CM
Ideation
| Schedule brainstorming with team |  | CM
| Draft a word/text document of the ideas generated from the team brainstorming and send to JB within 48 hours |  | CM
| Obtain JB’s feedback/sign off |  | CM
| Develop word document into prezzy and share concept design with client |  | CM
| Client gives feedback/signs off |  | Client
Implementation
| Send approved prezzy to PT to generate a quotation |  | CM
| Prepare workplan |  | PT
| Send client the workplan schedule with timelines and evaluation criteria |  | CM
| Create PSD for JB’s approval. Create M.Doc as well. |  | PT
| Request for costs from vendors, put together initial quote and share with Accounts |  | PT
| Send internally approved quotation to client (1 week after) and reminder for 20% balance payment |  | Finance
| Negotiate, review quotation and identify areas for adjustment |  | PT + Finance
| Issue invoice and reiterate vendor clause in the contract |  | Finance
| Client pays of ALL fees (100% of vendor fees and and 20% balance of professional fees) |  | GIWE
| Share admin budget with Accounts department |  | TEX
| Give a bargaining margin and payment policy to PT to use to negotiate with their vendors. |  | Finance
| Approve admin budget |  | Finance
| Send a formal brief to selected suppliers and book them |  | PT
| Ideate with suppliers. Meet with them if necessary and tap into their creative minds. |  | PT
| Request for quotes from vendors. Relay payment plan with them as communicated by Accounts team. |  | PT
| Negotiate costs with vendors along with the Accounts Team. |  | PT
| Request for reviewed invoices and share with Accounts. |  | PT
| Prepare vendor schedule, get FINAL invoices from PT and process payment |  | Finance
| Ensure that deposits are made to vendors after client makes payment. |  | PT
| Actively manage vendors and receive constant progress on their work progress. Share all necessary creatives with them. |  | PT
| Share weekly project progress and updates with CM to share with the client. |  | PT
| Act as client liaison in sending designs, weekly updates, samples etc. for sign off. |  | CM
| Request list of event personnel for set up and D-Day and prepare ID (wristbands/tags) |  | PT
| Conduct walkthrough/production meeting with all event stakeholders. Identify issues and solutions. |  | PT
| Ensure master document has been properly populated (nothing left out) and share production schedule with vendors. |  | PT
| Facilitate in-house production meeting. |  | PT
| Manage event team to ensure all tasks are done according to timeline and expectations. | Leading up to the event | PT
Event Live!
| Ensure all vendors, suppliers, GEMs are at the venue at pre-agreed time |  | PT
| Ensure all event staff are properly accredited and that they follow GIW Partner Guide. |  | PT
| Use task checklist to ensure that vendors have delivered all that was promised/agreed on. |  | PT
| Conduct final run-through and security checks. |  | PT
| EVENT LIVE! Supervise vendors during the event, manage the event flow, identify issues before they bloom and troubleshoot them. |  | PT
| Manage and ensure proper event shut down THEN sleep! #ToWhatEnd |  | PT
Closure
| Send thank you note, evaluation form and schedule post mortem meeting with client (48hrs after) |  | CM
| Facilitate in-house post-event meeting to discuss event. |  | PT
| Send feedback emails/forms and/or thank you cards to vendors and suppliers. |  | PT
| Share evaluation forms with contacts in all the companies in attendance/all guests |  | PM
| Send post event meeting report to client (48hrs after) |  | PM
| Create report from internal post event meeting and share with team. |  | PT
| Send post event deliverables to the client i.e. videos/photos/drinks (depending on nature of the event) |  | PT + CM
| Process balance payments to vendors as agreed after client pays balance. |  | Finance
| Ensure Accounts makes balance payments to vendors as agreed after client pays balance. |  | PT
ON TO THE NEXT ONE!

## Client work plan
The UX Party Workplan | [5 empty] | Done
Category | Tasks | Responsibility | Deadline | Status | Comments | In the process
Late Task
Archival | Send event briefs and request for costs
Confirm Photographer and Videographer for entire event
Make a photography list of shots
Agree on list of photoshots with client and share with supplier
Branding | Determine venue branding, way finders, signages etc.
Shortlist branding company (s) based on needs
Send brief and request for costs from shorlisted company
Present design creatives with FVO for approval
Catering and Beverages | Finalise menu
Determine drinks/ cocktails/sponsorships/needs
Co-ordinate food and drink tastings with client (if necessary)
Decor/Venue Design | Agree theme/direction for décor
Determine/obtain floor plan for dinner area, party area, stage, CEO lounge, cocktails area etc.
Shortlist decor company based on needs
Send brief and request for costs from shorlisted company
Finalise decor pieces,placement and general look and feel
Entertainment | Determine MC and/or comedian
Book and finalise talks with all talent.
Schedule and hold briefing with FVO and MC
Determine set up times and soundcheck and share with talent managers.
Event day | Set up, event goes live and tear down
Event flow | Determine event flow; awards, raffle draw, performances, lipsync battle mashup, photos for Employee of the Year Awards photos for winners etc.
Determine games and competitions among the companies,etc.
Share draft event flow with Stage Manager for finetuning + creation of cue sheet
Recieve finalised event flow and share with FVO for final approval + implementation
Event Management | Share moodboard with FVO
Request for costs from suppliers to aid creation of budget
Share suppliers quote with client + finance team
Agree on suppliers quote
Get final budget sign off from client
Finances | Create vendor schedule of payment
Agree on payment terms and communicate to all vendors/suppliers
Guest Experience Management | Populate the guest list
Audition for hostesses
Final selection, briefing and training of hostesses
Determine and finalise on outfits for hostesses
Determine guest experience management processes and procedure and assign managers
Commission the production/purchase (where necessary) of outfits
Finalise on seating plan using guest list
Logistics | Finalise all accommodation, feeding and transport plans for the team and create admin budget document accordingly
Determine support staff (casual staff + temps) needs and hire additional staff as is needed
Post Event | Post event meeting with client
Share videos from the event with client/stakeholders
Share pictures from the event with client/stakeholders
Print Production | Determine invitation style/concept
Formally brief creative agency (InkHearts) based on FVO's needs to request for quote/design
Present first draft of invitation creatives to client for approval
Deliver invitations to the office
Deliver invitations to the guests
Production Meeting/Walkthrough | Conduct an event walk-through with tech and design suppliers and troubleshoot
Conduct an event walk-through with all suppliers and troubleshoot
Conduct production meeting on site with FVO, NS team and suppliers
Rentals | Determine rental needs
Shortlist rental company (s) based on needs
Send brief and request for costs from shorlisted company
Security/Parking | Brief and book security company
Souvenirs/Goody Bags | Determine gift items for goody bags, gifts, brochures etc
Technical | Determine Technical director
Brief Technical Director on Event Objective
Determine technical needs, stage positions, lighting, sound requirements etc
Ensure stage manager is briefed and has the event flow/program
Obtain all riders from entertainers and share with sound company + TD
Agree terms and possible partnerships with venue; sign contract
Venue | Pay 1st installment of venue cost
Pay 2nd installment of venue cost
Pay 3rd installment of venue cost
Pay 4th installment of venue cost
Venue recce with suppliers
Pay final installment of venue cost

## Supplier contact sheet + Accred
Supplier Contact Sheet + Accreditation
Category | Service | Name of Company | Contact person | Formal Engagement Yes or No? | Final Invoice received? | Next steps | Comments | Cell phone number | Total crew on site | Crew for set up | Crew for live event | Agreed arrival time | Actual arrival time
Archival
Entertainment
Technical
Catering
Beverage
Rentals
Venue design
Guest Experience
Designs and Printings
Keepsakes
Media
Security
Internet

## Signage planner + Printing brea
Directional/Event info signage Breakdown
Location | Text for Signage | Signage style | Dimension
Landmark Main Gate | Welcome to The Unofficial Christmas Party (logo) #PartyInWhite #CelebrateWhatYouDo #TheUxParty | Branding Wall | 8 by 8ft wall
Drop off | The Unofficial Christmas Party (logo) Drop Off here #TheUXPartyInWhite
Check In Area | Check In Here A, B-J, K-N, O, P-Z #TheUXPartyinWhite | Match Box
Check In Area | Executive Check In Here
Coctail/ Red Carpet Area | Sip, Socialize and Pose for the Camera Here #TheUXPartyinWhite | Match Box
Dinner Area | This way to the Dining Area: Let's Celebrate and Eat #TheUXPartyinWhite
After Party | Turn Up in White Here #TheUXPartyinWhite | On the the tunnel wall
VIP Entrance to The After Party | Silver Wristbands Only | A5 landscape foam board
Regular Entrance to the After Party | Black Wristbands Only | A5 landscape foam board
Restroom | This way to the restrooms | A5 landscape foam board
Printing breakdown
Item | Content/Text | Dimension | Quantity
Invitation cards + Envelopes
Menu cards |  | A5 card
Table names |  | 4.5inches by 11inches Tent Card
Table numbers |  | A5 card
Table number cards for guests |  | Complimentary card
Gift redeeming vouchers |  | Complimentary card
Table Place Cards
Wristbands
Envelope for menu options
Wristband color coding
Menu option cards
Internet cards |  | Complimentary card
Access cards + Envelopes (Blue, White and Purple)
Gift vouchers |  | Complimentary card
Gift Bags
Placards |  | 1 by 2 feet
Employee of the year certificate |  | A4 Card
Badges
Backdrops
Notes for Cinematics | [Logo]- Do your best shoki, Jiggle all the way, Who run the world?! Girls, Sparkle like you mean it, Cheers to the team. | Complimentary card
Welcome notes + envelopes |  | Complimentary card
Wrapping papers
Ribbons
VIP parking stickers |  | 3 by 6 inches
Cue Card |  | A5
Branding Break down

## Event flow
Event name:
Event date:
Set up time:
Sound check time:
Event time:
Activity | Time | Duration

## Event Cue sheet
Event name:
Event date:
Set up time:
Sound check time:
Event time:
Activity | Time | Duration | Location | Music | Lighting/Effect | Cue/Props | Responsibility | Comments

## Venue readiness checklist
Venue Readiness Checklist
Location | Activity | Requirements | Props/Décor | Personnel | Company/Supplier responsible

## Team task allocation
Role | Description | Team member | Team member questions | Daily Update by team member in charge | Next Steps
Stationery/collateral/Welfare
Stationery, Invitations, Table numbers, Table no allocation, Menu cards, client/vendor wristband, wristbands,crew tags, colour coding, invitation delivery and documentation. Work with whoever is in charge of press to ensure the right number of crew tags are printed, same goes for suppliers. Make sure they are handed over to the people in charge of accreditation Determine team needs days before the event, feeding, hotel accommodation etc. Ensure you source for the best options and negotiate, ensure all plan are seamless. Manage all that the team need for onsite office, secure the room in advance and ensure that all needs are met. Manage admin template and ensure all teams fill out their needs before set up/event day.
Security/Parking+ Venue Readiness
Determining number of personnel, positioning, outfits/uniform specification, entry processes/flow, troubleshooting, damage control,personnel alignment with the different wristbands and boundaries Ensuring that set up is completed and the venue is ready in due time. Create venue readiness checklist and production schedule and ensure it is adhered to.
Technical/Talent Management/Event Flow/Stage Production
Be the contact person between Dr Yemi/tech suppliers and NS. Ensure all quotes are received and compiled in time to make a decision, ensure all that is finalised and agreed on is delivered Design event flow incorporating all the elements as sold to guests, ensure all is aligned and communicate with Dr Yemi Laiase with all talent and have all their contact details, manage all their schedules and arrival times, ensure they are comfortable and are backstage on time for their performace, work closely Dr. Yemi
Guest Experience and Management
Detailed and well thought through check in process to limit guest wait time to a minimum, ensuring the welcome area is well lit especially when it gets dark, ensuring there are at least 6 check in points with cue breakers, seating and seats assignments, templates and processes for guest experience/usher appraisal, photobooth sourcing, props, placards and placement, gift/voucher sourcing, picking up of vouchers and pitching to prospective partners, handling invitations and distribution to guests, team competition logistics and coordinating with show producer Determine number of ushers and auditions, outfits design and sourcing, make up and personal hygiene, training, event alignment and venue orientation
Press/PR/Achival (Photography and videography)
Compile shot list and share with FVO, Confirm all photographers and play to their strengths, ensure all necessary shots are captured for social media and PR, Ensure there is a dedicated photographer for red carpet, ensure there is adequate lighting for the red carpet
Venue Design/Decor and branding
Venue design, mood board, Floor planning, chair selection and sourcing, table setting, VIP/CEO lounge planning, tablescaping, napkins, napking rings, centrepieces, table and chair alignments, cocktail area, photobooth, bar placing, props etc.
Sponsor/Partner Management and Gifting Logistics
Obtain all agreements with sponsors and ensure all agreements are met in terms of logo usage on media wall, magazines etc. Liaise with sponsors before event day to ensure there is alignment especially with vouchers and gifts etc. Ensure all raffle tickets have a process and this is clear and communicated with all concerned. Ensure sponsors get their data capture and database for those that apply as agreed. Ensure there is brand visibility for all brands however without compromising on TUCP's image and venue design...no roll up banners! Ensure sponors are given their mentions as agreed post event, in the magazines, on the media walls etc as agreed
Food and Beverages
Obtaining the menu for food and desserts, finalising with the suppliers and designing the menu, designing artwork and getting sign off, ensuring they are printed on time and align with brand values, confirm all arrangements with suppliers Taking stock of all drinks and ensuring they are properly stored and chilled, put proper process in place to secure drinks Hans and Rene Cafe Neo Chef Benedict Salt Lagos Kots Catering Artisan Grind grill Diageo Lucky cocktails
Proposals, sales and invoicing, Accounting
Ensuring prospects get the appropriate documentation/invoicing on time, following up to ensure all payments are made on time

## Production Schedule
Event :
Load in on:
START DATE | DAY | START TIME | END TIME | TASK/ACTION | TEAM MEMBER RESPONSIBLE | SPECIAL NOTES | LOCATION | ORGANISATIONAL RESPONSIBILITY

## List of shots
Major aspects to capture:
A. SETUP DAY | Capture event setup day, photo of *The hall in its empty state *The hall after partitioning into different areas without furniture arrangement *The different areas being set up with furniture arrangement *The different areas without decor and technical *The different areas being set up with decor and technical elements *GIW team during set up
B. EVENT DAY | Capture event day, photo of
1. All hostesses dressed up
2. Each group of hostesses positioned at their different areas.
3. GIW crew together, before the event goes live.
4. The venue without guests (aerial or panorama).
5. All security in position
6. Check-in area *Guests during check-in process. *Hostesses during check-in process. *Guest list verification. *Photos of arriving guests. *Up close photos of a hostess attending to/receiving a guest.
7. Guest interacting with the tunnel
8. Capture moments at the red carpet/cocktail area. *Team photos of each company *Guests photos on red carpet *Team photos with set design
9. Dining Area *Employee award *Lipsing battle *Grand Pianist and area
10. After Party *Dancefloor with guests dancing

## AdminBasecampTeam Hospitality
Basecamp request sheet
Event name:
Event date:
Project Manager:
Basecamp location:
Event time:
Item | Quantity | Requester | Comment
TV SCREENS & STANDS | -
PRINTER
A4 PAPER
STAPLER & STAPLE PIN
CREW TAGS
EXTENSION CABLE/CABLE REELS
CLIPBOARDS
INTERNET
SCISSORS
VENDORS WRISTBAND
PENS
MARKERS
HOSTESS NAME TAG JACKETS
TABLE NUMBER | -
RESERVED SIGNS
CELLOTAPE
TABLE NUMBER STANDS | -
LETTER LABELS
COCKTAIL TABLES/CHAIRS | -
CUE BREAKERS | -
TABLE COVERS
FIRST AID BOX
EXTRA WALKIE TALKIES
Umbrellas
Kettle
BIN BAGS
HOSPITALITY SCHEDULE, EVENT DAY.
CALL TIME
ONSITE OFFICE/BASE CAMP
| TIME | BATCH 1 | BATCH 2 | BATCH 3
MEAL 1 (20 minutes)
MEAL2 (20 minutes)
CHANGING SHIFTS (30 minutes)
ACCOMMODATION PLAN
TEAR DOWN/GO HOME:

## Guest management + casual staff
GEMs and supervisor allocation
Quantity | Location | Task | GEM | Supervisor/NS team member | GEM contact/phone number
2 | Just before the check-in point | Direct guests to their assigned check-in table
7 | Regular check-in area | Check and highlight guest's names on the provided computer
Wear wristbands for guests
3 | VIP check-in area | Check and highlight guest's names on the provided computer
Wear wristbands for guests
1 | Entrance of the tunnel | Direct guests to the cocktail area
3 | Cocktail area (After cocktails and guests have moved into the dining area, the GEMs will move into the afterparty area to welcome afterparty guests and ensure they are served) | Ensure guests are served and direct guests to video booth
Ensure guests are served and direct guests to the "Celebrate your 2017" wall
Ensure guests are served and direct guests to photo props and photo area
1 | Stage - MC's assistant | To assist the MC on stage with gifts and any other thing
1 | Green room | Ensure the artistes are well taken care of
65 | Dining Area (A GEM to be assigned to a table) | Ensure every person on the designated table is well taken care of | Table 10 -
Table 11 -
Table 12 -
Table 13 -
Table 14 -
Table 15 -
Table 16 -
Table 17 -
Table 18 -
Table 19 -
Table 20 -
Table 21 -
Table 22 -
Table 23 -
Table 24 -
Table 25 -
Table 26 -
Table 27 -
Table 28 -
Table 29 -
Table 30 -
Table 31 -
Table 32 -
Table 33 -
Table 34 -
Table 35 -
Table 36 -
Table 37 -
Table 38 -
Table 39 -
Table 40 -
Table 41 -
Table 42 -
Table 43 -
Table 44 -
Table 45 -
Table 46 -
Table 47 -
Table 48 -
Table 49 -
Table 50 -
Table 51 -
Table 52 -
Table 53 -
Table 54 -
Table 55 -
Table 56 -
Table 57 -
Table 58 -
Table 59 -
Table 60 -
Table 61 -
Table 62 -
Table 63 -
Table 64 -
Table 65 -
Table 66 -
Table 67 -
Table 68 -
Table 69 -
Table 70 -
Table 71 -
Table 72 -
Table 73 -
Table 74 -
2 | Extras
Total = 85 GEMs
Afterparty GEM Allocation (To be chosen from the 85 GEMs)
10 | Afterparty
Casual Staff

## Gifts
Gift/memorabilia | Gift/memorabilia type | Gift/memorabilia instructions

## Invitation Distribution Record
Invitation Distribution Record Sheet
Delivered
Not Delivered
Individual/Company Name | Individual/Company Address | Contact Person Taking Delivery | Phone No of Contact Person | Content of Invitation Suite | Courier Company | Dispatch Date | Delivery Status | Comment

## Planning status
Team Status Update
Done
Pending
Category | Tasks | Responsibility | Deadlines | Status | Comments | Late
Finance and Budgeting
Prepare/draft costs estimates
Obtain real costs based on industry price
Break costs down based on sponsorship ideas
Facilitate negotiations to save costs
Raise the necessary cheques and communicate terms of payment to all suppliers/partners
Table sales & sponsorships
Table Sales | Articulate value add to guests, new and improved additions to 2015 edition and table/add on costs
Draft/Prepare letters for prospects and get sign off
Create prospect list for table sales
Send emails/newsletter to prospects A and B, starting with A first
Follow up emails with phone calls where applicable and get some form of committment and create a list /table as you engage prospects
Table sales end
Sponsorship drive | Create a table/articulate sponsorship opportunities
Send emails/letters to shortlisted prospective companies with detailed and clear requests and ROI
Follow up letters/emails with phone calls
Create a document of sponsors who have gone on board and list all the deliverables both ways
Design/create agreements and send to sponsors
Engage the accounts departement to sync
Sponsorship souvenirs sourcing
| Determine the different opportunities for gifting |  |  |  |  | 22
Create a list of gifting companies we can partner with
Engage/meet with them to share value proposition
Confirm all arrangements and document all agreements
Guest Experience Management
Team selection/audition/job desciptions based on deliverables | Create job profiles based on role needs
Place ad/call for audition
Selection of team members
Create training materials and train selected team members
Set up process for monitoring team members managing the different accounts
Guest management | Determine which team member manages what account
Communicate changes and plans to the team as they come and standby to be creative as challenges arise
Hostesses outfit | Share ideas for outfit for hostesses
Confirm and finalise final outfit, source and obtain costs
Obtain invoices, sign off and make necessary payments
Guest experience | Determine fun ideas and activities for guests
Share thoughts and ideas with team
Make a selection and obtain a quote
Order the necessary props as early as possible
Take delivery of the props
Goody bags | Work with team to determine number of goody bags and when they'd be available
Determine strategy for gift distribution and advise as necessary
Plan for transportation of the gifts to the venue and storage
Assign distribution of gifts to hostesses
Venue Management
Check for hall availability and book the venue
Obtain invoice and terms of agreement
Thoroughly go through the terms and raise any issues/concerns
Ensure deposit is paid against the venue to secure the booking
Confirm set up lines and communicate our plans to venue as they change to ensure alignment
Make complete payment
TUCP Campaigns
Identify the different campaigns
Break down the tasks for each campaign
Assign the different roles and ensure all deliverables are met on time
Venue layout & design
Study overall presentation of the event to have an understanding of the venue layout
Create a floor plan based on event flow and get a sign off
Share plans and ideas with venue designers and send a formal brief stating the different areas, functions and needs
Receive feedback and initial ideas from venue designers
Schedule first site meeting for a walk through
Share venue designer's ideas with team and send feedback
Obtain quote/invoice from supplier
Negotiate and reach an agreement with the supplier
Work with accounts to make a deposit payment
Agree and communicate with the venue designers the set up times and any other info from the venue managers
Schedule pre event sampling of every aspect of the venue layout
Communicate changes and plans to the team as they come and standby to be creative as challenges arise
Schedule final site meeting
Supervision of all supplies and construction for the venue layout
Source for industrial confetti blaster and/or bubble thrower
Catering & tablescaping
Catering | Confirm guest estimate
Contact KOTS the caterer for a discussion on event brief, menu and budget determination
Obtain menu from KOTS based on the budget communicated and sign off with FVO
Confirm/agree costs with KOTS and obtain invoice
Work with accounts to pay a deposit against the costs
Schedule first site meeting for a walk through
Confirm/agree on logistics and planning on site with KOTS
Communicate and changes and plans to the team as they come and standby to be creative as challenges arise
Schedule final site meeting
Tablescaping | Determine style and needs
Shop around for rental companies that can provide plates, cutlery, chargers and napkins of high quality
Schedule inspection of the rentals to ensure they are of the best quality and that we have enough
Obtain quote and negotiate based on market rate and budget
Confirm and agree on logistics and transportation etc
Make a deposit payment
Make final payment
Drinks & Bar
Source for drinks company and send them a VERY CLEAR brief, please include cocktails for pre event
Decide who to go with depending on quote, quality of service, experience and overall presentation
Meet with supplier to discuss the detailed logistics
Schedule first onsite visit
Make payment deposit
Communicate changes and plans to the team as they come and standby to be creative as challenges arise
Schedule final onsite visit
Talent engagement and management
Shortlist and determine the different artistes and performers
Confirm the acts based on availability and fit
Make enquiries on availability and costs
Negotiate and agree on costs based on available funds and budget
Obtain invoices from all performers
Make deposit payments
Send a detailed brief to all talent informing them of the expectations and timing
Communicate changes and plans to the team as they come and standby to be creative as challenges arise
Determine green room needs and obtain a quote also determine which rooms to allocate
Technical/Stage Production
Shortlist technical production company
Determine mobile screen company
Determine company or sponsor for plasma screens for Bond effect
Send a detailed brief to all technical crew based on the needs as created in the presentation
Obtain quotes from all technical team based on needs
Negotiate and agree terms based on budget
Draft an agreement will all technical companies including deliverables
Make deposit payment
Schedule a first site visit
Schedule a final site visit
Cue sheet and event flow
Create a draft event flow based on event elements
Meet with the technical director to see how the event flow works against what is expected
Create a cue sheet and sign off with team
Ensure all the elements work and all the performers are aligned
Archival
Photography | Determine photography needs
Source and speak to different photographers and make a presentation of your top 3 with your personal selection and why
Finalise on choices and send a more detailed brief to the photographers
Work with the GEMs to ensure group/company photos are well organised, create schedules as companies purchase tables
Videography | Book videographer
Meet with video team and agree on overall theme and style of the video
Communicate changes and plans to the team as they come and standby to be creative as challenges arise
Team welfare/Admin
Study event tasklist and determine team member roles
Create a document/table to show who needs to be where at what time to determine needs
Draw up a budget based on the needs and discuss with accounts for approval
Communicate changes and plans to the team as they come and standby to be creative as challenges arise
Ensure team mates are well taken care of so they can be productive without distractions
Ensure team mates are well taken care of so they can be productive without distractions
Security + Traffic
Discuss with team to determine security and traffic needs for the event
Source different security companies and shortlist/ present your top 3 to the team with reasons
Select security and traffic team and obtain invoices to present to accounts
Schedule a walkthrough of the venue with the heads of the security and traffic team
Send a very detailed brief to the service provides detailing deliverables and time
Ensure execution is as planned
Inter company competitions
Discuss with team to determine the various competitions
Discuss ways to communicate the info to the companies/attendees
Brainstorm on appropriate prizes for winners
Make a list of all the prizes for the evening to help organise for sponsorship partners
Make a list of all the participating companies as they register, work with the GEMs on this

## Decor Cost Breakdown
Areas | ITEMS | UNIT COST | QUANTITY | SUB TOTAL
Registration Area | Table Cover | 1000 | 6 | 6000
| Skirting | 10000 | 1 | 10000
| Centerpiece | 5000 | 1 | 5000
| Red Carpet | 0 | 1 | 0
Cocktail/Red Carpet | Cocktail Tables | 8000 | 6 | 48000
| Coctail Table Covers | 1000 | 6 | 6000
| Center Piece | 2000 | 6 | 12000
| Red Carpet | 0 | 1 | 0
Dining Area | Table Linen | 1000 | 65 | 65000
| Centerpiece with candles | 5000 | 65 | 325000
| Flower arrangements | 2000 | 65 | 130000
VIP Lounge | Drapes on Cabana | 30000 | 1 | 30000
Entire Hall | White on black drapes to cover the panels around the venue | 700000 | 1 | 700000
| Rental of lift for draping (Set up & Tear down) | 50000 | 2 | 100000
| Transportation | 70000 | 1 | 70000
| Service charge | 250000 | 1 | 250000
Total |  |  |  | 1757000
ITEMS | UNIT COST | QUANTITY | SUB TOTAL
Napkins
Napkin Rings
Charger Plates
Wine Glass
Water Glass
CutlerIies

## Guest Activity
Guest Activity Tracking Sheet
S/N | Name of Company | Table Number | Checking in in seconds | Champagne with candy floss on arrival | Cocktails and canapes at red carpet | Red carpet photos | Team photos | Guest experience card (“5 senses”) | All 3 course meals | Desserts | Wine and soft drinks/Water | Gourmet after party snacks and champagne at after party | Gourmet after party snacks and champagne at after party | Hamper at check out
1 | No Surprises Events | 11
2
3
4