## Sheet1
Meeting date: 17th March, 2018
Attendees: Micheal Ogunoye, Ayo Omosehin, Kolade Ojo, Ronke Adeneye, Julianah Balogun
Event Date:24th March, 2018
Event Time: 7am- 3:00pm
Event Venue: Faith Plaza, Lagos
Item | Comment | Next Steps | Responsibility & Contact | Deadline | Questions/Concerns
Venue | Trad: -White: -Reception
Event look and feel | Casual, relaxed and fun, not stiff. Guests should feel relaxed throughout the event. Theme is
Guest size | Size: Age range: | Plan to cater for ____ guests
Invitations |  |  |  |  | Is the event strictly by invitation -Do we have a guest list -Have the invitations be printed -Has distribution started -Is there any other freebies attached to the invitation -Are there specially invited guests
Branding & Signages |  |  |  |  | Are there going to be way finders -If yes, have they been printed -If no, can it be incorporated -Signages needed are indicated in the way finder sheet
Guest's experience |  |  |  |  | Are we having any guest engaging activities -How many hostesses are we using and who is handling that -Has the hostesses outfit been decided on -Do we have guest list
Décor |  |  |  |  | Have we contracted a décor vendor -Has the decorator been properly briefed -What call time was given to the vendor and what was the duration of setup given
Seating | Informal, relaxed seating to comprise of some lounge furniture, cocktail tables and bar stools, some banquet tables for the older guests. LMBC has some furniture so some more will be brought in to supplement those already there. |  |  |  | What seating style are we using/has a seating style been concluded -Are we using the chairs from the venue or we are renting -Would you require special seats for some particular people
Catering | Client would like very good presentation of food, Nigerian Hors d'oeuvres presentated in a unique manner. KOTS was suggested and Chef Eros was suggested to provide some Nigerian hors d'oeuvres and dinner, client suggested Chef Tiyan. NS to source an additional caterer to complement Kemabom's catering provisions. Nigerian food to include small chops. Ram meat to also be provided |  | No Surprises | 26th April
Drinks | Client would like cocktails served to guests and wants Eventi cocktails and any other recommendation. She'd want both to come in for a tasting as well. Client to provide alcoholic drinks | Recommend a second cocktails and mocktails supplier | No Surprises | 26th April
Lighting | Client would like some bunting lights and lighting by Dejour | NS to recommend another | No Surprises | 5th April
Rentals | Canopies and tents are not desired for this event, however because of it would likely rain on that day, a contingency plan is needed. Canopy/tents should be set up on the day. | Include canopies/tents in plan and budget | No Surprises | 7th February
Security | Client prefers Salt Lagos and would like a food tasting. | Brief Salt Lagos and get her to do something unique | No Surprises | After moodboard sign off
DJ | DJ Obi was suggested as a possible DJ | Call and book the DJ for the date | Client to confirm who they prefer | After moodboard sign off
Entertainment | Beejay Sax was suggested by the client to perform during dinner before the after party. NS suggested a DJ instead due to the long period slated for dinner. King Sunny Ade (KSA) will be performing at the after party and has been booked by the client for the day | Connect with Dejour who has booked KSA already | Client + NS | 7th March
Surprise performance | No surprise performance or video will be done | N/A | NS + Client | N/A
Sound equipment | Dejour has already been contacted and is giving the client a good discount. Other options to be suggested by NS, but very good sound and equipment to be rented for the performances | Speak with other suppliers and get quotes to compare costs, client to introduce us to Dejour | NS + Client | 16th February
Cake | There will be no 50th birthday cake - Client to speak with Eros on getting a cake for them on the morning of the celebrant's birthday | N/A | N/A | N/A
Photographer | Client wants photographs to be excellently captured but not too pricey and is open to suggestions based on who we've worked with | Share options of photographers showing work done with client to select In moodboard | No Surprises | 18th January
Videographer | Client is open to suggestions | Share options and photos with client to select in moodboard | No Surprises | 18th January
MC | It was agreed that a friend or member of the family is preferred rather than a professional MC to keep the event informal and intimate | Client suggested her sister-in-law, Mrs Habiba Balogun to be the MC | Client | 7th February
Keepsakes | Client would like teabags and mugs and tote bags by Osione, wine bottles by the client's friend. NS to recommend and send photos of samples in the moodboard. | NS to find out other keepsakes and share with client | NS + Client | 5th April
Other technicalities | Mistfans to be brought in if it gets warm at night | Include in the budget | No Surprises | 7th February
Measurements for success 1. Excellent quality of food and food service, prompt service from all service providers and event organiser 2. Flawless and seamless event, food and drinks should always flow 3. Guests should feel relaxed throughout the day and have fun and should be well catered for 4. Great quality of all service providers 5. Great photos and memories captured.

## Sheet2
Mr Afolabi Balogun's 50th Birthday Party Work Plan
Done
Ongoing
Late task/Pending
Category | Tasks | Responsibility | Deadline | Status | Comments
Event Management | Share Mood board + Professional fees + Letter of Engagement with client | NS | 19th Jan |  | These were all shared before the due date
| Client signs off on ideas and agrees on professional fees | Client | 30th Jan |  | Client approved the ideas but has made some changes to decor and doesn't want some elements. Professional fees have received sign off and have been paid
| Payment of first instalment of Professional fees | Client | 30th Jan |  | First instalment paid
| Sign the contract/Letter of engagement | Client | 7th Feb |  | This has been signed and signed copies have been returned to us
| Agree on suppliers quote and payment instalments | NS + Client | 8th Feb |  | Additional costs are being considered
| 2nd Instalment of professional fees to be paid | Client | 11th April |  | Paid in full and on time
| Last instalment of professional fees to be paid | Client | 8th June |  | Paid in full and on time
Catering and Beverage | Finalise dessert options with client and share scope of work (SoW) with suppliers | NS + Client | 5th April |  | Client and NS have agreed on options and cost
| Finalise on drinks options and costs | NS + Client | 26th April |  | Client and NS have agreed on options and cost
| Finalise on menu options with client and share with suppliers | NS + Client | 5th April |  | Client has approved catering options and they have been communicated with suppliers
| Finalise the costs for food | NS + Client | 26th April |  | All costs for food have been finalized
Décor | Do a walk through of the venue with the decor vendor | NS | 12th July |  | Walkthrough has been conducted
| Finalise decor pieces and placement | NS + Client | 12th July |  | Client has approved and finalized on decor pieces and placement
| Client to sign off on all materials to be printed + graphic designs | NS + Client | 14th July |  | NS to share all graphic design options and get client sign off
Entertainment | Book DJ Wayne | NS | 5th April |  | He has been booked and will be paid by July 14
| Client shares the contact of her preferred MC | Client | 26th April |  | Mrs Habiba Balogun is the MC
| Finalise on artistes booking | NS + Client | 11th April |  | KSA has been booked and payment made
Event day | Set up, dress rehearsal, event goes live and tear down | NS + Suppliers | 18th - 19th July |  | Set-up to commence on Tuesday 18th, dress rehearsal and event goes live on the 19th and tear down and complete venue clean-up on the 19th.
Guest Experience Management | Finalise on style of hostess' outfits with client | NS + Client | 8th June |  | Client to confirm her bringing her own hostesses, outfit options and get a preference from client.
| Meet with client to finalise on seating plan using client's guest lists | NS + Client | 12th July |  | NS to work with client on guest list and assign seating plan
Production Meeting | Do a final run through at the production meeting | NS + Client + Suppliers + Stake holders | 12th July |  | Production meeting with client, NS and all suppliers.
| Client sign off on final event documentation i.e. list of photo shots, event flow/cue sheet + live décor presentation | Client + NS | 14th July |  | - Decorator has arranged a live presentation of table setting for client's approval. - Client to approve shots list for photography - Client to approve favorite artists and songs for the DJ, NS to draw up DJ's playlist
| Final dress rehearsal with technical director | MC + NS | 18th July |  | Dress rehearsal with MC
Security/Parking | Meet with CSO to plan marine security, bouncers, LASTMA, discuss logistics for drop offs and parking | NS | 18th July |  | To ensure a flawless experience with parking, drop off and security for guests, a meeting with client's CSO to sync plans is inevitable.
Technical | Share suppliers quote with client | NS | 7th Feb |  | An estimate was drawn and shared with client on February 7. Supplementary budgets were shared and approved.
| Finalise all arrangements with the technical supplier | NS + Client + Supplier | 12th July |  | All arrangements have been discussed with Dejour
| Payment of suppliers' quote | Client | 8th June |  | Payment has been made
Venue | Technical venue recce | NS | 15th March |  | NS co-ordinated this process
| Share draft floor plan with client | NS | 13th July |  | This will be shared with the client on July 13 following changes to seating plan.
| Sign off on final floor plan | Client + NS | 14th July |  | The final floor plan to be signed off by client after implementing all tweaks
Archival | Share portfolios of photographers with client | NS | 8th June |  | This has been done
| Retrieve client's final selection of photographer, book supplier and share a list of photography shots | Client | 14th July |  | Awaiting client's final selection
| Share pictures from the event | NS | 26th July |  | Pictures of event to be shared with client.
Post Event | Post event meeting with client | Client + NS | 21st July |  | A meeting with client and NS to evaluate event and get feedback on NS performance and achievement of client's KPI