## Sheet1
PENDING TASKS / DELIVERABLES
S/N | TRACK RESPONSIBLE | DELIVERABLES | TASK NAME | ASSIGNEE
1 | DESIGNERS | Remove "stories" from the header
2 |  | Take out username from the profile
3 |  | Under settings, people shouldn't be able to change their names
4 |  | Add a space for user bio (more like about the author) on the profile
5 |  | Input field for confirm password on the sign up page
6 |  | New header without the "Get started" button for people who are logged in
7 |  | 3 cards instead of 2 on the blog page
8 |  | Cards on the pricing page should be smaller, alignment issues, resizing of elements
9 |  | Year and day on the billing page should be in the same input field
10 | FRONTEND | Profile image should display initials. | Bugs and Fixes | Christopher
11 |  | All logo icons should redirect to home |  | Christopher
12 |  | Remove username from signup input |  | Christopher
13 |  | Add an input field for 'confirm password' |  | Christopher
14 |  | Fix the broken FAQ link on the footer |  | Christopher
15 |  | Implement premium feature, pricing and billing section |  | James
16 |  | Trigger confirmation modal when you try to delete an account from user settings | Implement confirmation modal | Christopher
17 |  | Redesign Landing Page |  | Okiki
18 |  | Add a background to the active navigation | Admin sidebar fixes. (See the implementation on the [non] user dashboard)
19 |  | Increase the click-area on each navigation
20 |  | Add a border-right to the active navigation
21 |  | Increase the click-area on each navigation
22 |  | Rebuild the settings page and connect it to the endpoint | Rebuilding Settings Page | Kareem
23 |  | [Archived users] Fetch the list of archived users, and remove the user status [premium/free] column from the table. | Implement archived users | Taddy
24 |  | Dashboard] From the list of users, an admin should be to click on the “archive” option |  | Taddy