## Project Roadmap
PRODUCT ROADMAP |  |  | START MONTH |  | 2019-01-01
Marketing Project | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
| 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01
Website | 2019-01-01: Mobile App Design and Development; 2019-04-01: Optimize for Mobile; 2019-07-01: E-commerce Dev; 2019-10-01: E-commerce Update
|  |  |  | Purchase Flow |  |  | Rebrand Update |  |  | Funnel Optimization
Blog Design Update
SEO/SEM | 2019-01-01: SEO Audit; 2019-04-01: SEO Optimization; 2019-07-01: Social Media Campaign; 2019-10-01: SEO Review
| SEM Audit |  |  | SEM Campaign |  |  | Blog Campaign |  |  | SEM Review
SEM Campaign
Advertisment | 2019-01-01: Facebook Ads; 2019-04-01: Bing Ads; 2019-07-01: Third Party Lead Generation; 2019-10-01: YouTube Ads
| Google Ads |  |  | Display Ads Creative | [5 empty] | Mobile Ads
Email Ads
DevOps | 2019-04-01: Geo-replication; 2019-07-01: Access Firewall Integration; 2019-10-01: Disaster Recovery Testing
Security Audit
Testing | 2019-04-01: Automated Test Framework; 2019-07-01: Automated Testing; 2019-10-01: Automated Testing