## WBS Spreadsheet
Milestone | Task ID | Task | Owner | Duration (days) | Notes
Establish a plant delivery and logistics plan | 1.1 | Source materials for packaging | Fulfillment Director
| 1.2 | Hire delivery drivers | Human Resources Specialist
| 1.3 | Calculate the delivery fees. | Financial Analyst
Select and install supply chain management software and equipment | 2.1 | Supervise vendor setup of inventory management and fulfillment software | Inventory Manager
| 2.2 | Supervise vendor installation of fulfillment equipment | Inventory Manager
| 2.3 | Determine internal safety protocols for the equipment | Quality Assurance Tester
Develop and launch an employee training program | 3.1 | Develop training sessions | Inventory Manager
| 3.2 | Train employees to use the software and equipment | Training Manager
| 3.3 | Monitor progress and improve training processes | Training Manager