## Tasks and Timeline
S/N | Task | Notes | Start Date | Due Date | Duration | Task Owner | Status | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[8 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[8 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Milestone: Choose Tablet Vendor
1.1 | Source Tablet installation vendor |  |  |  | 1
1.2 | Choose service package |  |  |  | 1
1.3 | Generate quotes and review costs |  |  |  | 2
1.4 | Engage Tablet installation vendor |  |  |  | 1
1.5 | Create contracts and statements of work for vendors |  |  |  | 1
2 | Milestone: Tablet Installation
2.1 | Shipping and receiving Tablets |  |  |  | 10
2.2 | Software installation |  |  |  | 3
2.3 | Infuse ordering process into tablets |  |  |  | 1
2.4 | Integrate tablet software with existing host software and POS system |  |  |  | 10
2.5 | Upgrade the POS system if S&S is running an older version |  |  |  | 5
2.6 | Include menu item add-on feature and coupons |  |  |  | 9
2.7 | Wire the tables | Check with electrician on whether mornings or afternoons work better with their schedule. Notify GMs when their locations need to close for wiring |  |  | 5
2.8 | Enable GPS location services on each tablet |  |  |  | 1
2.9 | Create a procedure for securing tablets at the end of the night (at the table or in a safe) |  |  |  | 2
2.11 | Create messaging about payment portal security to display on the tablets |  |  |  | 1
3 | Milestone: Staff Training
3.1 | The preparations and planning for the trainings |  |  |  | 9
3.2 | Staff meeting to introduce the concept of the Tablet |  |  |  | 1
3.3 | Management training |  |  |  | 1
3.4 | FOH staff training and BOH staff training for location 1 (Include payment security talking points in waitstaff training) |  |  |  | 1
3.5 | FOH staff training and BOH staff training for location 2 (Include payment security talking points in waitstaff training) |  |  |  | 1
3.6 | Train the staff to update the menu |  |  |  | 1
4 | Milestone: BOH staff Recruitment
4.1 | Send out vacancies for open roles |  |  |  | 1
4.2 | Interview applicants |  |  |  | 3
4.3 | Hire two part time cooks |  |  |  | 3
5 | Milestone: Branding and Layout
5.1 | Connect the Sauce & Spoon marketing team with Terrific Tablets for branding |  |  |  | 2
5.2 | Update the menu interface to match the branding and layout of our menus |  |  |  | 2
6 | Milestone: Pre Launch Tablet Testing
6.1 | Invite family and friends for test run before launch |  |  |  | 2
6.2 | Implement a post-dining survey to assess customer satisfaction |  |  |  | 2
6.3 | Implement survey feedback |  |  |  | 10
7 | Milestone: Create a launch day plan: staffing, troubleshooting, etc. |  |  |  | 5

## Task Brainstorm
Task Brainstorm
Task | Notes | Estimated Duration (Days) | Optimistic | Most Likely | Pessimistic | Confidence Rating (H/M/L) | Known Dates
Milestone: Choose Tablet Vendor
Source Tablet installation vendor |  | 1 | 1 | 1 | 3
Choose service package |  | 1 | 1 | 1 | 3
Generate quotes and review costs |  | 2 | 2 | 2 | 4
Engage Tablet installation vendor |  | 1 | 1 | 1 | 3
Create contracts and statements of work for vendors |  | 1 | 1 | 1 | 3
Milestone: Tablet Installation
Shipping and receiving Tablets |  | 10 | 8 | 7 | 15
Software installation |  | 3 | 3 | 2 | 5
Infuse ordering process into tablets |  | 1 | 1 | 1 | 3
Integrate tablet software with existing host software and POS system |  | 10 | 8 | 7 | 15 | L
Upgrade the POS system if S&S is running an older version |  | 5 | 5 | 3 | 7
Include menu item add-on feature and coupons |  | 9 | 7 | 5 | 14
Wire the tables | Check with electrician on whether mornings or afternoons work better with their schedule. Notify GMs when their locations need to close for wiring | 5 | 5 | 2 | 8 | H
Enable GPS location services on each tablet |  | 1 | 1 | 1 | 3
Create a procedure for securing tablets at the end of the night (at the table or in a safe) |  | 2 | 2 | 2 | 4
Create messaging about payment portal security to display on the tablets |  | 1 | 1 | 1 | 3
Milestone: Staff Training
The preparations and planning for the trainings |  | 9 | 8 | 5 | 14 | M
Staff meeting to introduce the concept of the Tablet |  | 1 | 1 | 1 | 3 | M
Management training |  | 1 | 1 | 1 | 3 | M
FOH staff training and BOH staff training for location 1 (Include payment security talking points in waitstaff training) |  | 1 | 1 | 1 | 3 | M
FOH staff training and BOH staff training for location 2 (Include payment security talking points in waitstaff training) |  | 1 | 1 | 1 | 3 | M
Train the staff to update the menu |  | 1 | 1 | 1 | 3 | L
Milestone: BOH staff Recruitment
Send out vacancies for open roles |  | 1 | 1 | 1 | 3
Interview applicants |  | 3 | 3 | 2 | 5
Hire two part time cooks |  | 3 | 3 | 2 | 5
Milestone: Branding and Layout
Connect the Sauce & Spoon marketing team with Terrific Tablets for branding |  | 2 | 2 | 2 | 4
Update the menu interface to match the branding and layout of our menus |  | 2 | 2 | 2 | 4
Milestone: Pre Launch Tablet Testing
Invite family and friends for test run before launch |  | 2 | 2 | 2 | 4
Implement a post-dining survey to assess customer satisfaction |  | 2 | 2 | 2 | 4
Implement survey feedback |  | 10 | 8 | 7 | 15
Milestone: Create a launch day plan: staffing, troubleshooting, etc. |  | 5 | 5 | 3 | 7

## Additional Resources
Additional Resources
Title | Link | Date Added | Notes

## Quality and Evaluation
Quality and Evaluation
Quality Standards | Quality Standards
Category | Criteria/Description | Evaluation Questions | Evaluation Indicators | Criteria Met?
Customer Satisfaction | Average ticket time for entrees 15miuntes | Do customers have to wait longer than 15mins for their entrees tickets to be attended to? | " Guests with shorter ticket wait times meet up with the 30mins table turn over time | FALSE
| Average ticket time for appetizer 8 minutes | Do customers have to wait longer than 15mins for their entrees tickets to be attended to? | " Guests with shorter ticket wait times meet up with the 30mins table turn over time | FALSE
| Lobby wait time of under 10 minutes | Do customers have to wait more than 10mins before beign attended to? | Guests with shorter wait times report wanting to return 20% more often than those with longer wait times | FALSE
| 98% order accuracy | Are customers receiving the correct orders? | 98% of customers who use tablets receive the correct order | FALSE
| One minute check out time | Are the check-out process seemless? | Check out time is pegged at one minute max | FALSE
| Increase customer retention in tablet areas by 5% | Are customers having a better dining experience with the tablets? | Guests who use the tablets are 50% more likely to recommend the restaurant to a friend | FALSE
FALSE
Ease of Use | 5% or less technical issues report by customers on tablet usage | Do all the tablets work as expected? | Tablet error logs report a maximum of one error per shift | FALSE
| 90% of customers should be able to navigate tablets easily | How quickly are customers learning how to navigate the tablets? | Average check out time shows one min | FALSE
FALSE
Functionality | 20% Increase in staff work performance | To what extent do tablets increase work performance? | What number of side works are staff able to complete during a shift | FALSE
| 98% decrease in error logged on tablets functionality | Are the tablets functioning properly | Tablet error logs report a maximum of one error per shift | FALSE
| 90% tablet functionality for wait staff | To what extent do tablets increase work performance? | Waitstaff can log into their tablet accounts on the first try | FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Survey Questions
Survey Questions
Quality Standards |  |  |  |  | Question Answer Options (depends on question type)
Criteria/Description | Evaluation Questions | Evaluation Indicators | Survey Question | Question Type | Option #1 | Option #2 | Option #3 | Option #4 | Option #5
Average ticket time for entrees 15miuntes | Do customers have to wait longer than 15mins for their entrees tickets to be attended to? | " Guests with shorter ticket wait times meet up with the 30mins table turn over time | How long did your dinner take tonight? | Multiple choice | 10-20mins | 20-30mins | 30-40mins | 40-50mins
Average ticket time for appetizer 8 minutes | Do customers have to wait longer than 15mins for their entrees tickets to be attended to? | " Guests with shorter ticket wait times meet up with the 30mins table turn over time | How long did your dinner take tonight? | Multiple choice | 10-20mins | 20-30mins | 30-40mins | 40-50mins
Lobby wait time of under 10 minutes | Do customers have to wait more than 10mins before beign attended to? | Guests with shorter wait times report wanting to return 20% more often than those with longer wait times | How long did you have to wait in the lobby before getting a seat. | Multiple choice | 0-5mins | 5-10mins | 10-20mins | 20-30mins
98% order accuracy | Are customers receiving the correct orders? | 98% of customers who use tablets receive the correct order | Was your order delivered accuratley? | Yes/No | Yes | No
One minute check out time | Are the check-out process seemless? | Check out time is pegged at one minute max | You were able to check out in less than one minute? | True/False | TRUE | FALSE
Increase customer retention in tablet areas by 5% | Are customers having a better dining experience with the tablets? | Guests who use the tablets are 50% more likely to recommend the restaurant to a friend | How would you rate your dining experience tonight? | Scaled | 1 (Poor) | 2 (Fair) | 3 (Good) | 4 (Very Good) | 5 ( Excellent)
5% or less technical issues report by customers on tablet usage | Do all the tablets work as expected? | Tablet error logs report a maximum of one error per shift | Did you encounter any difficulty while using the tablet? | Open-ended | Write your response here
90% of customers should be able to navigate tablets easily | How quickly are customers learning how to navigate the tablets? | Average check out time shows one min | How quickly were you able to navigate the tablet? | Scaled | 1 (Slowly) | 2 (Fairly) | 3 (Quick) | 4( Very Quickly)
20% Increase in staff work performance | To what extent do tablets increase work performance? | What number of side works are staff able to complete during a shift | How many side works are you able to complete during a shift | Multiple choice | 2023-01-05 | 2023-06-10 | 2023-11-15 | 16 | 20
98% decrease in error logged on tablets functionality | Are the tablets functioning properly | Tablet error logs report a maximum of one error per shift | How many errors did you log in while using the tablets | Multiple choice | 1 | 2 | 3 | 4 | 5 and above
90% tablet functionality for wait staff | To what extent do tablets increase work performance? | Waitstaff can log into their tablet accounts on the first try | How many attempts did you take to log into your account? | Multiple choice | 1 | 2 | 3 | 4 | 6 and above